Lecture 4. Communication Management, Leadership, and Project Team Management

1. Communications Management
2. Communication Types
3. Leadership Skills
4. Leadership Styles and Servant Leadership
5. Creating a Project Culture
6. Developing and Managing a Project Team [Oguz]

1. Communications Management
Projects require teamwork, and team members must communicate with each other in a variety of ways. The documents they produce must be collected, distributed, and stored in an appropriate manner to assure timely and accurate communication between team members. This process is often assisted by a variety of technologies including computer and smartphone software programs and applications. The advent of the Internet accompanied by various ICTs (Information and Communication Technologies), and the emergence of the COVID-19 pandemic by the end of 2019 accelerated the process of digitalization for people, and all organizations including the companies, multinational corporates, non-governmental organizations, governments, and international bodies. Thus, the adoption and spread of ICTs worldwide across organizations and countries increased exponentially. The use of global virtual teams in organizations increased to unprecedented levels. 94% of the respondents of CultureWizard’s Global Virtual Work Survey indicated that employees want to continue working from home—at least part time. More virtual presence has brought about new challenges.
ICTs can facilitate faster and better communication, or they can become a barrier if they are not well understood and applied appropriately. The project manager and the team should be in ongoing contact with all the stakeholders based on their power and interest levels, and other factors such as influence, involvement, support required, and interdependencies. This necessitates the manager to choose an optimal portfolio of communication technologies and methodologies. Therefore, these issues should be well-thought by the project manager while preparing the project plan and its subcomponent “Project Communications Management Plan”.
Communication Management Plan
Communications management is about keeping everybody in the loop. The communications planning process concerns defining the types of information we will deliver, who will receive it, the format for communicating it, and the timing of its release and distribution. Hence, it is of high importance to make sure everybody gets the right message at the right time.
All projects require a sound communication plan, but not all projects will have the same types of communication or the same methods for collecting, analyzing, and distributing the information. The communication plan documents the types of information needs the stakeholders have, when the information should be distributed, how the information will be delivered with which frequency, who will receive it, and the format and technologies we will use to communicate.
First off, we should figure out what kind of communication our stakeholders (including the project team) need so they can make good decisions and they are well-informed. This is called the communications requirements analysis. Our project will produce a lot of information, so we don’t want to overwhelm the stakeholders with all of it. Our job is to figure out what they feel is valuable.
Therefore, the stakeholder power/interest grid (matrix) and the stakeholder engagement assessment matrix would be very helpful to determine the priorities of each stakeholder, and how we can communicate with each of them, Communicating valuable information doesn’t mean we always paint a rosy picture. Communications to stakeholders may consist of either good news or bad news. The point is that we don’t want to bury stakeholders in too much information but we do want to give them enough so that they’re informed and can make appropriate decisions. ICTs have a major impact on how we keep people in the loop. Therefore, our analysis and the plan should include them.

Task 1. Learn about the stakeholder power/interest grid (matrix). Be prepared to present your findings in class.

We should answer the questions below in our communications management plan:
1. What are the methods of communicating that we need to consider? Which methods can we choose to transfer information?
Ex.: written reports, conversations, email, formal status reports, meetings, online databases, online schedules, and project websites.
2. How should we arrange the timing of the information exchange or need for updates? What is the reporting frequency for each stakeholder according to the expectations and concerns of stakeholders?
3. Who is the person responsible for communicating the information? Who authorizes the release of confidential information?
4. Who receives the information according to their needs, expectations, and concerns?
5. Do we need to procure (purchase) new technology or systems, or are there systems already in place that will work?
6. What is the experience of our staff with the technology? Are there project team members and stakeholders experienced at using this technology, or should we need to train them?
7. How does the project team function? Are they located together or spread out across several locations in a country or the world?
8. What are the resources, time, and budget allocated for communication activities?
The answers to these questions should be documented in the communication plan. Keep in mind that all the components of a project management plan are interrelated. A communication plan cannot be prepared independently of other components such as the plans for the scope, schedule, cost, risk, and stakeholders. For example, concerning ICTs, we should consider if the technology we are choosing would work throughout the life of the project or we should upgrade or update it at some point.
The types of information we will communicate typically include project status, project scope statements and updates, project baseline information, risks, action items, performance measures, project acceptance, and so on. We should also consider the language, format, content, and level of detail. The information needs of the stakeholders must be determined as early in the planning phase of the project management life cycle as possible so that as we develop project planning documents, we already know who should receive copies of them and how they should be delivered.

2. Communication Types
The communication management plan should address the needs, expectations, and concerns of the project team and the stakeholders by considering the communication types. Completing a complex project successfully requires good communication among team members. If those team members work in the same building, they can arrange regular meetings, simply stop by each other’s office space to get a quick answer, or even discuss a project informally at other places like meeting rooms and even in the kitchen and next to the coffee machine. Many projects are performed by teams that interact primarily through electronic communication and are, therefore, called virtual teams. However, virtual interaction has been exponentially prevalent for many organizations and collocated project teams. To avoid miscommunication that can harm trust and to include team members in a project culture, the project team needs a plan for communicating reliably and in a timely manner. This planning begins with understanding two major categories of communication – synchronous and asynchronous.

Synchronous Communications
If all the parties to the communication are taking part in the exchange at the same time, the communication is synchronous. The following are examples of synchronous communications:
In-person meetings: This is the traditional meeting method used by collocated teams. Some virtual teams may also prefer in-person meetings several times (e.g., kick-off and closing meetings) during the project life cycle to socialize and build trust.
One-on-one and conference phone (audio) calls: These calls would be effective if there is an urgent need to meet, and participants are not available for video calls.
Video conferences: These meetings have prevailed with the widespread use of virtual teams and the emergence of the COVID-19 pandemic. Online tools such as Skype, Zoom, Google Meet, and WhatsApp are used for video conferences.
Integrated solutions such as Microsoft Teams: Teams can use synchronous communication tools such as video conferences and instant messaging, and they can share the files with other team members (asynchronous).
IM (instant messaging): Team members can exchange text or voice messages on computers and mobile devices. They can also have group pages on which more than two members can chat and share documents, pictures, and videos. IM may not be synchronous all the time, and it provides an opportunity for the team members to reply later, and keep the records of the chat logs.

Asynchronous Communications
Getting a team together at the same time can be a challenge—especially if they are spread out across time zones. Many types of communication do not require that the parties are present at the same time. This type of communication is asynchronous. There are several choices of asynchronous communications such as mails and faxes. Recently, asynchronous communication has also been transferred mostly to online communication. In many projects, there is a need to deliver mails and packages to other team members or sub-teams, and stakeholders in different locations. Physical signatures can be still demanded to comply with the legal requirements. However, online tools have been allowing people to sign electronically, which is also legally acceptable (e.g., Adobe Acrobat, DocuSign). Therefore, this provides time and cost-saving opportunities to the project teams. Electronic mail (email) is widely used to coordinate projects and for the communication and collaboration between team members and with stakeholders. Emails have several valuable characteristics for project management. Information can be sent to a list of team members. Messages can be saved to document the process in case of a misunderstanding or miscommunication. Files can be attached and distributed.
The communication management plan should include a protocol that delineates all the critical communication channels for the team and stakeholders, such as the purpose of communication, ICTs utilized, frequency of communications, and types of information to be communicated. An example of a Communications Management Protocol has been provided in Table 6.1 which includes only four purposes of communication.

3. Leadership Skills
Project managers, as leaders, spend 90% of their time communicating with team members and stakeholders. Therefore, communication is the most important leadership skill a project manager should possess, but not the only one. Project managers need a large number of skills which include administrative skills, organizational skills, and technical skills associated with the technology of the project. The types of skills and the depth of the skills needed are closely connected to the size and complexity of the project. This is why each project needs tailoring according to various factors including the purpose, objectives, business field, size, complexity, and stakeholders. Although project managers always need to possess interpersonal skills to communicate and collaborate effectively with the team members and stakeholders, on smaller, less complex projects, they need a greater degree of technical skills. On larger, more complex projects, project managers need more organizational skills to deal with the complexity.
PMBOK Guide 6th Edition differentiates among three skill sets project managers should possess – technical project management, leadership, and strategic and business management. Contrary to the name as is referred to as technical, it doesn’t indicate the skills regarding product and industry expertise. This expertise is included inside strategic and business management skills. PMBOK Guide highlights this skill set as “technical project management skills”, and defines them as the skills to effectively apply project management knowledge to deliver the desired outcomes for projects and programs. Organizations look for project managers who are competent in implementing a systematic project management approach applying the right artifacts and methods to achieve the project objectives. Accordingly, project managers should be able to define critical success factors for the project, create plans for all the knowledge areas (i.e., integration, scope, schedule, cost, quality, resource, communications, risk, procurement, stakeholders), create, manage and monitor the project team, conduct all project management processes, monitor and control all the project work, close out the project, and disband the team. Besides, project managers should have the capability to decide which development approach would be the best for the project. Therefore, they should know the development approaches including traditional (waterfall or predictive) and agile (adaptive) tools, techniques, and methods. As indicated, strategic and business management skills include developing and applying pertinent (relevant, appropriate) product and industry expertise. They involve the ability to see the high-level overview of the organization and effectively negotiate and implement decisions and actions that support strategic alignment and innovation. This ability may include a working knowledge of other functions such as finance, marketing, and operations. This business knowledge is also known as domain knowledge .
The third skillset, leadership skills, involves the ability to guide, motivate, and direct a team. Leadership is defined as a social (interpersonal) influence relationship between two or more persons who depend on each other to attain certain mutual goals in a group situation. Effective leadership helps individuals and groups achieve their goals by focusing on the group’s maintenance needs (the need for individuals to fit and work together by having, for example, shared norms) and task needs (the need for the group to make progress toward attaining the goal that brought them together). These skills include negotiation, resilience, communication, problem-solving, critical thinking, and interpersonal skills.
Projects have become increasingly more complicated as more businesses execute their strategies through projects. Project management is more than just working with numbers, templates, charts, graphs, and computing systems. Though they can be counted, a common denominator in all projects is people. But they are not just numbers. A large part of the project manager’s role involves dealing with people. Hence, project managers should study people’s behaviors and motivations. Project managers must be perceived to be credible by the project team and stakeholders. They should detect and clarify the ambiguities effectively to remove the obstacles. On projects, the environment changes frequently, and the project manager must apply the appropriate leadership approach for each situation. They must have good communication skills. Lack of communication skills and team-building skills as well as organizational skills would cause problems in a project and could lead to failure.
PMBOK Guide 6th Edition makes an analogy of a music conductor for the project managers. This analogy is a perfect example describing the responsibilities and skills of project managers. An orchestra conductor coordinates a variety of performers who play different instruments and should ensure that the audience enjoys the music on the day of the performance. The conductor cannot know how to play all the instruments in an orchestra, but only one of them or a few of them. However, the conductor must assure that all the performers playing the instruments including but not limited to violins, violas, cellos, double basses, flutes, oboes, clarinets, kettledrums, and harps must create a piece of music in harmony that the audience can enjoy. Conductors perform many rehearsals with all the performers to achieve this harmony. During these rehearsals and the performance, most of the work of the conductor would be regarding communication with all the performers.
The term “project manager” can come across a variety of concepts such as project leader, project lead, and project coordinator in other resources. So a project manager should possess interpersonal leadership skills.

Listening
One of the most important communication skills of the project manager is the ability to actively listen. Active listening is placing oneself in the speaker’s position as much as possible, understanding the communication from the point of view of the speaker, observing and paying attention to the body language and other environmental cues, and striving not just to hear, but to understand. Active listening takes focus and practice to become effective. It enables a project manager to go beyond the basic information that is being shared and to develop a more complete understanding of the information.

Negotiation
When multiple people are involved in an endeavor, differences in opinions and desired outcomes naturally occur. Negotiation is a process for developing a mutually acceptable outcome when the desired outcome for each party conflicts. A project manager will often negotiate on different aspects of a project (e.g., scope, schedule, budget, quality, purchases, conflicts with stakeholders) with the client, team members, vendors, and other project stakeholders. Negotiation is an important skill in developing support for the project and preventing frustration among all parties involved, which could delay or cause project failure. Negotiation is used to achieve support or agreement that supports the work of the project or its outcomes and to resolve conflicts within the team or with other stakeholders.
Negotiations involve four principles:
1. Separate people from the problem:
Framing the discussions in terms of desired outcomes enables the negotiations to focus on finding new outcomes.
2. Focus on common interests:
By avoiding the focus on differences, both parties are more open to finding acceptable solutions.
3. Generate options that advance shared interests:
Once the common interests are understood, solutions that do not match with either party’s interests can be discarded, and solutions that may serve both parties’ interests can be more deeply explored.
4. Develop results based on standard criteria:
The standard criterion is the success of the project. This implies that the parties develop a common definition of project success.
For the project managers to successfully negotiate issues on the project, they should first seek to understand the position of the other party. They should figure out the concerns and expectations of team members or stakeholders with whom they will negotiate, as well as the business drivers and personal drivers that are important to them. Without this understanding, it is difficult to find a solution that will satisfy them. Project managers should also seek to understand what outcomes are desirable to the project. Typically, more than one outcome is acceptable. Without knowing what outcomes are acceptable, it is difficult to find a solution that will produce that outcome.

Conflict Management
Conflict on a project can be expected because of a variety of reasons such as the level of stress, lack of information in particular during the early phases of the project, personal differences, role conflicts, and limited resources. Although good planning, effective communication, and healthy team building can reduce the amount of conflict, the conflict will still emerge. How the project manager deals with the conflict results in the conflict being destructive or an opportunity to build energy, creativity, and innovation.
One of the well-known conflict management models is the Thomas-Kilmann Conflict Mode Instrument (TKI) which assesses an individual’s behavior in conflict situations when the concerns of two people appear to be incompatible. This model is based on two dimensions that describe a person’s behavior in conflict.
1. Assertiveness: The extent to which the individual attempts to satisfy his or her own concerns.
2. Cooperativeness: The extent to which the individual attempts to satisfy the other person’s concerns.
According to different levels of these two dimensions, the model defined five methods of dealing with conflict (Figure 6.1).

Competing (forcing) is assertive and uncooperative. It is a power-oriented mode. An individual pursues his or her own concerns at the other person’s expense, using whatever power seems appropriate to win his or her position.
Collaborating is both assertive and cooperative. An individual attempts to work with the other person to find a solution that fully satisfies the concerns of both. It involves digging into an issue to identify the underlying concerns of the two individuals and to find an alternative that meets both sets of concerns.
Compromising is intermediate in both assertiveness and cooperativeness. The objective is to find an expedient, mutually acceptable solution that partially satisfies both parties. Compromising might mean splitting the difference, exchanging concessions, or seeking a quick middle-ground position.
Avoiding is unassertive and uncooperative. When avoiding, an individual does not immediately pursue his or her own concerns or those of the other person. He or she does not address the conflict. Avoiding might take the form of diplomatically sidestepping an issue, postponing an issue until a better time, or simply withdrawing from a threatening situation.
Accommodating is unassertive and cooperative, which is the opposite of competing. An individual neglects his or her own concerns to satisfy the concerns of the other person. Therefore, there is an element of self-sacrifice in this mode.
Each of these approaches can be effective and useful depending on the situation. Project managers will use each of these conflict resolution approaches depending on the project manager’s personal approach and an assessment of the situation. Most project managers have a default approach that has emerged over time and is comfortable. For example, some project managers find the use of the project manager’s power the easiest and quickest way to resolve problems. “Do it because I said so” is the mantra for project managers who use competing as the default approach to resolve conflict. The competing approach often succeeds in a situation where a quick resolution is needed, and the investment in the decision by the parties involved is low. Some project managers find accommodating with the client the most effective approach to dealing with client conflict.

After the problem has been restated and agreed on, alternative approaches are developed. This is a creative process that often means developing a new approach or changing the project plan. The result is a resolution to the conflict that is mutually agreeable to all team members. If all team members believe every effort was made to find a solution that achieved the project charter and met as many of the team member’s goals as possible, there will be a greater commitment to the agreed-on solution.

Trust
Building trust in a project begins with the project manager. On complex projects, the assignment of a project manager with a high trust reputation can help establish the trust level needed. The project manager can also establish the cost of lying in a way that communicates an expectation and a value for trust in the project. Project managers can also assure that the official goals (stated goals) and operational goals (goals that are reinforced) are aligned. The project manager can create an atmosphere where informal communication is expected and reinforced.
Informal communication is important to establishing personal trust among team members and with the client and other stakeholders. Allotting time (setting aside time) during project start-up meetings to allow team members to develop a personal relationship is important to establishing team trust. The informal discussion allows for a deeper understanding of the whole person and creates an atmosphere where trust can emerge.
Small events that reduce trust often take place on a project without anyone remembering what happened to create an environment of distrust. Taking fast and decisive action to establish a high cost of lying, communicating the expectation of honesty, and creating an atmosphere of trust are critical steps a project manager can take to ensure the success of complex projects.
Project managers can also establish expectations of team members to respect individual differences and skills, look and react to the positives, recognize each other’s accomplishments, and value people’s self-esteem to increase a sense of benevolent intent.

Emotional Intelligence (EQ)
Emotions are neither positive nor negative. Emotions are both a mental and physiological response to environmental and internal stimuli. Project managers need to understand and value their emotions to appropriately respond to the client, project team, stakeholders, and project environment. Daniel Goleman (Goleman, 1995) discussed emotional intelligence quotient (EQ) as a factor more important than IQ in predicting leadership success. Emotional intelligence is the ability to sense, understand, and effectively apply the power and acumens of emotions as a source of human energy, information, connection, and influence (Cooper and Sawaf, 1997).
Emotional intelligence includes the following:
- Self-awareness
- Self-regulation
- Empathy
- Relationship management
Emotions are important to generating energy around a concept, building commitment to goals, and developing high-performing teams. Emotional intelligence is an important part of the project manager’s ability to build trust among the team members and with the client. It is an important factor in establishing credibility and open dialogue with project stakeholders. Emotional intelligence is a critical ability for project managers, and the more complex the project profile, the more important the project manager’s EQ becomes to project success.

4. Leadership Styles and Servant Leadership
Leadership is a function of both the personal characteristics of the leader and the environment in which the leadership must occur. Several researchers have attempted to understand leadership from the perspective of the characteristics of the leader and the environment of the situation. These researchers described leaders as either autocratic or democratic (Tannenbaum & Schmidt, 1958), as pathfinders (visionaries), problem solvers (analytical), or implementers (team-oriented) (Leavitt, 1986), and as either transactional (focused on actions and decisions) or transformational (focused on the long-term needs of the group and organization)(Burns, 1978). Fred Fiedler introduced contingency theory and the ability of leaders to adapt their leadership approach to the environment (Fiedler, 1971). Most leaders have a dominant leadership style that is most comfortable. For example, most engineers spend years training in analytical problem solving and often develop an analytical approach to leadership. A leadership style reflects personal characteristics and life experiences. Although a project manager’s leadership style may be predominantly a pathfinder (using Leavitt’s taxonomy), most project managers become problem solvers or implementers when they perceive the need for these leadership approaches. The leadership approach incorporates the dominant leadership style and Fiedler’s contingency focus on adapting to the project environment.
PMBOK Guide 6th Edition provides a list of leadership styles as below:
1. Laissez-faire: Leaders allow the team to make their own decisions and establish their own goals. It is also referred to as taking a hands-off style.
2. Transactional: Leaders focus on goals, feedback, and accomplishment to determine rewards.
3. Servant: Leaders demonstrate a commitment to serve and put other people first. They focus on other people’s growth, learning, development, autonomy, and well-being. They concentrate on relationships, community, and collaboration.
4. Transformational: Leaders empower followers through idealized attributes and behaviors, inspirational motivation, encouragement for innovation and creativity, and individual consideration.
5. Charismatic: Leaders are able to inspire with high energy. They are enthusiastic and self-confident and hold strong convictions.
6. Interactional: This leadership style is a combination of transactional, transformational, and charismatic leadership styles.
Among them, the “Agile Practice Guide” accompanying PMBOK Guide Sixth Edition highlights the servant leadership style in particular for the agile project management approach. Although servant leadership isn’t unique to agile, project managers and organizations can observe and experience that this leadership style integrates into the agile mindset value. As the name refers, servant leaders serve those on the team by promoting self-awareness, listening, helping team members and stakeholders improve themselves, coaching rather than controlling, facilitating coordination, removing obstacles and organizational impediments in front of the team, the members, and the project, promoting safety, respect, and trust, and promoting the energy and intelligence of others.
No particular leadership approach is specifically appropriate for managing a project. Each project has a unique set of circumstances because, by definition, projects are unique endeavors. The leadership approach and the management skills required to be successful vary depending on the complexity profile of the project. The Project Management Institute published research that studied project management leadership skills and concluded that project managers needed good communication skills and the ability to build harmonious relationships and motivate others (Shi & Chen, 2006). Beyond this broad set of leadership skills, the successful leadership approach will depend on the profile of the project.
A transactional project manager with a strong command and control leadership approach may be very successful on a small software development project or a construction project, where tasks are clear, roles are well understood, and the project environment is cohesive. This same project manager is less likely to be successful on a larger, more complex project with a diverse project team and complicated work processes.
Each project phase may also require a different leadership approach. During the start-up phase of a project, when new team members are first assigned to the project, the project may require a command and control leadership approach. Later, as the project moves into the conceptual development phase, creativity becomes important, and the project management takes on a more transformational type leadership approach. Most experienced project managers can adjust their leadership approach to the needs of the project phase. Occasionally, on very large, complex projects, some companies will change project managers after the conceptual phase of the project to bring in a different project leadership approach or change project managers to manage the closeout of a project. Changing project managers may bring the right level of experience and the appropriate leadership approach but is also disruptive to a project. Senior management must balance the benefit of matching the right leadership approach with the cost of disrupting the project.

5. Creating a Project Culture
Project managers have a unique opportunity during the start-up of a project. They create a project culture, something organizational managers seldom have a chance to do. In most organizations, the corporate or organizational culture has developed over the life of the organization, and people associated with the organization understand what is valued, and what behaviors are expected. Edgar Schein defined culture as a pattern of basic assumptions formed by a group on how to perceive and address problems associated with both internal adaptation and external integration (Schein, 1990). While organizational culture constrains, stabilizes, and provides structure to the organization, it is being constantly enacted, created, and shaped by leadership behavior.
A project culture represents the shared norms, beliefs, values, and assumptions of the project team. Understanding the unique aspects of a project culture and developing an appropriate culture to match the project are important project management abilities.
Culture is developed through the communication of the priority, the given status, and the alignment of official and operational rules. Official rules are the rules that are stated, and operational rules are the rules that are enforced (followed). Project managers who align official and operational rules are more effective in developing a clear and strong project culture because the project rules are among the first aspects of the project culture to which team members are exposed when assigned to the project. In addition to official and operational rules, the project leadership can communicate what is important by the use of symbols, storytelling, rituals, rewards or punishments, and taboos.

Operational Rules on a Project in India
During the initiation of a project in India, members of the project team were given a policy that stated all travel expense claims must be submitted within three days of completion of travel. During the first few weeks, the administrative team began to understand that this was a difficult policy to enforce without creating moral problems on the project. Instead of changing the official rule, it was seldom enforced. The official rules and operational rules differed.
Later in the project, a worker was injured after crossing an area that was marked as unsafe. Workers indicated that they knew the official rules but it took too much time to go around the unsafe area. They assumed that official rules could be ignored if they were difficult to obey. The difference between official rules and operational rules of the project created a culture that made the communication of the priorities more difficult.

Creating a Culture of Safety
A project manager in South America who wanted to create a strong safety culture on a construction project with significant safety concerns used several methods to create the desired culture. The very first meeting that project team members attended was a safety orientation. Members were issued a card—a symbol—after the meeting granting permission to participate in the project. The project leadership team told stories of previous projects where people were fired for breaking safety rules and often warned that the fastest way to get fired on the project was to break a safety rule—an example of storytelling. Every project meeting started with a discussion of a safety topic—a ritual—and any discussion of lessening the safety rules was forbidden—taboo—and was quickly and strongly cut off by the project leadership if it occurred.
As can be seen in both examples above, culture guides behavior and communicates what is important and is useful for establishing priorities. On projects that have a strong safety culture, team members feel free to challenge anyone who breaks a safety rule, even managers. The safety aspects of culture are stronger than the cultural aspects of the power of management.

Culture of Stakeholders
When project stakeholders do not share a common culture, project management must adapt its organizations and work processes to cope with cultural differences. Three major aspects of cultural difference that can affect a project are communications, negotiations, and decision-making.
Communication is perhaps the most visible manifestation of culture. Project managers encounter cultural differences in communication in language, context, and candor (honesty). Language is clearly the highest barrier to communication. When project stakeholders do not share the same language, communication slows down and is often filtered to share only information that is deemed critical. The barrier to communication can influence project execution where quick and accurate exchange of ideas and information is critical. The interpretation of information reflects the extent that context and candor influence cultural expressions of ideas and understanding of information. In some cultures, an affirmative answer to a question does not always mean yes. The cultural influence can create confusion on a project where project stakeholders share more than one culture. It is of high importance to keep in mind that not all cultural differences are related to international projects. Corporate cultures and even regional differences can create cultural confusion on a project.

6. Developing and Managing a Project Team
A team is “a group of individuals who interact interdependently and who are brought together or come together voluntarily to achieve certain outcomes or accomplish particular tasks” (Berry, 2011, p.136). Teams are utilized in organizations to establish novel combinations of people who would work on unique problems and generate critical decisions as outcomes (Gersick, 1988). Much of the work that is performed today in organizations requires a focus on teamwork. The ability to work successfully as a team member, as well as the ability to lead teams, is an ultimate advantage within the workforce. Teams themselves must be managed, in addition to managing just the individuals, to be successful. We’ve all heard the quote originally coined by Aristotle that states that “the whole is greater than the sum of its parts.” This captures the nature of the team perfectly—there is such a synergy that comes from a team that the individuals alone are not able to create.
A team is a collaboration of people with different personalities that is led by a person with a favored leadership style. Managing the interactions of these personalities and styles as a group is an important aspect of project management. The project team is made up of people dedicated to the project. These people, team members, are generally borrowed from other departmental units in an organization or are recruited from outside the organization. They may work full-time, part-time, or in some of the activities when their skills are needed. The formal organizational structure would have a substantial impact on how project teams are created and managed. In a functional organization, project managers may have low authority and control over the resources and budget. Besides, they may not work full time as a project manager as they may still carry out the routine tasks of their functional unit. The main advantage of a functional organization type is that the project manager can acquire qualified and experienced human resources from other functional departments. In a strong matrix organization type, a Project Management Office (PMO) or a designated program management office is added besides functional departments. This department employs full-time project managers with a designated job role. They manage the project budget, and their authority becomes moderate to high. They can also have a full-time administrative staff. This organizational structure may be preferred by many project managers since they can still acquire qualified and experienced team members from functional departments inside the organization. Among functional, weak matrix, strong matrix, and project-oriented organization types, a strong matrix structure may suggest more opportunities for a project manager. However, it is of high importance for a project manager to keep in mind and consider various internal and external factors as well as organizational politics.
In particular, in the functional, weak matrix, and balanced matrix organization types, there may be some difficulties for project managers while dealing with project team members. Since these members are borrowed from other units, they may work at the project less than 100% of their working time, and project managers may not be their direct supervisors. Their priorities may be elsewhere. Thus, their dedication to the project objectives and activities couldn’t reach the level project managers expect from them to accomplish their tasks and responsibilities as desired. They may be juggling more than one project as well as their full-time job and have difficulty meeting deadlines.
Project managers need to provide leadership, direction, and above all, support to team members as they go about accomplishing their tasks. Working closely with the team to solve problems can help project managers learn from the team and build rapport. Managing project team members requires interpersonal skills. Here are some suggestions that can help with more effective team management:
- Involve team members in project planning.
- Arrange to meet privately and informally with each team member at several points in the project, perhaps for lunch or coffee.
- Be available to hear team members’ concerns at any time.
- Encourage team members to pitch in and help others when needed.
- Complete a project performance review for team members.

Team Development Stages
One of the models used to describe team development is the Tuckman ladder. According to Tuckman (1965), small groups go through four stages of development which are forming, storming, norming, and performing. As a result of a literature review of fifty-five articles, Tuckman (1965) proposed a model of developmental stages for group settings over time. In respect to the group structure, he labeled these stages as
(1) testing and dependence ­– orientation to task,
(2) intragroup conflict – emotional response to task demands,
(3) development of group cohesion – open exchange of relevant interpretations, and
(4) functional role relatedness – emergence of solutions.
An essential correspondence between the perspectives of group structure and task activity caused Tuckman to summarize the group stages as “forming,” “storming,” “norming,” and “performing.” These four stages covered both group interpersonal and task activities. Tuckman and Jensen (1977) added the fifth stage as adjourning after they reviewed twenty-two studies .
The first stage, forming, is characterized by orientation to the group setting, testing the boundaries of interpersonal and task behaviors of other members, and a dependency relationship with the leader. The storming stage following the forming stage is characterized by conflict and polarization around interpersonal issues, with concomitant emotional responses in the task sphere. These behaviors with hidden agendas and prejudices serve as resistance to group influence and task requirements. In the third stage, norming, resistance to authority is overcome, in-group feeling and cohesiveness develop, new standards evolve, and new roles are adopted. In the performing stage, group energy is channeled into the task after the structural issues are resolved and the structure becomes supportive of task performance. The last stage, adjourning, indicates the completion of the project where groups disband, and team members are reassigned to other projects or tasks.
Although these classic stages in group development may not be apparent for all groups, and not all groups may follow them, they would be useful for predicting team performance (Mannix and Jehn, 2004) as well as conflicts and harassment cases within an organized framework. Besides, not all the teams could experience all stages and they may spend different times in stages (Ayoko et al., 2012). Some teams may also face challenges in the transition process from one stage to another, such as moving toward the norming stage from the storming stage. Nevertheless, all teams can find themselves in the performing stage while some of them would spend substantially longer times which could lead them to a higher achievement rating in the end. Johnson et al. (2002) proposed an iterative group development model based on Tuckman’s model [7]. In their model based on student virtual learning teams, there was no evidence of the storming stage for all student teams due to rapid movement between each stage given the limited time in accomplishing assignments. Thus, teams moved along forming, norming, and performing stages and they resolved the conflict when it arose among team members. After the conflict was resolved, teams continued the process of forming, norming, and performing.

Virtual Teams
Advances in ICTs have enabled the creation and utilization of virtual teams (VTs) within organizations in the last three decades (Alsharo et al., 2017). The advent of the Internet accompanied by various ICTs, and the emergence of the COVID-19 pandemic by the end of 2019 accelerated the process of digitalization for people, organizations, and governments. Thus, the adoption and spread of ICTs worldwide across organizations and countries increased exponentially. The utilization of global virtual teams in organizations increased to unprecedented levels. 94% of the respondents of CultureWizard’s Global Virtual Work Survey indicated that they want to continue working from home—at least part time. These advances ensured the organizations to design their teams composed of members from different geographic locations and organizations virtually beyond a setting of the same location (Berry, 2011). Nevertheless, even though ICTs are prerequisites of VTs, other factors were also prominent in the process of shifting from traditional face-to-face teams to VTs. Some of these factors could be listed as increased use of horizontal organizational structure, the emergence of environments that require inter-organizational cooperation, continued shift from production to service and knowledge-intense work environments, and increasing globalization of trade and corporate activity (Townsend et al., 1998) .
Virtual interactions and virtual teams cannot be considered identical concepts. Virtual interactions also occur in collocated teams extensively, such as the widespread exchange of emails in the same office (Berry, 2011). A VT can be distinguished from a face-to-face team in terms of several factors. The most prominent factor would be the use of ICTs as the primary communication and collaboration media. Taking into consideration the utilization of ICTs, VT members are less likely to observe physical behaviors (e.g., gestures and intonation), which face-to-face team members rely upon to establish and sustain trust (Alsharo et al., 2017). Virtual teams have various benefits such as task, resource and schedule flexibility, access to and bringing specialized skills and diverse experiences together in a relatively short time, enhanced knowledge sharing and repository, easier documentation of performance outcomes, and opportunities for accelerated problem solving and solution finding (Jimenez et al., 2017). Virtual teams employ experts who have acquired more flexibility in temporal and spatial aspects since they save time by not traveling to meet their teammates. These time and cost-saving effects and flexible work schedule benefits are also commonly observed for the teleworkers who work outside of the office by means of virtual communication tools such as teleconferences, videoconferences, and intranets with remote log-in (Coenen and Kok, 2014). The ability to bridge time and space provides the team with the capability to respond and adjust to new tasks more rapidly, and human resources can be distributed more efficiently without physical relocation of employees thus leading to better utilization of human resources. Although flexibility is assumed to generate positive outcomes, it may cause inherent obstacles for virtual teams. The lack of shared work history among team members as well as less face-to-face interaction could bring about trust issues in virtual teams (Coenen and Kok, 2014).
While virtual teams can be confined to a region in a country or the entire country, they can extend beyond national and continental borders when members of VTs work and live in different countries (Pinjani and Palvia, 2013). One of the advantages of flexibility in Global Virtual Teams (GVTs) is easier access to skilled experts all around the world. This ensures the availability of resources in other parts of the world when scarcity exists in the organization’s or project’s geographical area. The dispersed structure of GVT members around the globe allows a 24-hour relay workflow (Carmel et al., 2010). For instance, members located in Asia and Australia can work on the project during their business hours. They can pass the work on to their colleagues in Europe and Africa for further processing, and then, they can pass it on to the colleagues in the Americas, who can work on it while their more eastern team members are asleep. This follow-the-sun approach creates a cycle of work through which GVT members pass the work on to the members in Asia and Australia, where 24-hour relay starts again (Carmel et al., 2010).
Despite the unprecedented benefits mostly owing to the developments in ICTs, the virtual nature of these teams is not immune to the challenges to effective collaboration and team outcomes (Alsharo et al., 2017). One of the essential challenges in virtual work is the elimination of face-to-face meetings that would otherwise help team members build interpersonal relationships (Cummings and Dennis, 2018). Lack of first impressions of other team members might have a substantial impact on the formation and functioning of the team, and the outcome of the teamwork. Cummings and Dennis (2018) contended that virtual team members examine each other’s profiles on enterprise social networking sites to get acquainted with them, otherwise not possible in a dispersed team. Some of the problems that GVTs and their members might encounter can be enumerated as lack of trust, language and time barriers, cultural differences, lack of onsite monitoring, lack of tone and body language, and different interpretations by the members due to the lack of cues. Eventually, if these likely challenges are not addressed by the GVT leaders and upper hierarchical levels in the organization, virtual teams may cause disadvantages to the team members’ well-being and job satisfaction, and team performance.
Team diversity or heterogeneity might have either a positive or negative impact on a team’s performance. Although team diversity could exacerbate the conflict and emotional reactions in GVTs (Ayoko et al., 2012) and cohesiveness in homogeneous teams (Drescher and Garbers, 2016), and team members can build higher trust, team diversity, on the contrary, could improve GVT effectiveness (Jimenez et al., 2017). The diverse backgrounds of team members could provide representation and exchange of different opinions and perspectives within the team. Hence, this process can create value by providing a more extensive range of information sources and thus aiding creativity and problem solving, and a higher level of organizational learning and synergy (Berry, 2011; Jimenez et al., 2017).
CultureWizard’s Global Virtual Work Survey pointed to complications in global virtual teams such as difficulty in building relationships (37%), managing conflict (33%), and lack of responsiveness from team members (20%). The survey also highlighted an issue with the technology as it cannot completely erase the barriers of miscommunication. The survey indicated that 75% of respondents use webcams to compensate for lack of face-to-face contact, but webcams come with their complications, such as ambient noise, feeling pressure to look attentive and professional on camera, and technical issues such as insufficient bandwidth or difficulty in operating new software.