## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 6
Financial Management, Budgeting and Administration of International Projects
Financial planning, budget structure, eligibility of costs, procurement and audit, financial reporting and the prevention of financial irregularities
Content Module 2 · Implementation, Administration and Evaluation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
02
01
Principles of financial planning for an international project
02
Budget structure: personnel, travel, equipment, subcontracting, other direct costs, indirect costs
03
Eligibility of costs, co-financing, lump sums, unit costs, actual costs, and donors' financial rules
04
Procurement, document management, financial control and audit in international projects
05
Financial reporting, supporting documents, transparency and accountability in the use of funds
06
Preventing financial risks, double funding and breaches of grant agreements
Notes: The lecture follows the financial life of a grant: from planning the budget (Sections 1–2) and the rules that decide which costs the donor will pay (Section 3), through the administration of funds during implementation (Section 4) and reporting on their use (Section 5), to the prevention of financial irregularities (Section 6). It builds on the budget and cost-effectiveness criteria of Topic 3 and on the transparency principles of Lecture 4.

## Slide 3
01
SECTION 1
Principles of Financial Planning for an International Project
Why must every budget line be traceable to the work plan?
How do realism, economy and donor rules shape the budget?
Why must a consortium plan its cash flow and divide the budget among partners?
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
03
Notes: Financial planning rests on a set of principles whose observance is a mandatory condition both for passing the competitive selection and for trouble-free implementation. This section presents five of them. Ask students which of the five is most often violated in applications they have seen.

## Slide 4
1 · FINANCIAL PLANNING
Five Principles of Financial Planning
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
04
Alignment with the work plan
Every budget line is justified by its link to specific activities and work packages.
Realism and economy
Costs match market prices and actual needs; overstatement and unwarranted understatement both weaken the assessment.
Compliance with the donor's financial rules
Donor eligibility rules are mandatory and take precedence over internal procedures.
Advance cash-flow planning
Funding is paid in tranches, so the consortium needs working capital to cover gaps.
Allocation of the budget among partners
Partner budgets add up to the consortium budget, which the coordinator consolidates.
Why the principles matter
Competitive selection
Reviewers check that the budget follows the work plan and assess it against the criterion of cost-effectiveness (Topic 3).
Trouble-free implementation
Adherence to the principles is a mandatory condition for implementing the project without financial problems.
Notes: Alignment: each budget line must be justified by its link to specific activities and work packages (Topic 3); a budget that does not follow the logic of the work plan is a typical basis for reviewers' comments. Realism and economy: both overstatement and unwarranted understatement lower the assessment against the cost-effectiveness criterion (Topic 3, Section 5). Donor rules on eligibility are mandatory and take precedence over the applicant's internal procedures. Funding arrives in tranches, so the consortium must plan its own working capital. The consortium budget is the sum of partner budgets; the coordinator consolidates it.

## Slide 5
1 · ADVANCE CASH-FLOW PLANNING
Funding Arrives in Tranches: Planning for Cash-Flow Gaps
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
05
Cumulative amount
Stylised illustration
Pre-financing
Interim payment
Final payment
Cash-flow gap
Cash-flow gap
Start
End of implementation
Approval of reporting
Expenditure
Donor payments
Gap: own working capital
Pre-financing
An advance paid at the start of the project.
Interim payments
Paid in the course of implementation.
Final payment
Paid only after the donor approves the reporting.
The consortium plans its own working capital in order to cover temporary cash-flow gaps.
Notes: Donor funding is, as a rule, disbursed in tranches: pre-financing, interim payments, and a final payment following approval of the reporting. Expenditure, by contrast, runs continuously. Whenever cumulative spending runs ahead of cumulative payments — before an interim payment and, above all, between the end of implementation and the final payment — the consortium must bridge the gap from its own working capital. The diagram is stylised; the shares of each tranche differ between programmes.

## Slide 6
1 · ALIGNMENT AND ALLOCATION
One Budget, Two Views: Work Packages and Partners
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
06
Work package | P1 Coordinator | P2 Partner | P3 Partner | P4 Partner | WP total
WP1 Project management | 40 | 10 | 10 | 10 | 70
WP2 Development | 30 | 60 | 45 | 20 | 155
WP3 Piloting | 20 | 35 | 50 | 30 | 135
WP4 Dissemination | 15 | 10 | 10 | 25 | 60
Partner total | 105 | 115 | 115 | 85 | 420
Illustrative example
Figures in EUR thousand; work packages and partners are hypothetical. Gold cell: consolidated consortium budget.
Rows: the work plan
Each budget line traces back to activities in a work package.
Columns: the partners
Each partner is responsible for its own costs and reporting.
Total: the consortium
The coordinator consolidates the budget for the project as a whole.
Notes: The matrix combines two principles. Read across a row: each work package has a budget built from the costs of the activities in it, which is how the budget is aligned with the work plan. Read down a column: each partner has its own budget, is responsible for its own costs and reports on them. The coordinator consolidates the partner budgets into the budget of the project as a whole. The figures are hypothetical and serve only to show the logic.

## Slide 7
02
SECTION 2
Budget Structure: Personnel, Travel, Equipment, Subcontracting, Other Direct Costs, Indirect Costs
Which unified cost categories make up a project budget?
How are personnel costs calculated and evidenced?
How are indirect costs determined by a flat rate?
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
07
Notes: Irrespective of the donor, the budget of an international project is structured according to unified cost categories: five categories of direct costs and one of indirect costs. This section defines each category, shows how the largest line — personnel — is calculated, and shows how a flat rate produces the indirect costs.

## Slide 8
2 · BUDGET STRUCTURE
Six Unified Cost Categories
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
08
Five categories of direct costs and one category of indirect costs (highlighted):
Personnel costs
Usually the largest line: salaries in proportion to time actually worked, at a documented rate, supported by timesheets.
Travel costs
Transport, accommodation and subsistence for project travel, within donor limits (class of air travel, daily accommodation cap).
Equipment costs
Purchase or lease; for long-term equipment, as a rule only the depreciation over its period of use in the project.
Subcontracting costs
Third parties performing clearly defined tasks on a contractual basis; usually capped as a share of the budget; competitive procurement.
Other direct costs
Consumables, publications, translation, audit, and the visualisation and dissemination of results.
Indirect costs (overheads)
Administrative costs not attributable to one project (rent, utilities, accounting); usually a flat rate of eligible direct costs.
Notes: Personnel is as a rule the largest line: salaries in proportion to time actually worked, at a documented rate (the actual salary or a unified donor rate), always supported by timesheets. Travel covers transport, accommodation and subsistence within the donor's limits. For equipment intended for long-term use that will continue to be used after the project ends, only the depreciation corresponding to the period of use in the project is, as a rule, included. Subcontracting is usually capped as a share of the total budget and requires competitive procurement. Indirect costs cannot be attributed to a specific project and are determined by a flat rate, e.g. 7% or 25% depending on the programme.

## Slide 9
2 · PERSONNEL COSTS
Personnel Costs: Time Actually Worked × Documented Rate
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
09
Time actually worked
in person-months or person-days, recorded in timesheets
×
Documented rate
the actual salary or a unified rate established by the donor
=
Personnel cost
declared in the personnel category of the budget
Illustrative example
6 person-months
×
EUR 3,000 per month
=
EUR 18,000
Personnel costs must be supported by timesheets; without them the time actually worked cannot be demonstrated.
Notes: Personnel costs are calculated in proportion to the time actually worked on the project, in person-months or person-days, multiplied by a documented rate: either the actual salary or a unified rate established by the donor. They must necessarily be supported by timesheets. This is the answer to self-check question 4: timesheets recording the time worked, together with documents establishing the rate (e.g. the employment contract and payment orders for the salary). The numbers in the example are hypothetical.

## Slide 10
2 · THE BUDGET IN FIGURES
An Illustrative Project Budget by Cost Category
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
10
Chart: 
| Personnel | Travel | Equipment | Subcontracting | Other direct costs | Indirect costs (7%)
Budget | 180000 | 45000 | 30000 | 20000 | 25000 | 21000
EUR 321,000
total budget
Cost category
EUR
Share
Personnel
180,000
56%
Travel
45,000
14%
Equipment
30,000
9%
Subcontracting
20,000
6%
Other direct costs
25,000
8%
Indirect costs (7%)
21,000
7%
Total
321,000
100%
Flat rate: direct costs EUR 300,000 × 7% = EUR 21,000 indirect costs
Illustrative example
Hypothetical figures; 7% is one of the example flat rates cited in the lecture (7% or 25%, depending on the programme).
Notes: A hypothetical consortium budget: direct costs total EUR 300,000. Indirect costs are not calculated from actual overhead expenditure; a flat rate of 7% is applied to the sum of eligible direct costs, giving EUR 21,000 and a total of EUR 321,000. Under a programme with a 25% flat rate the same direct costs would generate EUR 75,000 of indirect costs. Note that personnel is the largest line, as is typical. Link to self-check question 1: why are indirect costs, as a rule, set by a flat rate rather than on the basis of actual amounts?

## Slide 11
03
SECTION 3
Eligibility of Costs, Co-financing, Lump Sums, Unit Costs, Actual Costs, and Donors' Financial Rules
When is a cost eligible for funding?
How do actual costs, unit costs, lump sums and flat rates differ?
How is co-financing calculated and contributed?
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
11
Notes: This section sets out the rules that decide whether the donor will pay for a cost at all: the eligibility criteria, the forms in which costs are financed, the co-financing obligation, and the donor's own regulatory documents, which the consortium must study before planning.

## Slide 12
3.1 · ELIGIBILITY OF COSTS
Five Criteria a Cost Must Meet Simultaneously
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
12
Incurred during the implementation period
Exception: the costs of preparing the final report.
Linked to the project and budgeted
Directly linked to the subject matter and provided for in the approved budget.
Actually incurred by the beneficiary
Not by a third party outside the established procedures.
Documented and identifiable
Recorded in accordance with the beneficiary's accounting system.
Economical, efficient and effective
Complies with the principles of economy, efficiency and effectiveness.
Eligible cost
only when all five criteria are met at the same time
If any one criterion fails, the cost is ineligible.
Notes: A cost is eligible only if it satisfies all of the criteria at the same time: incurred during the implementation period (except the costs of preparing the final report); directly linked to the subject matter of the project and provided for in the approved budget; actually incurred by the beneficiary, not by a third party outside the established procedures; documented and identifiable in the beneficiary's accounting system; and compliant with the principles of economy, efficiency and effectiveness. Use a quick exercise: give students borderline cases and ask which criterion each fails.

## Slide 13
3.2 · FORMS OF COST FINANCING
Actual Costs, Unit Costs and Lump Sums Compared
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
13
Actual costs
PAID ON THE BASIS OF
Costs actually incurred
EVIDENCE REQUIRED
Primary accounting records for every amount spent
ADMINISTRATIVE LOGIC
Each cost is documented and checked
Unit costs
PAID ON THE BASIS OF
A predetermined rate per unit, e.g. per person-day or a daily subsistence allowance
EVIDENCE REQUIRED
Confirmation that the unit was used (e.g. a day of travel), not the amount spent
ADMINISTRATIVE LOGIC
Only the number of units is verified
Lump sums
PAID ON THE BASIS OF
A pre-agreed fixed amount for a defined result or milestone
EVIDENCE REQUIRED
Achievement of the result, irrespective of the costs actually incurred
ADMINISTRATIVE LOGIC
Simplified administration; increasingly used in EU Lump Sum Grants
Flat-rate financing is applied predominantly to indirect costs. The choice of form of financing is determined by the type of call.
Notes: The choice of the form of financing is determined by the type of call. Actual costs are reimbursed on the basis of primary accounting records. Unit costs apply a predetermined rate per unit (e.g. per person-day of staff time, or a daily subsistence allowance): only the use of the unit must be confirmed, not the amount spent. Lump sums pay a pre-agreed fixed amount when a defined result or milestone is achieved, irrespective of the costs actually incurred; they are increasingly used in the new generation of EU Lump Sum Grants to simplify administration. Self-check question 3 asks about exactly this advantage. Flat-rate financing is applied mainly to indirect costs.

## Slide 14
3.3 · CO-FINANCING
Co-financing: A Worked Example at an 80% Rate
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
14
Illustrative example
Total eligible project costs: EUR 500,000
Donor grant · 80% · EUR 400,000
Co-financing · 20%
EUR 100,000
1
Donor grant = eligible costs × co-financing rate
EUR 500,000 × 80% = EUR 400,000
2
Consortium's share = eligible costs − donor grant
EUR 500,000 − EUR 400,000 = EUR 100,000
3
Who covers the remaining 20%?
The applicant and partners, from own or other sources
Cash contribution
Money contributed by the applicant and partners from their own or other sources.
In-kind contribution
Resources provided free of charge, e.g. volunteers' working time or the use of own premises; documented and valued by an established methodology.
Notes: The co-financing rate determines the proportion of project costs covered by the donor's grant — here 80%. The remaining 20% must be covered by the applicant and partners from their own or other sources. With total eligible costs of EUR 500,000, the grant is EUR 400,000 and the consortium must contribute EUR 100,000. Co-financing may be a cash contribution or an in-kind contribution: resources provided free of charge, such as volunteers' working time or the use of the organisation's own premises, which must be documented and valued by an established methodology (self-check question 2). The figures are hypothetical.

## Slide 15
3.4 · DONORS' FINANCIAL RULES
Whose Rules Apply? Donor Rules Take Precedence
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
15
PRECEDENCE
Donor's financial rules
Model Grant Agreement and annotated rules: limits, procedures, exceptions
Consortium financial handbook
Adapts the donor's general rules to the practice of the specific project
Partners' internal financial procedures
Remain in force, but the donor's rules prevail where they differ
Study the rules first
The consortium is obliged to study the donor's rules before beginning financial planning.
Rules differ between programmes
They may differ significantly even between programmes of the same donor.
Rules are mandatory
Eligibility rules bind every partner and take precedence over internal procedures.
Notes: Each funding programme is accompanied by a detailed regulatory document — for EU programmes, the Model Grant Agreement and the corresponding annotated rules — setting out specific limits, procedures and exceptions. These rules are mandatory and take precedence over the partners' internal financial procedures. The consortium must study them before beginning financial planning, since they may differ significantly even between programmes of the same donor. In practice a consortium financial handbook (Section 6) translates the donor's general rules into the practice of the specific project.

## Slide 16
04
SECTION 4
Procurement, Document Management, Financial Control and Audit in International Projects
Which principles govern procurement within a project?
Which documents must be retained, and for how long?
How do internal control, external control and audit differ?
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
16
Notes: During implementation, the use of funds is administered through a chain of procedures: procurement, systematic document management, internal and external financial control, and independent audit. Each link produces the evidence that the next one relies on.

## Slide 17
4.1 · PROCUREMENT
Procurement: Four Principles and the Threshold Rule
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
17
Best value for money
Transparency
Equal treatment of suppliers
Non-discrimination
THE THRESHOLD RULE
Planned purchase of goods, works or services
Above the donor's threshold value?
Yes
Competitive procedure
price quotations from several suppliers, or a tender
Documented selection
mandatory record of how the winner was chosen
No
Purchase in line with the four principles above
Threshold values and the required procedures are set by each donor's rules.
Notes: The procurement of goods, works or services within an international project follows the principles of best value for money, transparency, equal treatment of suppliers and non-discrimination. For procurements exceeding the threshold values established by the donor, competitive procedures are required — price quotations from several suppliers, or a tender — and the process by which the winner was selected must be documented. Threshold values differ between donors and programmes, so always check the applicable rules.

## Slide 18
4 · THE CHAIN OF FINANCIAL ADMINISTRATION
From Procurement to Audit: One Chain of Evidence
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
18
Procurement
Best value, transparency, equal treatment; competitive procedures above thresholds
Document management
Contracts, invoices, payment orders, timesheets, certificates of completed work, procurement records
Financial control
Internal budget-versus-actual reconciliation; external checks by the donor
Audit
Independent Certificate on Financial Statements (CFS) appended to the final financial report
DOCUMENT RETENTION
Project end
Implementation
documents collected and filed systematically
Retention period: typically three to five years
documents accessible to the donor or auditors on request
Notes: Proper document management means systematic retention of all financial documentation: contracts, invoices, payment orders, timesheets, certificates of completed work and records of procurement procedures. Donors, as a rule, set a mandatory retention period after the project ends — typically three to five years — during which the documents must be accessible on request to the donor or to auditors. Each link of the chain depends on the one before: control and audit are only possible if procurement and every payment have been properly documented.

## Slide 19
4.3–4.4 · FINANCIAL CONTROL AND AUDIT
Internal Control, External Control and Independent Audit
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
19
Internal financial control
Coordinator controls the consolidated project budget
Each partner controls its own costs
A REGULAR CYCLE
1
Reconcile actual expenditure against the budget
2
Identify deviations
3
Notify the Steering Committee in good time
External financial control
by the donor, directly or through authorised bodies
Desk review of submitted reports
On-the-spot check
Full financial audit
increasing depth of verification
Certificate on Financial Statements (CFS)
Mandatory for most grants above a threshold: an independent certified auditor confirms the reliability of the financial reporting.
Notes: Internal control is exercised by the coordinator over the consolidated project budget and by each partner over its own costs. It consists of regular budget-versus-actual reconciliation, identification of deviations and timely notification of the Steering Committee. External control is exercised by the donor, directly or through authorised bodies, as a desk review of submitted reports, an on-the-spot check, or a full financial audit. The Certificate on Financial Statements (CFS) — mandatory for most grants above a threshold — is an independent certified auditor's confirmation of the reliability of financial reporting, appended to the final financial report.

## Slide 20
05
SECTION 5
Financial Reporting, Supporting Documents, Transparency and Accountability in the Use of Funds
Which financial reports does a consortium submit?
Which primary documents support each declared cost?
What is an audit trail, and why must it be complete?
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
20
Notes: Reporting is where the consortium accounts to the donor for every euro spent. The section covers the types of financial report, the primary documents behind each declared cost, and the audit trail that gives concrete expression to the principles of transparency and accountability examined in Lecture 4, Section 5.

## Slide 21
5.1 · TYPES OF FINANCIAL REPORTING
Interim and Final Financial Reports
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
21
Start
Interim reporting
Technical progress report
+ interim financial report
Interim reporting
Technical progress report
+ interim financial report
End of implementation
Final reporting
Final financial report
whole period; CFS appended
Every financial report
shows the costs actually incurred, broken down by budget category, for each partner
P1
P2
P3
P4
Personnel
Travel
Equipment
Subcontracting
Other direct
Indirect
Interim reports
Accompany the technical progress reports during implementation.
Final report
Summarises the whole period; the final payment follows its approval.
Notes: Financial reporting is, as a rule, submitted as interim financial reports, which accompany the technical progress reports, and a final financial report, which summarises the use of funds over the entire implementation period; where required, the auditor's CFS opinion is appended to it. Each report breaks down the costs actually incurred by budget category, for each partner in the consortium. The number of interim reporting periods depends on the grant agreement; two are shown for illustration. Recall from Section 1 that the final payment follows approval of the reporting.

## Slide 22
5.2 · SUPPORTING DOCUMENTS
Every Declared Cost Needs a Primary Document
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
22
Cost category | Typical primary supporting documents
Personnel | Timesheets; documentation of the rate (actual salary or the donor's unified rate); payment orders
Travel | Boarding passes; invoices for transport and accommodation; payment orders
Equipment | Procurement records; invoice; certificate of acceptance of goods; payment order
Subcontracting | Contract; procurement records; certificate of completed work; invoice; payment order
Other direct costs | Invoices; certificates of acceptance of goods or services; payment orders
Indirect costs | Follow from the eligible direct costs to which the flat rate is applied
Financial correction
Without a proper supporting document, the donor may disallow the cost, even where it was actually and reasonably incurred.
No document, no eligible cost.
Notes: Every cost declared in a report must be supported by an appropriate primary document: an invoice, a payment order, a timesheet, a boarding pass for travel, or a certificate of acceptance of goods or services. The table maps these documents onto the budget categories. The absence of a proper supporting document is grounds for the donor to disallow the cost — a financial correction — even where the cost was actually and reasonably incurred. This is why document management (Section 4.2) is a core financial function, not an administrative afterthought.

## Slide 23
5.3 · TRANSPARENCY AND ACCOUNTABILITY
The Audit Trail: Tracing Every Cost to Its Source
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
23
REPORTING →
Primary document
Invoice, payment order, timesheet, boarding pass
Accounting record
Identifiable in the beneficiary's accounting system
Partner report
Costs by category, for each partner
Consolidation
The coordinator consolidates partner reports
Final financial report
Whole implementation period, with the CFS
← VERIFICATION: THE DONOR OR AUDITOR TRACES A DECLARED COST BACK TO ITS SOURCE
Obligation: a complete audit trail and readiness for independent verification at any time within the document-retention period.
Notes: The transparency and accountability principles of Lecture 4, Section 5 are given concrete expression through the obligation to ensure a complete audit trail: the ability to trace every declared cost from the primary document to the final financial report. Reporting moves from left to right; verification by the donor or an auditor moves from right to left, sampling a figure in the report and tracing it back to its source. The consortium must be ready for such independent verification at any time within the document-retention period.

## Slide 24
06
SECTION 6
Preventing Financial Risks, Double Funding and Breaches of Grant Agreements
Which financial risks are typical of international projects?
What is double funding, and why is it a serious irregularity?
Which mechanisms prevent breaches of the grant agreement?
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
24
Notes: The final section turns from procedures to prevention: the typical financial risks of an international project, the particular danger of double funding, and the systematic mechanisms by which a consortium prevents financial irregularities before an external check discovers them.

## Slide 25
6.1 · TYPICAL FINANCIAL RISKS
Four Typical Financial Risks and the Responses
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
25
Currency risk
Exchange-rate fluctuations when national-currency costs are converted into the donor's reporting currency.
Response: Regular budget-versus-actual monitoring to detect deviations early.
Delayed donor payments
Late tranches create cash-flow gaps for the partners.
Response: Advance cash-flow planning and own working capital.
Disallowed costs
Costs rejected owing to insufficient documentary support.
Response: Systematic document management and a complete audit trail.
Exceeding category limits
Spending above the limit of a budget category without an approved reallocation.
Response: Timely request for the donor's approval of a reallocation.
Notes: Currency risk arises from exchange-rate fluctuations when costs incurred in a national currency are converted into the donor's reporting currency. Delayed donor payments create cash-flow gaps. Costs may be disallowed owing to insufficient documentary support. Limits within particular budget categories may be exceeded without timely approval of a reallocation. The responses shown draw on the tools discussed earlier in this lecture: cash-flow planning (Section 1), budget-versus-actual control (Section 4) and document management (Sections 4–5).

## Slide 26
6.2 · DOUBLE FUNDING
Double Funding: One Cost, Two Grant Agreements
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
26
Illustrative example
100% of the time actually worked
Correct allocation
Double funding
Project A 60%
B 40%
Project A 100%
Project B 100%
Each hour charged once
The same hours are charged under both grant agreements: 200% of the time actually worked.
Prevention: a clear system for recording the working time of staff engaged in several projects, plus the coordinator's internal control.
A serious irregularity
POSSIBLE CONSEQUENCES
Repayment of funds under both projects
Termination of the Grant Agreement
Entry into the European Commission's Early Detection and Exclusion System (EDES)
Notes: Double funding occurs when one and the same cost — for example, the working time of one member of staff for one and the same period — is claimed simultaneously under two or more grant agreements. In the example, a staff member working on two projects should have the hours divided between them according to the timesheet; charging the same hours to both means claiming twice the time actually worked. Donors treat this as a serious irregularity even where each cost was actually incurred once (self-check question 5): repayment under both projects, termination of the grant agreement and registration in the European Commission's EDES (Topic 4, Section 6). Prevention: a clear time-recording system for staff on several projects and the coordinator's internal control.

## Slide 27
6.3 · PREVENTING BREACHES OF GRANT AGREEMENTS
Five Mechanisms for Preventing Financial Irregularities
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
27
1
Internal financial handbook adapts the donor's general rules to the practice of the specific project
2
Regular training of the partners' financial staff
3
The “four eyes” principle two-stage approval of significant financial transactions
4
Periodic internal audits conducted in advance of external checks
5
Timely consultation with the donor's project officer on ambiguous questions of cost eligibility
The “four eyes” principle
Significant financial transaction
Stage 1: first approval
Stage 2: approval by a second person
Transaction executed
Minimises the risk of erroneous approval.
Notes: Systematic prevention involves: an internal financial handbook for the consortium that adapts the donor's general rules to the practice of the specific project; regular training of partners' financial staff; the four-eyes principle, i.e. two-stage approval of significant financial transactions; periodic internal audits in advance of external checks; and timely consultation with the donor's project officer on ambiguous questions of cost eligibility. The four-eyes principle is the answer to self-check question 6: no significant transaction is approved by one person alone.

## Slide 28
6 · SYNTHESIS
Red Flags of Breaches and How to Prevent Them
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
28
Red flag | Rule at risk | Prevention measure
The same staff hours charged to two projects | Prohibition of double funding | Time recording for staff on several projects; coordinator's control
A declared cost without a primary document | Documentation requirement; audit trail | Systematic document management and retention
A purchase above the threshold without quotations or a tender | Competitive procurement procedures | Handbook procurement rules; four-eyes approval
A budget category exceeds its limit | Category limits; approval of reallocations | Budget-versus-actual analysis; timely request for approval
Costs incurred outside the implementation period | Eligibility criteria | Eligibility checks before approval; periodic internal audits
Doubt about whether a cost is eligible | Donor's financial rules | Timely consultation with the donor's project officer
Notes: This synthesis links the warning signs a coordinator should watch for to the rules of this lecture and to the preventive mechanisms. Each red flag corresponds to a rule: the prohibition of double funding, the documentation requirement, competitive procurement above thresholds, budget-category limits, the eligibility period and the donor's specific rules. Use it as a checklist for an internal audit exercise: give students an extract from a partner's cost statement and ask them to spot the red flags.

## Slide 29
SUMMARY
Key Takeaways
Financial planning rests on five principles: alignment with the work plan, realism and economy, donor rules, cash-flow planning and allocation among partners.
Budgets use unified categories: personnel, travel, equipment, subcontracting and other direct costs, plus indirect costs set by a flat rate.
A cost is eligible only if it meets all eligibility criteria simultaneously; the donor's rules take precedence over internal procedures.
Actual costs, unit costs, lump sums and flat rates differ in what must be proven; co-financing may be made in cash or in kind.
Procurement, document management, internal and external control and the CFS audit form one chain of evidence behind every report.
A complete audit trail, reliable time recording and the four-eyes principle prevent disallowed costs, double funding and breaches.
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
29
Notes: Summarise the logic of the lecture: plan the budget on sound principles, respect the donor's eligibility rules, administer and document every transaction, report transparently, and prevent irregularities through internal control rather than waiting for external checks.

## Slide 30
SELF-CHECK
Questions for Self-Assessment
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
30
1
Why are indirect costs, as a rule, determined by a flat rate rather than on the basis of actual amounts?
2
Explain the difference between cash and in-kind co-financing, and give an example of an in-kind contribution.
3
What is the advantage of lump sums over actual costs from the point of view of the administrative burden on the consortium?
4
What documents must support personnel costs in an international project?
5
Why is double funding considered a serious breach of the grant agreement, even where both costs were actually incurred?
6
What internal-control mechanism minimises the risk of the erroneous approval of financial transactions?
Notes: Relevant slides: indirect costs and flat rates (slides 8 and 10); cash and in-kind co-financing (slide 14); forms of financing (slide 13); personnel costs and timesheets (slides 9 and 22); double funding (slide 26); the four-eyes principle (slide 27).

## Slide 31
SOURCES
Recommended Reading
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
31
Model Grant Agreement (Multi-beneficiary General MGA) and Annotated Grant Agreement. European Commission, Funding & Tenders Portal.
Financial Guidelines for EU external actions. European Commission, DG INTPA/NEAR.
EU Grants: How to manage your grant — Financial Management. Funding & Tenders Portal Online Manual.
Regulation (EU, Euratom) 2018/1046 (EU Financial Regulation).
Practice Standard for Project Cost Estimating. 2nd edition. Project Management Institute.
Note: Regulation (EU, Euratom) 2018/1046 has been recast as Regulation (EU, Euratom) 2024/2509 of 23 September 2024, in force since 29 September 2024. Source: European Commission, “EU Financial Regulation”, commission.europa.eu.
Notes: Point students to the Model Grant Agreement and the Annotated Grant Agreement as the primary sources for EU grant financial rules. Note for currency: Regulation (EU, Euratom) 2018/1046 has since been recast as Regulation (EU, Euratom) 2024/2509 of 23 September 2024, which entered into force on 29 September 2024 (European Commission, EU Financial Regulation page).

## Slide 32
Thank you for your attention
Questions and discussion
NEXT
Lecture 7. Risk, Communication and Quality Management in an International Project
LECTURE 6 · INTERNATIONAL PROJECT ACTIVITY
32