## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 7
Risk, Communication and Quality Management in an International Project
Risk analysis and response, communication and visibility, stakeholder and intercultural management, quality assurance and conflict resolution in project consortia
Content Module 2 · Implementation, Administration and Evaluation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
02
01
Identification, analysis, assessment and response planning for the risks of an international project
02
The risk register, the assumptions log, the contingency plan and the management of uncertainty
03
Communication strategy: internal and external communication, visibility, dissemination and exploitation of results
04
Stakeholder management and intercultural interaction within an international consortium
05
Quality management of results and deliverables, peer review and monitoring of compliance with donor requirements
06
Conflicts within the project team and mechanisms for their resolution
Notes: This lecture covers three management functions that run in parallel throughout implementation: risk management (Sections 1–2), communication and stakeholder management (Sections 3–4), and quality management (Section 5). Section 6 turns to conflicts within the team and the mechanisms for resolving them. The lecture builds on the logical framework (Lecture 2), the Consortium Agreement (Lecture 4) and consortium governance (Lecture 5).

## Slide 3
01
SECTION 1
Identification, Analysis, Assessment and Response Planning for Project Risks
What is a project risk, and can it be positive?
How are risks identified, classified and prioritised?
Which response strategies apply to threats and to opportunities?
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
03
Notes: Section 1 defines project risk and walks through the four sequential stages of the risk management cycle: identification, analysis, assessment and response planning. Emphasise from the outset that risk is not only a threat: an uncertain event can also have a positive effect on the project's objectives.

## Slide 4
1 · RISK MANAGEMENT
Project Risk and the Risk Management Cycle
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
04
Project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on at least one of the project's objectives: scope, schedule, cost, quality.
Risk management cycle
1 Identification
Brainstorming, checklists, logframe assumptions, SWOT analysis, consultations with experts and partners
2 Analysis
Probability of occurrence and degree of impact on the objectives; qualitative or quantitative
3 Assessment
Prioritisation of risks by level of criticality in the probability–impact matrix
4 Response planning
Strategies and specific measures for threats and opportunities
Notes: A project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on at least one of the project's objectives: scope, schedule, cost or quality. Risk management is a cyclical process comprising four sequential stages: identification, analysis (probability and impact), assessment (prioritisation by criticality) and response planning. The cycle is repeated throughout implementation, because the risk register must be reviewed and updated regularly, not only at the planning stage.

## Slide 5
1.1–1.2 · IDENTIFICATION AND CLASSIFICATION
Identifying Risks: Techniques and Categories
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
05
IDENTIFICATION TECHNIQUES
Brainstorming
Open generation of possible risks by the team
Checklist analysis
Typical risks of international projects
Logframe assumptions
Every uncertain assumption is a potential risk
SWOT analysis
Strengths, weaknesses, opportunities, threats
Consultations
With experts and consortium partners
SIX CATEGORIES BY SOURCE OF ORIGIN
Political and security
Changes in legislation, political instability, military action
Financial and economic
Currency fluctuations, inflation, delayed donor payments
Organisational and managerial
Staff turnover, insufficient consortium coordination
Operational
Delayed delivery of equipment, inaccessibility of target groups
Reputational
Negative media coverage, conflict of interest
Compliance
Non-compliance with the donor's financial rules, breach of reporting deadlines
Notes: Risks are identified systematically through brainstorming, analysis of checklists of typical risks in international projects, analysis of the logframe assumptions (Lecture 2), SWOT analysis and consultations with experts and consortium partners. Every assumption whose likelihood of occurrence is uncertain is a potential source of risk. It is appropriate to classify the risks of international projects by source of origin into the six categories shown; ask students to add one example from a project implemented in Ukraine to each category.

## Slide 6
1.3 · QUALITATIVE AND QUANTITATIVE ANALYSIS
Qualitative Analysis: The Probability–Impact Matrix
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
06
High
Medium
Low
Low
Medium
High
PROBABILITY OF OCCURRENCE
IMPACT ON OBJECTIVES
R1
R2
R3
R4
R5
Low
Medium
High priority
Illustrative example
Qualitative
Probability and impact are rated on a scale (e.g. low / medium / high); risks are prioritised by criticality in the matrix.
Quantitative
Numerical estimate of expected monetary impact; probabilistic modelling (e.g. Monte Carlo). Chiefly for large infrastructure and investment projects.
EXAMPLE RISKS ON THE MATRIX
R1
Exchange-rate fluctuations · financial
R2
Security situation prevents an in-person event · political
R3
Turnover of key staff at a partner · organisational
R4
Damage to equipment during delivery · operational
R5
Late submission of an interim report · compliance
Notes: Qualitative analysis assesses each identified risk against two parameters, the probability of occurrence and the degree of impact on the project's objectives, using a scale such as low, medium and high. Plotting risks in the probability–impact matrix allows them to be prioritised by their level of criticality. The five risks shown are an illustrative example and reappear in the risk register in Section 2. Quantitative analysis, applied chiefly in large infrastructure and investment projects, estimates the expected monetary impact of a risk numerically and uses probabilistic modelling such as the Monte Carlo method.

## Slide 7
1.4 · RISK RESPONSE
Response Strategies for Threats and Opportunities
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
07
THREATS · NEGATIVE RISKS
MIRROR
OPPORTUNITIES · POSITIVE RISKS
Avoid
Eliminate the cause of the risk by changing the project plan
Exploit
Make sure that the opportunity is realised
Mitigate
Reduce the probability or the impact of the risk
Enhance
Increase its probability or its positive impact
Transfer
Shift the consequences to a third party: insurance, subcontracting
Share
Involve a third party better able to capture it
Accept
Acknowledge the risk consciously: passively, or actively with a contingency reserve
Accept
Take the benefit if it arises, without active pursuit
Notes: For negative risks (threats): avoidance eliminates the cause of the risk by changing the project plan; mitigation reduces its probability or impact; transfer shifts its consequences to a third party, for example through insurance or subcontracting; acceptance is a conscious acknowledgement of the risk without active response measures, either passive or active, with a contingency reserve for unforeseen costs. For positive risks (opportunities), mirror strategies apply: exploit, enhance, share and accept. Ask students to match each strategy to one risk from the previous slide.

## Slide 8
02
SECTION 2
The Risk Register, the Assumptions Log, the Contingency Plan and the Management of Uncertainty
What does the risk register record, and why is it a living document?
How are logframe assumptions tracked during implementation?
How does the management reserve differ from the contingency reserve?
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
08
Notes: Section 2 turns from the logic of risk management to its working documents: the risk register, the assumptions log and the contingency plan. It closes with the management of overall uncertainty, which cannot be handled risk by risk.

## Slide 9
2.1 · RISK REGISTER
The Risk Register: The Central Risk-Management Document
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
09
ID | Risk and source | Category | Probability / impact | Priority | Strategy | Response measures | Owner | Status
R1 | Exchange-rate fluctuations reduce the value of the grant | Financial and economic | High / Medium | High | Accept (active) | Contingency reserve for exchange-rate losses | Financial manager | Materialised
R2 | Security situation prevents an in-person training event | Political and security | High / High | High | Avoid | Deliver the event online instead | Host partner | Closed
R3 | Turnover of key staff at a partner organisation | Organisational and managerial | Medium / Medium | Medium | Mitigate | Deputies for key roles; documented procedures | Partner lead | Active
R4 | Damage to equipment during delivery | Operational | Low / High | Medium | Transfer | Insurance of the shipment | Procurement officer | Active
R5 | Late submission of an interim report | Compliance | Low / Medium | Low | Mitigate | Internal deadlines set ahead of the donor's deadline | Coordinator | Active
Illustrative example. Status options: active, materialised, closed.
A “living” document: the register is reviewed and updated regularly throughout the entire project life cycle, not only at the planning stage.
Notes: For each identified risk the register records a description and source, the category, probability and impact, priority, the chosen response strategy, specific response measures, the responsible person (risk owner) and the current status: active, materialised or closed. The rows are an illustrative example that matches the probability–impact matrix in Section 1. Stress that the register is a living document: it must be reviewed and updated regularly throughout the entire project life cycle, not only at the planning stage.

## Slide 10
2.2 · ASSUMPTIONS LOG
The Assumptions Log: Linking Design Logic and Risk Management
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
10
Logical framework
DESIGN STAGE
Intervention logic
Assumptions
Overall objective
External factor
Specific objective
External factor
Results
External factor
Activities
External factor
Assumptions log
IMPLEMENTATION STAGE
Records the status of each assumption:
Confirmed
At risk
Not fulfilled
Risk register
ONGOING RISK MANAGEMENT
Every assumption whose likelihood of occurrence is uncertain is a potential source of risk to be managed in the register.
1 Identify
2 Assess
3 Plan the response
Assumptions are external factors that the project team does not control: the log keeps the design logic of the logframe connected to risk management throughout implementation.
Notes: The assumptions of the logical framework (Lecture 2) are, by their nature, external factors not controlled by the project team. It is therefore advisable to maintain a separate assumptions log that records the status of each assumption: confirmed, at risk or not fulfilled. The log ensures a direct link between the project's design logic and ongoing risk management at the implementation stage, since every assumption whose likelihood of occurrence is uncertain is a potential source of risk. This slide answers self-check question 1.

## Slide 11
2.3 · CONTINGENCY PLAN
The Contingency Plan: Acting When a Risk Materialises
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
11
High-priority risk
A plan is prepared in advance for each high-priority risk
Risk trigger
Predefined conditions show that the risk is actually occurring
Plan activated
The specific, pre-agreed response steps are carried out
Contingency reserve
Reserved resources fund the implementation of the plan
PREVENTION VERSUS RESPONSE
Preventive measures
Part of the response strategy: taken before a risk occurs to reduce its probability or impact.
Contingency plan
Specifies in advance what is done when the risk actually occurs, when the plan is activated and which resources are used.
Notes: For high-priority risks a contingency plan is developed. It sets out in advance the specific steps to be taken in response to the actual occurrence of a risk, rather than merely preventive measures. It defines the trigger conditions (risk triggers) under which the plan is activated and the contingency reserve of resources for its implementation. Illustrative example for discussion: if an in-person event cannot take place, a pre-agreed online format is activated and funded from the reserve.

## Slide 12
2.4 · MANAGEMENT OF UNCERTAINTY
Contingency Reserve versus Management Reserve
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
12
PROJECT RESOURCES · SCHEMATIC
Management reserve
overall uncertainty
Contingency reserve
identified risks
Planned budget and schedule
resources for planned activities
 | Contingency reserve | Management reserve
Responds to | Identified risks recorded in the risk register | Overall uncertainty: the cumulative effect of many small factors that cannot be identified in advance
Link to risks | Tied to specific high-priority risks and their contingency plans (or active acceptance) | Not tied to any specific risk: a general reserve of project resilience
Form | Resources set aside to implement the contingency plan | Additional budgetary and time buffer, plus flexible and adaptive management
Contingency reserves answer the risks that can be named; the management reserve answers those that cannot.
Notes: Unlike identified risks, overall project uncertainty is the cumulative effect of a multitude of small, individually insignificant factors that cannot be exhaustively identified in advance. The contingency reserve is linked to specific identified risks and their contingency plans, or to active acceptance. The management reserve is an additional budgetary and time buffer not tied to any specific risk; it serves as a general reserve of project resilience and is combined with flexible, adaptive management processes in the consortium. This slide answers self-check question 2.

## Slide 13
03
SECTION 3
Project Communication: Internal and External Communication, Visibility, Dissemination and Exploitation
Who communicates with whom inside and outside the consortium?
How do visibility, dissemination and exploitation differ?
What does a communication plan define?
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
13
Notes: Section 3 distinguishes internal from external communication and three related but distinct concepts that donors treat separately: visibility, dissemination and exploitation of results. The communication plan brings all of these together in one document.

## Slide 14
3.1–3.2 · INTERNAL AND EXTERNAL COMMUNICATION
Internal and External Communication
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
14
Internal communication
Interaction among consortium participants
Coordinator
Partners
Steering committee
Working groups
THE INTERNAL COMMUNICATION PLAN DEFINES
Channels
Frequency
Formats
Escalation procedures
External communication
Interaction with those outside the consortium
External stakeholders
Target groups
Mass media
Wider public
RELATED ACTIVITIES
Visibility
Dissemination
Exploitation
Communication plan
Notes: Internal communication ensures effective interaction among consortium participants: the coordinator, the partners, the steering committee and the working groups (see Lecture 5, Section 5). The internal communication plan defines the channels, frequency and formats of information exchange, as well as procedures for escalating problematic issues. External communication encompasses the project's interaction with external stakeholders, target groups, the mass media and the wider public.

## Slide 15
3.2 · THREE RELATED CONCEPTS
Visibility, Dissemination and Exploitation of Results
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
15
Visibility
Acknowledge the funding
Essence: Public acknowledgement of the project's source of funding
Means: Donor logos and funding disclaimers on all materials, websites and publications
Status: Legally binding under most grant agreements, including EU programmes
Dissemination
Make the results known
Essence: Systematic publication of results for scientific, professional and governmental audiences
Means: Conferences, publications, the project website, social media
Aim: Maximum awareness of the project and its achievements
Exploitation
Put the results to use
Essence: Practical application of results after the project ends
Forms: Integration into partners' work; commercialisation where applicable; uptake into policy or practice
Link: Project sustainability (Lecture 8)
EU example: the EU emblem with the funding statement “Funded by the European Union” or “Co-funded by the European Union”, spelled out in full next to the emblem, and at least as large as the biggest other logo.
Source: European Commission, “Communicating and raising EU visibility”, commission.europa.eu (accessed September 2026).
Notes: Visibility is the set of measures for publicly acknowledging the project's source of funding, including the mandatory placement of the donor's logos and funding disclaimers on all materials, websites and publications; for most donors, including EU programmes, it is a legally binding condition of the grant agreement. Dissemination is the systematic publication of results for scientific, professional and governmental audiences through conferences, publications, the project website and social media, to maximise awareness. Exploitation is the practical application of results after completion: integration into partners' activities, commercialisation where applicable, and institutional uptake into policy or practice (Lecture 8, Section 5). For self-check question 3: the European Commission requires EU-funded projects to display the EU emblem with the funding statement 'Funded by the European Union' or 'Co-funded by the European Union', spelled out in full next to the emblem; if other logos are shown, the EU emblem must be at least as large as the biggest of them (source: European Commission, 'Communicating and raising EU visibility').

## Slide 16
3.3 · COMMUNICATION PLAN
The Communication Plan: Audience, Message, Channel, Frequency
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
16
Target audience | Key message | Channel and format | Frequency | Responsible | Effectiveness indicator
Consortium partners | Progress, deadlines, decisions | Online meetings; shared workspace | Monthly | Coordinator | Attendance; actions completed
Target groups | Availability and benefits of new training resources | Workshops; e-newsletter | Quarterly | Training partner | Participants; downloads
Public authorities | Evidence and policy recommendations | Policy brief; round table | At key milestones | Coordinator | Meetings held; follow-up requests
Academic and professional community | Research findings and methods | Conference papers; journal articles | Annually | Research partners | Publications presented
Mass media and wider public | Project aims, results and donor support | Website; social media; press releases | Monthly | Communication officer | Reach; engagement
Illustrative example.
One document for all communication: every audience has a message, a channel, a frequency, a responsible person and measurable indicators such as reach and engagement.
Notes: The communication plan consolidates internal and external communication, visibility, dissemination and exploitation. For each target audience it defines the key message, the channel, the format, the frequency and the person responsible for implementation, as well as indicators of the effectiveness of communication activities such as reach and engagement. The rows are an illustrative example for a capacity-building project; ask students to adapt one row to a project they know.

## Slide 17
04
SECTION 4
Stakeholder Management and Intercultural Interaction in an International Consortium
How do stakeholders' positions change during implementation?
When should the power–interest matrix be updated?
Which practical tools support intercultural cooperation?
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
17
Notes: Section 4 moves from the stakeholder analysis carried out at the design stage (Lecture 2) to the continuous management of stakeholders during implementation. It then gives the intercultural factors discussed in Lecture 1 an operational dimension.

## Slide 18
4.1 · STAKEHOLDER MANAGEMENT
Stakeholder Management at the Implementation Stage
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
18
Keep satisfied
informed of key decisions
Key players
active, continuous engagement
Minimal monitoring
monitoring only
Keep informed
regular information
POWER / INFLUENCE
INTEREST
Public authority
New stakeholder
Quadrants as in Lecture 2; gold dots show illustrative shifts.
A CONTINUOUS CYCLE DURING IMPLEMENTATION
1
Monitor changes in stakeholders' positions, interests and influence
2
Update the power–interest matrix built at the design stage (Lecture 2)
3
Adjust the engagement strategy in line with actual events
Typical triggers: new stakeholders emerge, or public authorities change their position.
Notes: Building on the stakeholder analysis carried out at the design stage (Lecture 2, Section 3), stakeholder management during implementation involves continuously monitoring changes in stakeholders' positions, interests and influence, updating the power–interest matrix, and adjusting the engagement strategy in line with actual events. The quadrant labels repeat Lecture 2. The two dots are illustrative: a public authority whose interest grows moves into the key-player quadrant, and a newly emerging stakeholder must be placed on the grid.

## Slide 19
4.2 · INTERCULTURAL INTERACTION
Managing Intercultural Interaction in the Consortium
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
19
Cultural differences (Lecture 1, Section 6) acquire an operational dimension at the implementation stage.
Shared ways of working
Explicitly align expectations on punctuality, decision-making style and feedback.
Intercultural briefing
Held at the start of implementation for new team members.
Cultural mediators
Appointed within partner organisations to bridge cultural differences.
Avoiding ethnocentrism
Consciously avoiding assumptions about the “correct” way of working.
Recall Lecture 1: power distance (Hofstede) and time orientation (Hall) shape expectations about hierarchy, decision-making and deadlines.
Notes: The factors of intercultural difference discussed in Lecture 1 (Section 6) acquire an operational dimension at the implementation stage. Practical tools include establishing shared ways of working that explicitly align expectations regarding punctuality, decision-making style and feedback; an intercultural briefing at the start of implementation for new team members; appointing cultural mediators within partner organisations; and consciously avoiding ethnocentric assumptions about the 'correct' way of working.

## Slide 20
05
SECTION 5
Quality Management of Deliverables, Peer Review and Compliance with Donor Requirements
How are quality standards and acceptance criteria set?
How does quality assurance differ from quality control?
Why do peer review and donor-compliance checks matter?
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
20
Notes: Section 5 follows a deliverable from quality planning through quality assurance and quality control to internal peer review and the final check against the donor's formal and substantive requirements.

## Slide 21
5.1–5.2 · QUALITY MANAGEMENT
Quality Planning, Quality Assurance and Quality Control
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
21
Planning stage
QUALITY PLANNING
Standards and acceptance criteria
Defined for each deliverable and agreed with donor requirements and target-group expectations.
Development
QUALITY ASSURANCE
Preventive · process-oriented
Prevents defects by adhering to established standards and procedures for developing deliverables.
Deliverable completed
QUALITY CONTROL
Reactive · checks the result
Checks the already-created deliverable against the established criteria.
Approval or submission
OUTCOME
Final approval or submission
Quality control takes place before the deliverable is finally approved or submitted to the donor.
Notes: Project quality management starts at the planning stage by defining the quality standards that deliverables must meet, including acceptance criteria for each deliverable, agreed with donor requirements and the expectations of target groups. Quality assurance is preventive and process-oriented: it prevents defects by adhering to established standards and procedures while deliverables are developed. Quality control is reactive: it checks an already-created deliverable against established criteria before its final approval or submission to the donor. This slide answers self-check question 4.

## Slide 22
5.3 · PEER REVIEW
Internal Peer Review of Deliverables
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
22
STEP 1
Draft
The responsible partner develops the deliverable
STEP 2
Independent review
A consortium member not involved in its development assesses it against predefined criteria
STEP 3
Revision
The authors address the reviewer's comments
STEP 4
Submission
The deliverable goes to the donor or is published for an external audience
DELIVERABLES TYPICALLY PEER-REVIEWED
Reports
Analytical materials
Learning resources
Three defining features
Independence: the reviewer did not develop the deliverable
Predefined criteria: agreed before the review starts
Timing: before submission to the donor or publication
Notes: Internal peer review is a common practice for assuring the quality of substantive deliverables such as reports, analytical materials and learning resources. A deliverable is assessed by an independent member of the consortium who was not involved in its direct development, against predefined criteria, before it is submitted to the donor or published for an external audience. The revision step shows how the authors typically respond to the reviewer's comments before submission.

## Slide 23
5.4 · DONOR COMPLIANCE
Monitoring Compliance with Donor Requirements
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
23
Systematic verification that every deliverable complies with the donor's formal and substantive requirements:
Reporting templates
Adherence to the donor's prescribed reporting templates.
Visibility requirements
Logos, funding statements and disclaimers, as set out in Section 3.
Grant agreement terminology
Consistent use of the terms of the grant agreement across deliverables.
Horizontal requirements
May be verified separately when interim and final reports are assessed (Lecture 8).
Gender equality
Accessibility
Environmental sustainability
Notes: A separate dimension of quality management is the systematic verification that all deliverables comply with the donor's formal and substantive requirements: adherence to reporting templates, the visibility requirements discussed in Section 3, grant agreement terminology, and horizontal requirements such as gender equality, accessibility and environmental sustainability. Horizontal requirements may be subject to separate verification when interim and final reports are assessed (Lecture 8, Section 3).

## Slide 24
06
SECTION 6
Conflicts within the Project Team and Mechanisms for Their Resolution
Where do conflicts in an international consortium come from?
Which behavioural style suits which conflict?
Which formal mechanisms does a consortium rely on?
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
24
Notes: Section 6 identifies five typical sources of conflict in an international consortium, presents the Thomas–Kilmann model of conflict-handling styles, and closes with the formalised resolution mechanisms anchored in the Consortium Agreement (Lecture 4).

## Slide 25
6.1 · SOURCES OF CONFLICT
Five Sources of Conflict in an International Consortium
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
25
Sources of conflict
in an international consortium
Allocation of resources
Disagreements over the budget and roles among partners
Divergent understanding of tasks
Imprecise definition of the scope of work; related to scope creep (Lecture 5)
Intercultural misunderstandings
Differing communication styles and management traditions
Personal incompatibility
Between individual members of the project team
Conflicting priorities
A partner's organisational interests versus the consortium's shared objectives
Notes: Conflicts within the project team may arise from disagreements over the allocation of resources (budget, roles) among partners; divergent understandings of tasks owing to an insufficiently precise definition of the scope of work, related to scope creep (Lecture 5, Section 2); intercultural misunderstandings arising from differing communication styles and management traditions; personal incompatibility among team members; and conflicting priorities between the organisational interests of an individual partner and the shared objectives of the consortium.

## Slide 26
6.2 · CONFLICT RESOLUTION STYLES
The Thomas–Kilmann Model: Five Conflict Styles
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
26
ASSERTIVENESS: attention to own interests
COOPERATIVENESS: attention to the other party's interests
Low
High
Competing
Collaborating
Compromising
Avoiding
Accommodating
Avoiding
Low attention to both parties' interests
Accommodating
Priority given to the other party's interests
Competing
Priority given to one's own interests
Compromising
Partial satisfaction of both parties' interests
Collaborating
A solution that fully satisfies both parties
An effective manager commands the full range of styles and consciously selects the one suited to the nature of the conflict and its potential impact on the project.
Notes: The Thomas–Kilmann model identifies five behavioural styles depending on the relative attention given to one's own interests (assertiveness) and to those of the other party (cooperativeness). Avoiding: low attention to both. Accommodating: priority to the other party's interests. Competing: priority to one's own interests. Compromising: partial satisfaction of both parties' interests. Collaborating: a solution that fully satisfies both parties. No style is always best: an effective manager of an international project commands the full range and consciously selects the most appropriate style. For self-check question 5, ask when time pressure or a minor issue makes a quick compromise preferable to a lengthy search for a fully collaborative solution.

## Slide 27
6.3 · FORMALISED MECHANISMS
Formalised Mechanisms for Resolving Disputes
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
27
CONSORTIUM AGREEMENT · DISPUTE RESOLUTION
1
Inter-partner dispute
Settled by the procedure set out in the Consortium Agreement
2
Steering committee
Escalation to the steering committee, as the agreement provides
3
Mediation or arbitration
The last resort
ESCALATION
SUPPORTING MECHANISMS
Regular structured meetings
Allow tension to be identified at an early stage
Neutral facilitator
Involved in complex disputes between partners
Documentation (minuting)
Agreements reached are clearly recorded in the minutes
Notes: The Consortium Agreement (Lecture 4, Section 4) sets out dispute resolution procedures, including the possibility of escalation to the steering committee or, as a last resort, to mediation or arbitration. Supporting mechanisms include regular structured meetings that allow tension to be identified early, the involvement of a neutral facilitator for complex inter-partner disputes, and the clear documentation (minuting) of agreements reached. This slide answers self-check question 6.

## Slide 28
SUMMARY
Key Takeaways
Risk management is a four-stage cycle of identification, analysis, assessment and response planning, applied to threats and to opportunities.
The risk register is a living document; the assumptions log links the logframe's assumptions to risk management during implementation.
Contingency plans and reserves address identified risks; the management reserve and flexible management address overall uncertainty.
Visibility acknowledges the donor, dissemination makes results known and exploitation puts them to use; stakeholder engagement is adjusted continuously.
Quality assurance prevents defects, quality control checks finished deliverables; peer review and compliance checks come before submission.
Conflicts arise from resources, scope, culture, personalities and priorities; managers choose a style consciously and rely on the Consortium Agreement.
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
28
Notes: Use the six takeaways to recap the lecture's three management functions (risk, communication and quality) and the handling of conflict. Each takeaway corresponds to one section of the lecture.

## Slide 29
SELF-CHECK
Questions for Self-Assessment
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
29
1
Explain the connection between the assumptions of the logical framework (Topic 2) and the project's risk register.
2
How does the management reserve differ from the contingency reserve?
3
Give an example of a visibility requirement for a project funded under an EU programme.
4
How does quality assurance differ from quality control?
5
Describe a situation in which the “compromising” style would be more appropriate than the “collaborating” style when resolving a conflict within a consortium.
6
What role does the Consortium Agreement play in resolving inter-partner disputes?
Notes: Question 1: slide on the assumptions log. Question 2: slide on contingency and management reserves. Question 3: slide on visibility, dissemination and exploitation. Question 4: slide on quality assurance and quality control. Question 5: Thomas–Kilmann slide. Question 6: slide on formalised mechanisms.

## Slide 30
SOURCES
Recommended Reading
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
30
A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edition. Project Management Institute, 2021.
Communication and Visibility Manual for European Union External Actions. European Commission.
Thomas K. W., Kilmann R. H. Thomas-Kilmann Conflict Mode Instrument.
Practice Standard for Project Risk Management. Project Management Institute.
Hofstede G., Hofstede G. J., Minkov M. Cultures and Organizations: Software of the Mind. McGraw-Hill.

## Slide 31
Thank you for your attention
Questions and discussion
NEXT
Lecture 8. Monitoring, Evaluation, Reporting and Sustainability of International Project Results
LECTURE 7 · INTERNATIONAL PROJECT ACTIVITY
31