## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 3
Developing an International Project Proposal and Grant Application
From the structure of a proposal and the logic of objectives to the work plan, the application form and the criteria used by evaluators
Content Module 1 · Design and Preparation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
02
01
The structure of an international project proposal: executive summary, relevance, objectives, results, methodology, impact and sustainability
02
Formulating the overall goal, specific objectives, expected results and indicators
03
Constructing work packages, tasks, activities, deliverables, milestones and the implementation plan
04
Methodology for preparing the application form and the technical description of the project
05
Criteria for evaluating applications: relevance, quality, impact, sustainability, cost-effectiveness
06
Common mistakes in writing grant applications and ways to prevent them
Notes: The lecture follows the path of an application from its overall structure to the moment it is scored by evaluators. Sections 1–3 deal with the substance of the proposal: its structure, the formulation of objectives and the work plan. Section 4 turns to the technical preparation of the application form; Sections 5 and 6 look at the proposal through the eyes of the evaluator and summarise the typical reasons for rejection.

## Slide 3
01
SECTION 1
The Structure of an International Project Proposal
Which sections does almost every proposal contain?
Why is the executive summary written last?
How do outputs, outcomes, impact and sustainability differ?
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
03
Notes: Despite differences between donor templates, the overwhelming majority of international project proposals — whether a concept note or a full application — share a common logical structure. That structure reflects the sequence of argumentation from the problem to the expected effect.

## Slide 4
1 · FROM THE PROBLEM TO THE EXPECTED EFFECT
The Anatomy of an International Project Proposal
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
04
1
Executive summary
The essence of the project on no more than one page. Written last.
2
Relevance and rationale
Evidence of the problem and its scale; fit with the priorities of the call.
3
Objectives
The overall goal and specific objectives, following the intervention logic.
4
Methodology
The approach, the choice of methods and formats, and their link to the results.
5
Work plan
Work packages, tasks and activities, with responsible partners and timeframes.
6
Expected results and impact
Outputs, outcomes and long-term impact, with indicators.
7
Sustainability
How the results keep their value after donor funding ends.
8
Management and consortium
Management structure, partner roles, coordination and communication.
9
Budget
Detailed costs by expenditure item, aligned with the work plan.
10
Annexes
Partner documents, CVs, letters of support, declarations, legal and financial documents.
Notes: Walk through the ten components in order: they follow the argument from the problem to the expected effect. The executive summary (highlighted) opens the document but is written last. Relevance draws on statistical data, research and strategic documents and shows alignment with the priorities of the specific call (Lecture 2, Section 6). The work plan is examined in Section 3 of this lecture, and the budget in Topic 6. Annexes include partner documents, CVs of key personnel, letters of support, declarations, and the applicant's legal and financial documentation.

## Slide 5
1 · EXECUTIVE SUMMARY
The Executive Summary: Read First, Written Last
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
05
EXECUTIVE SUMMARY
As a rule, no more than one page
The problem
The goal
Key activities
Expected results
Composition of the consortium
Budget
Duration
READING ORDER
Opens the document
1
2
3
4
5
6
7
8
9
10
WRITING ORDER
Drafted after sections 2–10 are agreed
2
3
4
5
6
7
8
9
10
1
The summary condenses every other section. It can therefore be finalised only once all sections of the application have been finalised and agreed by the partners.
Notes: The executive summary is a concise presentation of the essence of the project — as a rule, no more than one page. It covers the problem, the goal, the key activities, the expected results, the composition of the consortium, and the budget and duration. Although it appears at the beginning of the document, it is traditionally written last, once all sections of the application have been finalised and agreed. Ask students: what would happen to the summary if it were written first and the work plan later changed?

## Slide 6
1 · EXPECTED RESULTS, IMPACT AND SUSTAINABILITY
From Outputs to Impact — and Beyond the Funding Period
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
06
EXPECTED RESULTS AND IMPACT
Impact
Long-term change
Outcomes
Intermediate effects
Outputs
Immediate results of the project
Each level is described with quantitative and qualitative indicators.
SUSTAINABILITY
How will the project's results retain their value after donor funding ends?
Institutional
Financial
Political
Environmental
Evaluators return to this question: sustainability is a separate block of evaluation criteria (Section 5).
Notes: The section on expected results and impact describes three levels: the immediate results of the project (outputs), the intermediate effects (outcomes) and the long-term impact, each with quantitative and qualitative indicators. The sustainability section justifies how the project's results will retain their value after donor funding ends. The lecture distinguishes four dimensions: institutional, financial, political and environmental sustainability. The same question returns at the evaluation stage as a separate criterion (Section 5).

## Slide 7
02
SECTION 2
Formulating the Overall Goal, Specific Objectives, Expected Results and Indicators
How is the overall goal worded differently from the specific objective?
Why are activities not objectives?
What makes a formulation SMART, and an indicator informative?
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
07
Notes: The formulation of objectives must strictly follow the hierarchy of the intervention logic examined in Topic 2. This section adds a number of applied rules for wording each level, the SMART test, and the design of result indicators.

## Slide 8
2 · HIERARCHY OF THE INTERVENTION LOGIC
Formulating Each Level of the Hierarchy
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
08
LEVEL
HOW TO FORMULATE IT
MEASURED BY
Overall goal
A contribution to a broader strategic goal: no single project can guarantee its achievement on its own.
“to contribute to …”, “to support the achievement of …”
Long-term impact
Specific objective
A concrete, measurable effect for the target group, arising from the use of the project's results.
“the level of … has been raised”, “access to … has been expanded”, “capacity … has been strengthened”
Outcome indicators
Expected results
The immediate results (outputs) of the project, formulated according to the SMART rule.
Output indicators
Activities
What the project does. Activity wording belongs here, not at the level of objectives.
“to conduct …”, “to organise …”
Means and resources
Notes: The overall goal is formulated as a contribution — 'to contribute to', 'to make a contribution to', 'to support the achievement of' — because no single project can, on its own, guarantee the achievement of a broader strategic goal. The specific objective is a concrete, measurable effect for the target group arising from the use of the project's results; it is worded as a desired change of state rather than as an activity. Wordings such as 'to conduct' or 'to organise' belong at the level of activities. Output indicators measure the results, outcome indicators the specific objective.

## Slide 9
2 · A COMMON MISTAKE
Substituting Means for Objectives — and the Correction
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
09
ACTIVITY AND PRODUCT
“To conduct 10 training seminars for 200 entrepreneurs”
OBJECTIVE: A CHANGE OF STATE
“The level of export readiness of small and medium-sized enterprises in the region has been raised”
The numbers are kept:
10 training seminars
+
200 participants
serve as a result indicator
Wording for objectives: a change of state
“has been raised” · “has been expanded” · “has been strengthened”
Wording for activities: an action
“to conduct” · “to organise”
Notes: A common mistake is the substitution of means for objectives. 'To conduct 10 training seminars for 200 entrepreneurs' describes an activity and a product, not an objective. A correct formulation of the objective would be 'The level of export readiness of small and medium-sized enterprises in the region has been raised'. The seminars and the number of participants are not lost: they serve as a result indicator. This example answers self-assessment question 2.

## Slide 10
2 · QUALITY OF FORMULATIONS
The SMART Rule and the Design of Result Indicators
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
10
S
Specific
M
Measurable
A
Achievable
within the available resources
R
Relevant
to the identified problem
T
Time-bound
The test applies to every formulation of objectives and results.
Combine two dimensions
QUANTITATIVE
Number of participants; number of documents prepared
QUALITATIVE
Level of satisfaction; growth in competencies measured by pre- and post-testing
Distinguish two levels
OUTPUT INDICATORS
Measure the immediate results of the project (outputs)
OUTCOME INDICATORS
Measure the intermediate effects for the target group (outcomes)
Notes: Every formulation of objectives and results must be Specific, Measurable, Achievable within the available resources, Relevant to the identified problem, and Time-bound. Result indicators should combine a quantitative dimension — the number of participants, the number of documents prepared — with a qualitative one — the level of satisfaction, or growth in competencies measured by pre- and post-testing. They should also distinguish output indicators, which measure the immediate results, from outcome indicators, which measure the intermediate effects.

## Slide 11
03
SECTION 3
Work Packages, Deliverables, Milestones and the Implementation Plan
What is a work package and what does it contain?
What does the 100% rule require of a WBS?
How does a milestone differ from a deliverable?
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
11
Notes: This section turns objectives into a plan of work: work packages, the work breakdown structure, deliverables and milestones, and the implementation timetable. Detailed scheduling tools such as the Gantt chart and the critical path are examined in Topic 5.

## Slide 12
3.1 · WORK PACKAGES
Work Packages: Logically Complete Blocks of Activity
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
12
A work package unites activity around a common theme or function. A typical structure:
WP1
Project Management
WP2
Research and Analysis
WP3
Development of Training Materials
WP4
Piloting and Implementation
WP5
Communication and Dissemination of Results
Each work package has
A designated leader (lead partner)
Participants
A budget
A timeframe
A list of expected deliverables
Notes: A work package is a logically complete block of project activity, united by a common theme or function. The lecture's example: WP1 Project Management, WP2 Research and Analysis, WP3 Development of Training Materials, WP4 Piloting and Implementation, WP5 Communication and Dissemination of Results. Each work package has a designated leader (lead partner), participants, a budget, a timeframe and a list of expected deliverables.

## Slide 13
3.2 · WORK BREAKDOWN STRUCTURE
The WBS: Decomposing the Scope of Work
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
13
PROJECT
WORK PACKAGES
TASKS
ACTIVITIES
OPERATIONS
Project
WP1
Management
WP2
Research
WP3
Materials
WP4
Piloting
WP5
Dissemination
Task 3.1
Task 3.2
Task 3.3
Activity 3.2.1
Activity 3.2.2
Operation 1
Operation 2
Operation 3
Illustrative example
Σ = 100% of the project
Σ = 100% of WP3
Σ = 100% of Task 3.2
Σ = 100% of Activity 3.2.1
The 100% rule: the elements at each lower level must describe the full scope of the element above — with neither surplus nor deficit.
Notes: The WBS is a hierarchical decomposition of the entire scope of project work into progressively smaller elements: work packages, tasks, activities and individual operations. The underlying principle is the 100% rule: the sum of the elements at each lower level must fully describe the scope of the element at the level above — with neither surplus nor deficit. The diagram decomposes one branch (WP3) as an illustration; every other branch is decomposed in the same way. This slide answers self-assessment question 3.

## Slide 14
3.3 · DELIVERABLES AND MILESTONES
Deliverables versus Milestones
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
14
Deliverable
Milestone
What it is
A specific, documented result of the completion of a task
A significant event marking the completion of an important stage or the achievement of an intermediate result
Form
A tangible product: a report, training manual, database, prototype or publication
A point in time: unlike an activity, it has no duration or resource requirement
What it is used for
Submitted to the donor in accordance with the schedule
Monitoring progress and making go/no-go decisions
Each work package lists its expected deliverables; milestones mark the completion of important stages across the work plan.
Notes: A deliverable is a specific, documented result of the completion of a task — a report, training manual, database, prototype or publication — submitted to the donor in accordance with the schedule. A milestone is a significant event in the life of the project marking the completion of an important stage or the achievement of an intermediate result. Unlike an activity, it has no duration or resource requirement; it is used to monitor progress and to make go/no-go decisions. This slide answers self-assessment question 4.

## Slide 15
3.4 · SCHEDULING
The Implementation Timetable as a Gantt Chart
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
15
Months 1–6
Months 7–12
Months 13–18
Months 19–24
MILESTONES
WP1 Project management
WP2 Research and analysis
WP3 Training materials
WP4 Piloting and implementation
WP5 Communication and dissemination
MS1 · Analysis completed
MS2 · Materials approved
MS3 · Piloting completed
Duration of a work package
Milestone (no duration)
Deliverable submitted
Dependency between work packages
Illustrative example of a 24-month project. Scheduling tools, including the Gantt chart and the critical path, are examined in detail in Topic 5.
Notes: The work plan is accompanied by an implementation timetable, usually presented as a Gantt chart. It visualises the duration and sequence of activities and the interdependencies between work packages. The chart here is an illustrative 24-month example built on the five work packages from the lecture: the management and dissemination packages run throughout, while research, materials and piloting follow one another. Gantt charts and the critical path are examined in detail in Topic 5.

## Slide 16
04
SECTION 4
Preparing the Application Form and the Technical Description
What must be extracted from the Guidelines for Applicants?
Why can a departure from the template lead to rejection?
Which checks should precede submission?
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
16
Notes: Preparation of the application form is the final technical stage in drawing up a project proposal, in accordance with the requirements of the specific donor and call. The methodology comprises six steps, from the careful study of the Guidelines for Applicants to the technical checks before submission.

## Slide 17
4 · PREPARATION METHODOLOGY
Six Steps in Preparing the Application Form
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
17
Study the Guidelines
Formal requirements, eligibility of applicant, partners and costs, evaluation methodology
Use the official template
Standard e-form or Part B / Technical Description
Respect length limits
Strict page or character limits for each section
Keep sections consistent
Identical terms, indicators, budget lines and WP titles
Edit language and style
Clear, concise, well-argued text for a reviewer from another field
Run technical checks
Mandatory fields, signatures, eSignatures, early submission
Departure from the structure of the official template is grounds for formal rejection, and text that exceeds a length limit is truncated automatically by the submission system.
Notes: Step 1: the Guidelines for Applicants set out the formal submission requirements (file format, length, language, deadline), the eligibility criteria for the applicant, partners and costs, and the evaluation methodology. Step 2: most donors, including EU programmes via the Funding & Tenders Portal, require a standardised electronic form or a structured technical-description template (Part B / Technical Description); departure from its structure is grounds for formal rejection. Step 3: each section has a strict page or character limit, and the submission system automatically truncates excess text. Steps 4–6 are developed on the next two slides.

## Slide 18
4 · CONSISTENCY AND STYLE
One Proposal, One Vocabulary
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
18
Must be identical in:
All sections
The budget
The annexes
Terminology
=
=
Indicators
=
=
Budget lines
=
=
Work package titles
=
=
Language and style
AIM FOR
Clear language
Concise wording
Well-argued statements
AVOID
Excessive use of the passive voice
Sector-specific jargon that a reviewer from another field cannot follow
Notes: Terminology, indicators, budget lines and work package titles must be identical throughout all sections of the application, the budget and the annexes. A mismatch between sections is one of the common mistakes discussed in Section 6. On style: use clear, concise, well-argued language, avoid excessive use of the passive voice, and avoid sector-specific jargon that a reviewer from another field cannot follow.

## Slide 19
4 · FORMAL COMPLIANCE
From the Guidelines for Applicants to a Safe Submission
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
19
WHAT THE GUIDELINES FOR APPLICANTS SET OUT
Formal submission requirements
File format, length, language and deadline.
Eligibility criteria
For the applicant, the partners and the costs.
Evaluation methodology
The criteria and procedure by which applications are assessed (Section 5).
Pre-submission checklist
All mandatory fields correctly completed
Signatures and stamps present
eSignatures of the coordinator and partners valid
Structure of the official template followed
Page and character limits respected
All mandatory annexes attached
Submit well in advance: the portal may fail in the final hours before the deadline.
Notes: The Guidelines for Applicants are the document that sets out the formal submission requirements, the eligibility criteria and the evaluation methodology. Before submission, verify that all mandatory fields have been correctly completed, that signatures and stamps are present, and that the eSignatures of the coordinator and partners are valid. Submit well in advance: technical failures on the portal are possible in the final hours before the deadline. Together with the checklist of formal requirements (Section 6), this answers self-assessment question 6.

## Slide 20
05
SECTION 5
Criteria for Evaluating International Project Applications
Which blocks of criteria do evaluators apply?
How do individual and overall thresholds work?
How do Horizon Europe and Erasmus+ set scores and thresholds?
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
20
Notes: Donors, including EU programmes, evaluate project proposals through independent external experts using a unified system of criteria. Note how the blocks correspond to sections of the proposal discussed in Section 1: relevance, results and impact, sustainability and the budget.

## Slide 21
5 · EVALUATION CRITERIA
Five Blocks of Evaluation Criteria
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
21
Applications are scored by independent external experts using a unified system of criteria.
Relevance
Fit with the objectives and priorities of the call; relevance of the problem; choice of target groups; European added value.
Quality of design and implementation
Internal coherence; a realistic work plan and budget; methodology fit; consortium capacity; risk management.
Impact
Scale and depth of change for target groups and stakeholders; dissemination and exploitation; horizontal priorities.
Sustainability
Likelihood that results last after funding ends: partners' capacity, financial mechanisms, scaling up or replication.
Cost-effectiveness / value for money
Budget in relation to expected results; sound budget lines; no excessive or unjustified funding.
Each criterion is scored on a points scale, with a threshold for each criterion and for the total — the logic is shown on the next slide.
Notes: Relevance: correspondence to the objectives and priorities of the call, relevance of the problem, soundness of the choice of target groups, and European added value for transnational cooperation. Quality of design and implementation: internal coherence between problem, objectives, activities and resources; realism of the work plan and budget; fit between methodology and tasks; consortium capacity (experience, competence, complementarity); quality of the risk-management plan. Impact: scale and depth of change, dissemination and exploitation, horizontal priorities. Sustainability: preservation of results after funding ends. Cost-effectiveness: the relationship between budget and results, and the absence of excessive or unjustified funding.

## Slide 22
5 · SCORING AND THRESHOLDS
Two Filters Before Ranking: The Logic of Thresholds
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
22
Each criterion is scored
on a points scale, e.g. 0–5
Filter 1: each criterion
must reach its individual threshold
Filter 2: the total score
must reach the overall threshold
Only then is the application ranked
failing either filter means rejection
ILLUSTRATIVE EXAMPLE
Scale 0–5 · threshold 3 per criterion · overall threshold 15 of 25
Criterion
Threshold
Application A
Application B
Relevance
3
5
4
Quality of design and implementation
3
4
4
Impact
3
5
3
Sustainability
3
2
3
Cost-effectiveness
3
5
4
Total score
15
21
18
A: rejected
below the threshold on sustainability, despite the higher total
B: ranked
passes both the individual and the overall thresholds
Notes: Each criterion is generally scored on a points scale, for example from 0 to 5. Thresholds are set both for each criterion individually and for the overall total score. Applications that fail to meet the thresholds are rejected regardless of their overall ranking. In the illustrative example, application A has the higher total but falls below the threshold on sustainability and is therefore rejected, while application B passes both filters and enters the ranking. This answers self-assessment question 5.

## Slide 23
5 · THRESHOLDS IN PRACTICE
Scores and Thresholds in Two EU Programmes
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
23
Below the threshold: the application is rejected
Scores at or above the threshold
Horizon Europe
Research and Innovation Actions · Innovation Actions
min / max
Excellence
3 / 5
Impact
3 / 5
Quality and efficiency of the implementation
3 / 5
≥ 10 / 15
overall threshold for the sum of the three scores; Impact is weighted 1.5 when ranking Innovation Actions
Erasmus+
Cooperation Partnerships (Key Action 2)
min / max
Relevance of the project
13 / 25
Quality of the project design and implementation
15 / 30
Quality of the partnership and the cooperation arrangements
10 / 20
Impact
13 / 25
≥ 70 / 100
overall minimum, plus at least half of the maximum points in each criterion
Sources: European Commission, Horizon Europe Work Programme 2026–2027, General Annexes, Annex D; Erasmus+ Programme Guide 2026, Part B: Cooperation partnerships.
Notes: Horizon Europe (Research and Innovation Actions and Innovation Actions, full applications): three award criteria — Excellence, Impact, and Quality and efficiency of the implementation — each scored out of 5, with a threshold of 3 per criterion and an overall threshold of 10 for the sum of the three scores; for ranking Innovation Actions, the Impact score is weighted 1.5. Erasmus+ Cooperation Partnerships: four criteria with maximum scores of 25, 30, 20 and 25 points; proposals must score at least 70 of 100 points and at least half of the maximum in each criterion. Note that the programmes group the five generic blocks differently — Horizon Europe, for example, has no separate sustainability criterion. Always check the current Work Programme or Programme Guide for the call in question.

## Slide 24
06
SECTION 6
Common Mistakes in Writing Grant Applications and Ways to Prevent Them
Which mistakes most often lead to rejection?
How can each of them be prevented?
At which stage should each safeguard be applied?
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
24
Notes: Analysis of the practice of rejecting project applications makes it possible to summarise the most common mistakes made by applicants. Each mistake has a practical preventive measure; several of these measures must be applied early — before drafting or already at the design stage.

## Slide 25
6 · MISTAKES AND PREVENTION
Seven Common Mistakes and Ways to Prevent Them
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
25
COMMON MISTAKE
WAY TO PREVENT IT
1
Mismatch with the call's priorities: the idea misses the call's thematic focus, however significant the problem
Analyse the Guidelines for Applicants in advance; consult the programme's National Contact Point
2
Vague or overambitious objectives: unachievable within the available resources and timeframe
Apply the SMART rule; match the scale of the stated results to the budget requested
3
No logical link between sections: indicators vs methodology, budget vs work plan
Construct the logframe matrix before drafting the sections; cross-check terminology throughout
4
Weak justification of the partnership: a formal list of partners without clear roles
Describe each partner's competencies and link them to specific tasks in the work plan
5
Sustainability as a declaration: general statements without a specific mechanism
Develop a concrete, realistic plan for institutional and financial sustainability at the design stage
6
Breach of formal requirements: length limits, template, missing annexes, late submission
Draw up a checklist of compliance with formal requirements; submit well in advance
7
Unrealistic or inappropriate budget: inflated or unclear items; donor's financial rules not met
Involve the consortium's financial manager in the budget, in parallel with the substantive part
Notes: Go through the seven mistakes in pairs with their prevention. Stress mistake 1: a problem of high social significance is not enough if it does not match the thematic focus of the specific call. Mistake 3 is best prevented by constructing the logframe matrix before drafting the sections. Mistake 7 links to Topic 6: the consortium's financial manager should prepare the budget in parallel with the substantive part of the application, not after it.

## Slide 26
6 · WHEN TO APPLY EACH SAFEGUARD
Building Prevention into the Preparation Process
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
26
Before drafting
1
Analyse the Guidelines for Applicants; consult the National Contact Point
3
Construct the logframe matrix before drafting the sections
While drafting
2
Apply the SMART rule; match the scale of results to the budget
4
Link each partner's competencies to specific tasks
5
Plan institutional and financial sustainability at the design stage
7
Prepare the budget with the financial manager, in parallel
Before submission
3
Cross-check terminology, indicators and budget lines
6
Work through the checklist of formal requirements
6
Submit well in advance of the deadline
Numbers refer to the seven mistakes on the previous slide. Several safeguards belong before or alongside drafting, not at the end.
Notes: The preventive measures from the lecture fall naturally into three moments. Before drafting: analyse the Guidelines for Applicants, consult the National Contact Point and construct the logframe matrix. While drafting: apply the SMART rule, link partner competencies to tasks, plan sustainability at the design stage, and prepare the budget in parallel with the substantive part. Before submission: cross-check terminology, go through the compliance checklist and submit well in advance. The numbers refer to the seven mistakes on the previous slide.

## Slide 27
SUMMARY
Key Takeaways
Most proposals share one logical structure, from the problem to the expected effect; the executive summary opens the document but is written last.
The overall goal is a contribution; the specific objective is a measurable change of state for the target group; activities are not objectives.
SMART formulations and indicators that combine quantitative and qualitative dimensions, and separate outputs from outcomes, make results verifiable.
Work packages, a WBS built on the 100% rule, deliverables, milestones and a Gantt chart turn objectives into an implementation plan.
The application form demands the official template, length limits, cross-section consistency, technical checks and early submission.
Evaluators score relevance, quality, impact, sustainability and cost-effectiveness against individual and overall thresholds; common mistakes are preventable.
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
27

## Slide 28
SELF-CHECK
Questions for Self-Assessment
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
28
1
Why is the executive summary traditionally prepared after work on all other sections of the application has been completed?
2
Give an example of the common mistake of “substituting means for objectives” and propose a correct formulation.
3
What is the 100% rule in constructing a Work Breakdown Structure (WBS)?
4
How does a milestone differ from a deliverable?
5
Explain the logic of thresholds in evaluating applications against individual criteria.
6
What steps help prevent breaches of the formal requirements for submitting an application?

## Slide 29
SOURCES
Recommended Reading
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
29
Aid Delivery Methods. Volume 1: Project Cycle Management Guidelines. European Commission, EuropeAid Cooperation Office.
Horizon Europe Programme Guide. European Commission, Directorate-General for Research and Innovation.
EU Grants: How to complete your ethics self-assessment. Funding & Tenders Portal Online Manual. European Commission.
A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edition. Project Management Institute, 2021.
Erasmus+ Programme Guide. European Education and Culture Executive Agency.

## Slide 30
Thank you for your attention
Questions and discussion
NEXT
Lecture 4. Grant Funding, Donor Programmes and Building an International Consortium
LECTURE 3 · INTERNATIONAL PROJECT ACTIVITY
30