## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 2
Project Design: Conceptualisation, Intervention Logic and Project Justification
From the analysis of problems and stakeholders to the theory of change, the logical framework matrix and strategic fit with donor priorities
Content Module 1 · Design and Preparation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
02
01
Project design as the initial element of managing an international project
02
Analysis of problems, needs, cause-and-effect relationships and target groups
03
Stakeholder analysis: identification, classification, interests, influence and engagement
04
Theory of change and intervention logic: shaping the logic of change in an international project
05
The logical framework matrix: objectives, results, indicators, sources of verification, assumptions and risks
06
Conformity of the project idea with the strategic priorities of EU programmes and international donors
Notes: The lecture follows the logic of the design process itself. Section 1 defines project design and its place in Project Cycle Management; Sections 2 and 3 cover the analysis of problems, needs, target groups and stakeholders; Section 4 introduces the theory of change and intervention logic; Section 5 formalises them in the logical framework matrix; Section 6 examines the strategic fit of the project idea with donor priorities.

## Slide 3
01
SECTION 1
Project Design as the Initial Element of Managing an International Project
What does project design involve?
Where is design located in Project Cycle Management?
Why are errors made at the design stage so costly?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
03
Notes: Project design is the bridge between an idea and a fundable project. In this section we define design, locate it within Project Cycle Management (PCM), set out the five qualities that good design must ensure, and consider why design errors are so difficult to correct later.

## Slide 4
1 · DEFINITION
What Is Project Design?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
04
Project design is a systematic analytical process of transforming a previously formulated idea into a structured, justified project concept suitable for implementation.
PROJECT DESIGN · PCM IDENTIFICATION AND FORMULATION
Project idea
A previously formulated idea
Identification
Analysis of problems, needs and project ideas
Formulation
Detailed design using the Logical Framework Approach
Submission
The project proposal is submitted to the donor
Notes: Project design is a systematic analytical process of transforming a previously formulated idea into a structured, justified project concept suitable for implementation. In the methodology of Project Cycle Management, design corresponds to the identification and formulation phases, which precede the submission of the project proposal to the donor. Recall from Lecture 1 that the Logical Framework Approach is mandatory at the formulation stage.

## Slide 5
1 · QUALITY OF DESIGN
Five Qualities That High-Quality Design Ensures
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
05
5
qualities that high-quality project design ensures
They are built in at the identification and formulation stages, before the proposal reaches the donor.
Relevance
Conformity with the problems and needs of target groups and with the donor's priorities.
Logical consistency (internal coherence)
A transparent cause-and-effect relationship between resources, activities, results and objectives.
Measurability
Objectively verifiable indicators of achievement at every level of objectives.
Feasibility
Planned activities match the available resources, time frame and the consortium's capacity.
Sustainability
The project's results retain their value after donor funding ends.
Notes: High-quality design ensures relevance (conformity with the problems and needs of target groups and with the donor's priorities); logical consistency or internal coherence (a transparent cause-and-effect relationship between resources, activities, results and objectives); measurability (objectively verifiable indicators of achievement at every level of objectives); feasibility (conformity of the planned activities with the available resources, time frame and the consortium's capacity); and sustainability (the capacity of the results to retain their value after donor funding ends).

## Slide 6
1 · THE CRITICAL IMPORTANCE OF DESIGN
Why Design Errors Are So Costly
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
06
Unclear formulation of the problem
The central negative state that the project seeks to overcome is not clearly defined.
Objectives replaced by means
The objective names a means (e.g. “to hold trainings”) instead of the desired change.
Insufficient stakeholder analysis
Relevant parties, their interests and their influence are overlooked.
CONSEQUENCE
Such errors generally cannot be corrected at later implementation stages without a substantial revision of the project.
Hence the critical importance of the design stage.
Notes: Errors made at the design stage — an unclear formulation of the problem, the substitution of objectives by the means of achieving them, or insufficient stakeholder analysis — generally cannot be corrected at later implementation stages without a substantial revision of the project. Illustrate the second error: 'to hold a series of training sessions' is a means; the objective is the change that those sessions should bring about for the target group. This underlines the critical importance of the design stage.

## Slide 7
02
SECTION 2
Analysis of Problems, Needs,
Cause-and-Effect Relationships and Target Groups
Which sources of evidence support a needs analysis?
How is a problem tree built and turned into an objective tree?
Who are the target groups, and what barriers do they face?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
07
Notes: Section 2 covers the analytical core of the logical framework approach: needs analysis, the problem tree, its transformation into an objective tree together with strategy analysis, and the analysis of target groups.

## Slide 8
2.1 · NEEDS ANALYSIS
Needs Analysis: Where the Evidence Comes From
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
08
Existing (secondary) sources
Statistical data
Sectoral studies
Reports of international organisations
Strategic documents: national and regional development strategies
Primary data
Surveys
Focus groups
Expert interviews
Aim: a thorough study of the context and of the needs of potential target groups, which is the starting point of project development.
Notes: The development of a project begins with a thorough study of the context and the needs of potential target groups. Sources include statistical data, sectoral studies, reports of international organisations and strategic documents such as national and regional development strategies, as well as primary data obtained through surveys, focus groups and expert interviews. Ask students which sources they would use for a project in their own region.

## Slide 9
2.2 · PROBLEM TREE
The Problem Tree: Structuring Cause and Effect
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
09
EFFECTS
CORE PROBLEM
CAUSES
CAUSES OF CAUSES
Low export revenues of SMEs
Weak competitiveness of regional firms
Slower economic growth of the region
Low level of internationalisation among SMEs in the region
Limited knowledge of foreign markets
Weak export-support services
Limited access to export finance
Few staff with foreign-language and export skills
Low capacity of business associations
Illustrative example built on the core problem cited in the lecture.
1
Core problem: the central negative state the project seeks to overcome
2
Causes: placed below, broken down into levels (causes of causes)
3
Effects: the negative consequences, placed above
4
Logical check: every element is directly linked to the adjacent levels
Notes: The problem tree structures a problem situation and visualises cause-and-effect relationships within the logical framework approach. Steps: formulate the core (focal) problem — the lecture's example is a low level of internationalisation among small and medium-sized enterprises in the region; identify its causes, placed below and broken down into several levels where necessary; identify its effects, placed above; and check logical integrity — every element must stand in a direct cause-and-effect relationship with the adjacent levels. The causes and effects shown are an illustrative example for discussion, not research findings.

## Slide 10
2.3 · OBJECTIVE TREE AND STRATEGY ANALYSIS
From the Problem Tree to the Objective Tree
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
10
PROBLEM TREE · NEGATIVE STATES
OBJECTIVE TREE · DESIRED STATES
EFFECT
Low export revenues of SMEs
EXPECTED BENEFIT
Higher export revenues of SMEs
effects → benefits
CORE PROBLEM
Low level of internationalisation among SMEs in the region
OBJECTIVE
Higher level of internationalisation among SMEs in the region
negative → positive
CAUSE
Limited knowledge of foreign markets
MEANS
Improved knowledge of foreign markets
causes → means
Illustrative example continuing the problem tree on the previous slide.
Strategy analysis
Decide which “branch” of the objective tree the project will cover, having regard to:
the consortium's comparative advantages
its resources
the donor's priorities
Notes: The objective tree is constructed by transforming the problem tree: every negative statement (a problem-state) is reformulated into a positive, desired state (an objective-state). Causes are converted into means of achieving the objective, and effects into expected benefits. The objective tree then supports strategy analysis: the analyst decides which branch the project will cover, having regard to the consortium's comparative advantages, its resources and the donor's priorities. This slide addresses self-check question 1.

## Slide 11
2.4 · TARGET GROUP ANALYSIS
Target Group Analysis: Needs, Profiles and Barriers
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
11
Target groups
Specific needs
Gender
Age
Socio-economic characteristics
Barriers to access
1
Start from the problem tree: who is affected by the core problem?
2
Segment: the population groups or organisations with an interest in resolving the problem
3
Profile each segment: specific needs; gender, age and socio-economic characteristics; barriers to access
Method: gender and social analysis, which reveals potential barriers to accessing the project's benefits.
Notes: On the basis of the problem tree, the population groups or organisations with an interest in resolving the problem are segmented. For each segment we identify specific needs; gender, age and socio-economic characteristics; and potential barriers to accessing the project's benefits. This is the methodology of gender and social analysis.

## Slide 12
03
SECTION 3
Stakeholder Analysis: Identification, Classification, Influence and Engagement
Who are the project's stakeholders, and how are they classified?
How does the power–interest matrix guide engagement?
Why do donor experts assess the quality of this analysis?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
12
Notes: Stakeholder analysis builds on the distinction between beneficiaries, target groups and stakeholders introduced in Lecture 1. It is a systematic process of identifying the relevant parties, assessing their interests, expectations, influence and potential contribution, and determining an engagement strategy for each category.

## Slide 13
3.1 · STAGES OF STAKEHOLDER ANALYSIS
Stakeholder Analysis in Four Stages
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
13
A systematic process of identifying the persons, groups and organisations relevant to a project, assessing their interests, expectations, influence and potential contribution, and determining a strategy for engaging with each category.
Identification
An exhaustive list of potential stakeholders
Classification
Primary or secondary; supporters, neutral parties or opponents
Interests and influence
Assessment with the power–interest matrix
Engagement strategy
Format, frequency and channels of communication for each category
Done well at the design stage, this analysis is a precondition for managing stakeholders during implementation (Topic 7) and a criterion used by donor experts to assess the proposal.
Notes: Four stages: identification (an exhaustive list of potential stakeholders); classification (primary and secondary; supporters, neutral parties and opponents); assessment of interests and influence using the power–interest matrix; and the development of an engagement strategy. High-quality stakeholder analysis carried out at the design stage is a precondition for effective stakeholder management at the implementation stage (Topic 7), and it is a criterion taken into account by donor experts when they assess the quality of a proposal.

## Slide 14
3.1 · IDENTIFICATION AND CLASSIFICATION
Who Are the Stakeholders, and How Are They Classified?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
14
IDENTIFICATION · AN EXHAUSTIVE LIST
Public authorities
Local self-government
Business associations
Academic institutions
Civil-society organisations
Mass media
International partners
Competing initiatives
CLASSIFICATION
By relationship to the project
Primary
Directly affected by the project
Secondary
Intermediaries who influence implementation indirectly
By attitude to the project
Supporters
Neutral parties
Opponents
Each category calls for a different engagement approach.
Notes: Identification should be exhaustive: public authorities, local self-government, business associations, academic institutions, civil-society organisations, the mass media, international partners and competing initiatives. Classification distinguishes primary stakeholders (directly affected by the project) from secondary ones (intermediaries who influence implementation indirectly), and supporters from neutral parties and opponents. Ask students why competing initiatives belong on the list.

## Slide 15
3.1 · ASSESSMENT OF INTERESTS AND INFLUENCE
The Power–Interest Matrix and Engagement Strategies
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
15
POWER / INFLUENCE (LOW → HIGH)
INTEREST (LOW → HIGH)
HIGH POWER · LOW INTEREST
Keep satisfied
Inform them of key decisions.
HIGH POWER · HIGH INTEREST
Key players
Active and continuous engagement.
LOW POWER · LOW INTEREST
Minimal monitoring
Subjects of minimal monitoring only.
LOW POWER · HIGH INTEREST
Keep informed
Keep them informed about the project.
STAGE 4 · ENGAGEMENT STRATEGY
For each category of stakeholder, determine:
Format
How the category is engaged
Frequency
How often communication takes place
Channels
Which means of communication are used
Plan communication for the entire project life cycle, from the active engagement of key players to minimal monitoring.
Notes: The power–interest grid distributes stakeholders across four quadrants. Key players (high power, high interest) require active and continuous engagement; high-power, low-interest stakeholders should be kept satisfied by being informed of key decisions; low-power, high-interest stakeholders should be kept informed; low-power, low-interest stakeholders are subjects of minimal monitoring only. The engagement strategy then determines the format, frequency and channels of communication with each category throughout the entire project life cycle. For self-check question 2: unlike a simple list, the matrix assigns each stakeholder a position and a corresponding intensity of engagement.

## Slide 16
04
SECTION 4
Theory of Change and Intervention Logic
How and why will the expected change occur?
How does the theory of change differ from the logframe?
What is the vertical “if–then” logic of a project?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
16
Notes: The theory of change explains how and why change will occur in a specific context; intervention logic sets out the vertical hierarchy of objectives at the core of the logical framework approach. Both prepare the ground for the logical framework matrix in Section 5.

## Slide 17
4 · THEORY OF CHANGE
Theory of Change: The Pathway from Inputs to Impact
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
17
Theory of Change explains how and why the expected change will occur in a specific context, by explicitly defining the chain of cause and effect.
Inputs
Resources invested in the project
A
Activities
Actions carried out using the inputs
A
Outputs
Immediate products and services
A
Outcomes
Intermediate changes for target groups
A
Impact
Long-term change
A = assumption: a condition necessary for each successive level of the chain genuinely to follow from the preceding one. Identifying assumptions is mandatory.
Notes: Theory of Change (ToC) is a methodology that explains how and why the expected change will occur in a specific context. It explicitly defines the cause-and-effect chain from inputs, through activities, to immediate outputs, intermediate outcomes and, ultimately, long-term impact. The identification of assumptions is mandatory: they are the conditions necessary for each successive level of the chain genuinely to follow from the preceding one.

## Slide 18
4 · TWO COMPLEMENTARY TOOLS
Theory of Change and the Logframe Compared
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
18
Theory of change
Explains how and why change will occur in a specific context
A broader analytical and often visual tool
A diagram with cause-and-effect arrows plus a narrative explanation
Justifies the logic of the project before it is formalised
Logical framework matrix
A structured summary document
A tabular (4×4) representation of the intervention logic
A mandatory element of most grant applications to EU programmes and other donors
Formalises the logic in objectives, indicators, sources and assumptions
vs
Sequence: the theory of change justifies the logic of the project first; the logframe then summarises it in a structured form.
Notes: The logical framework matrix is a structured summary document. The theory of change is a broader analytical and often visual tool — a diagram with cause-and-effect arrows accompanied by a narrative explanation — that justifies the very logic underlying the project even before it is formalised in the logframe. This is the core of self-check question 3.

## Slide 19
4.1 · INTERVENTION LOGIC
Intervention Logic: The Vertical Hierarchy of Objectives
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
19
Overall Objective
(Impact)
Specific Objective / Purpose
(Outcome)
Results
(Outputs)
Activities
(Actions and resources)
THE PROJECT CONTRIBUTES
A long-term, strategic effect achieved together with other initiatives; the project cannot ensure it on its own.
THE PROJECT ACHIEVES
The central element: the direct effect for target groups from using the results. As a rule, formulated in the singular.
THE PROJECT DELIVERS
Specific, measurable products and services, directly controlled by the project team.
THE PROJECT CARRIES OUT
Specific actions undertaken to obtain the results, using defined resources.
Notes: Intervention logic is the vertical hierarchy of objectives at the core of the logical framework approach. The overall objective (impact) is a long-term, strategic effect to which the project contributes together with other initiatives; the project generally cannot ensure it on its own. The specific objective or purpose (outcome) is the central element: the direct effect for target groups resulting from the use of the project's results; as a rule it is formulated in the singular. Results (outputs) are specific, measurable products and services, directly controlled by the project team. Activities are specific actions carried out using defined resources. Invite discussion of self-check question 5: why a single specific objective?

## Slide 20
4.1 · VERTICAL LOGIC
The Vertical “If–Then” Logic
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
20
If activities are implemented, then results are obtained; if results are obtained, then the specific objective is achieved; if the specific objective is achieved, then a contribution is made to the overall objective — each time given the relevant assumptions.
IF Activities
are implemented
+ assumptions
THEN Results
are obtained
+ assumptions
THEN Specific objective
is achieved
+ assumptions
THEN Overall objective
a contribution is made
Each step up holds only if the assumptions at that level hold: external conditions outside the project team's control (Section 5).
Notes: The principle of vertical 'if–then' logic: if activities are implemented (given the relevant assumptions), then results are obtained; if results are obtained (given the assumptions), then the specific objective is achieved; if the specific objective is achieved (given the assumptions), then a contribution is made to the overall objective. Read the staircase from the bottom up, stressing that each step holds only if its assumptions hold.

## Slide 21
05
SECTION 5
The Logical Framework Matrix: Indicators, Sources of Verification and Assumptions
How is the classical 4×4 matrix structured?
What makes an indicator SMART?
When does an assumption become a “killer assumption”?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
21
Notes: The logical framework matrix (logframe) is a tabular representation of a project's intervention logic and a mandatory element of the vast majority of grant applications under EU programmes and other international donors. We examine its 4×4 structure, the SMART requirements for indicators, and the treatment of assumptions and killer assumptions.

## Slide 22
5 · LOGICAL FRAMEWORK MATRIX
The Logframe: A 4×4 Matrix
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
22
A tabular representation of the intervention logic: a mandatory element of the vast majority of grant applications to EU programmes and other international donors.
Intervention Logic | Objectively Verifiable Indicators (OVIs) | Sources of Verification (SoV) | Assumptions
Overall Objective | Impact indicators | Data sources for impact indicators | —
Specific Objective | Performance indicators at the objective level | Data sources, methods and frequency of collection | Assumptions between the specific objective and the overall objective
Results | Indicators at the results level (quantity, quality, timing) | Sources for verifying results | Assumptions between results and the specific objective
Activities | Resources (funds, staff, equipment) | Sources of information on resource expenditure | Assumptions between activities and results
 |  |  | Pre-conditions
Notes: The classical logframe is a 4×4 table: its rows correspond to the four levels of the intervention logic, and its columns to four categories of information — the intervention logic itself, objectively verifiable indicators, sources of verification, and assumptions. At the activities level, the indicators column shows the resources (funds, staff, equipment) and the sources column shows information on resource expenditure. Pre-conditions are placed below the assumptions column. Read the assumptions column diagonally: each assumption links one level to the next one up.

## Slide 23
5.1 · REQUIREMENTS FOR INDICATORS
SMART Indicators with Baseline and Target Values
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
23
S
Specific
States precisely what is measured
M
Measurable
Can be quantified or objectively verified
A
Achievable
Realistic with the available resources
R
Relevant
Linked to the objective or result it tracks
T
Time-bound
Specifies when the value is to be reached
ILLUSTRATIVE EXAMPLE · OBJECTIVE-LEVEL INDICATOR
Number of SMEs in the target region that conclude at least one export contract by the end of the project
Every indicator needs:
12
Baseline
start of the project
40
Target
completion of the project
Notes: Objectively verifiable indicators must meet the SMART criteria: Specific, Measurable, Achievable, Relevant and Time-bound. Every indicator must include a baseline value at the start of the project and a target value for its completion. The indicator and figures shown are an illustrative example only; ask students to formulate an indicator for one result of their own project idea.

## Slide 24
5.2 · ASSUMPTIONS AND RISKS
Assessing Assumptions: Identifying “Killer Assumptions”
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
24
An external factor or condition
Q1
Does it lie outside the direct control of the project team?
Within the team's control: not an assumption
No
Q2
Is it necessary for the transition to the next level of the intervention logic?
Not necessary for the transition: not an assumption
No
Q3
Is its probability of occurrence low and its impact on the project critical?
An assumption: enter it in the fourth column of the logframe
No
Yes
Yes
Yes
Yes
Killer assumption
Revise the project design or develop additional mitigation measures
Assumptions are external factors outside the team's direct control. The link between the logframe and the risk register is examined in Topic 7.
Notes: Assumptions are external factors and conditions that lie outside the direct control of the project team but are necessary for the successful transition from one level of the intervention logic to the next. Assumptions whose probability of occurrence is low but whose impact on the project would be critical are classified as killer assumptions and require either a revision of the project design or the development of additional mitigation measures. For self-check question 4, ask students to propose a killer assumption for a project in cross-border economic cooperation. The relationship between the logframe and the risk register is examined in Topic 7.

## Slide 25
06
SECTION 6
Conformity of the Project Idea with the Priorities of EU Programmes and International Donors
Why can even a flawless idea fail to secure funding?
How is strategic fit with a donor and a call analysed?
Which horizontal priorities apply to almost every EU project?
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
25
Notes: No project idea, however methodologically flawless, will secure funding unless it conforms to the priorities predetermined by a specific donor and a specific call. This section sets out the four elements of strategic fit (alignment) analysis.

## Slide 26
6 · STRATEGIC FIT (ALIGNMENT) ANALYSIS
Four Elements of Strategic Fit Analysis
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
26
1
Study the donor's programming documents: multiannual strategic frameworks, work programmes of funding instruments, thematic priorities of the year or call.
2
Match objectives with call priorities: identify the priority direction (call topic); adapt the wording of the objective and results to the donor's terminology.
3
Analyse horizontal priorities: gender equality, environmental sustainability, digitalisation and non-discrimination.
4
Analyse comparative advantages: why this consortium has the institutional capacity, experience and partner network required.
No project idea, however methodologically flawless, will secure funding unless it conforms to the priorities predetermined by a specific donor and a specific call.
The starting point of alignment analysis
Notes: Strategic fit analysis involves: studying the donor's programming documents (multiannual strategic frameworks such as the EU's Multiannual Financial Framework, the work programmes of specific funding instruments, and the thematic priorities of the given year or call); matching the project's objectives with the priorities of the call and adapting the wording to the donor's terminology; analysing the horizontal (cross-cutting) priorities; and analysing the applicant's comparative advantages — why this particular consortium has the institutional capacity, experience and partner network required.

## Slide 27
6 · FROM DONOR STRATEGY TO PROJECT OBJECTIVES
Aligning the Project Idea with Donor Priorities
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
27
Multiannual strategic framework
e.g. the EU's Multiannual Financial Framework 2021–2027
Work programme of the funding instrument
e.g. Horizon Europe Work Programme 2026–2027
Thematic priorities of the year or call
the call topic to which the idea corresponds
Project objective and results
worded in the donor's terminology
Find the call topic
Determine which priority direction the project idea corresponds to.
Speak the donor's language
Adapt the wording of the objective and results to the donor's terminology.
Conformity with strategic priorities is both a formal eligibility criterion and a substantive award criterion (Topic 3).
Sources: European Commission, “2021–2027 long-term EU budget & NextGenerationEU” (commission.europa.eu); “Horizon Europe work programmes” (research-and-innovation.ec.europa.eu).
Notes: Read the funnel from top to bottom: the multiannual strategic framework sets broad priorities; the work programme of a specific funding instrument translates them into topics; the call defines the thematic priorities of the given year. The team determines which priority direction (call topic) the idea corresponds to and adapts the wording of the objective and results to the donor's terminology. Conformity is both a formal eligibility criterion and a substantive award criterion in the qualitative assessment, examined in Topic 3. Examples on the slide: the current EU Multiannual Financial Framework covers 2021–2027; the Horizon Europe Work Programme 2026–2027 is an instrument-level work programme.

## Slide 28
6 · CROSS-CUTTING REQUIREMENTS
Horizontal Priorities and Comparative Advantages
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
28
HORIZONTAL (CROSS-CUTTING) PRIORITIES
To be taken into account in the vast majority of EU projects, regardless of their thematic focus.
Gender equality
Environmental sustainability
Digitalisation
Non-discrimination
COMPARATIVE ADVANTAGES OF THE APPLICANT
Justify why this particular consortium can implement the project successfully:
Institutional capacity
Experience
Partner network
Notes: Horizontal (cross-cutting) priorities — gender equality, environmental sustainability, digitalisation and non-discrimination — must be taken into account in the vast majority of EU projects regardless of their thematic focus; this answers self-check question 6. The applicant must also justify why this particular consortium possesses the institutional capacity, experience and partner network required for the project's successful implementation.

## Slide 29
SUMMARY
Key Takeaways
Project design turns an idea into a structured, justified concept; errors made at this stage are rarely correctable later.
Problem and objective trees make cause and effect explicit; strategy analysis selects the branch the project will cover.
Stakeholder analysis moves from an exhaustive list, through the power–interest matrix, to an engagement strategy.
The theory of change justifies how and why change will occur; intervention logic sets the vertical “if–then” hierarchy.
The logframe combines objectives, SMART indicators, sources of verification and assumptions; killer assumptions require redesign or mitigation.
Strategic fit with the donor's documents, the call and horizontal priorities is both an eligibility and an award criterion.
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
29
Notes: Summarise the logic of the lecture as a single chain: analyse the problem and the people, build the logic of change, formalise it in the logframe, and align it with the donor's priorities.

## Slide 30
SELF-CHECK
Questions for Self-Assessment
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
30
1
Explain the logic of transforming a problem tree into an objective tree.
2
How does the power-interest matrix differ from a simple list of stakeholders, and what managerial value does it add?
3
What is the fundamental difference between the theory of change and the logical framework matrix?
4
Give an example of a “killer assumption” for a project in the field of cross-border economic cooperation.
5
Why is it recommended that a project's specific objective (Purpose) be formulated in the singular?
6
Which EU horizontal priorities must be taken into account regardless of a project's subject matter?
Notes: These questions follow the order of the lecture. Questions 1, 3 and 6 can be answered directly from the slides; questions 2, 4 and 5 require students to apply the concepts to their own reasoning or examples.

## Slide 31
SOURCES
Recommended Reading
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
31
Aid Delivery Methods. Volume 1: Project Cycle Management Guidelines. European Commission, EuropeAid Cooperation Office.
Handbook on Sustainable Development and the Logical Framework Approach. Swedish International Development Cooperation Agency (Sida).
Guidance on the Use of Theory of Change in International Development. UK Department for International Development / BOND.
PM² Project Management Methodology Guide. European Commission, CoEPM².
Horizon Europe Programme Guide. European Commission, Directorate-General for Research and Innovation.
Notes: The EC PCM Guidelines are the core reference for the logical framework approach; the Sida handbook and the DFID/BOND guidance deepen the logframe and theory of change respectively; the Horizon Europe Programme Guide illustrates how programme priorities are expressed for applicants.

## Slide 32
Thank you for your attention
Questions and discussion
NEXT
Lecture 3. Developing an International Project Proposal and Grant Application
LECTURE 2 · INTERNATIONAL PROJECT ACTIVITY
32