## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 8
Monitoring, Evaluation, Reporting and Sustainability of International Project Results
How projects track progress, assess results against the OECD DAC criteria, report to the donor, secure lasting benefits and close in an orderly way
Content Module 2 · Implementation, Administration and Evaluation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
02
01
Progress monitoring: indicators, baseline, targets, means of verification and evidence-based management
02
Evaluating the relevance, effectiveness, efficiency, impact and sustainability of an international project
03
Interim and final reporting: technical, financial and analytical reports
04
Preparing management decisions based on the results of monitoring and evaluation
05
The sustainability plan, impact pathways, commercialisation, scaling up and institutionalisation of results
06
Project closure, handover of results, archiving of documentation and lessons learned
Notes: This final lecture of the course follows the project from implementation to completion. Sections 1–2 distinguish monitoring from evaluation; Section 3 covers reporting to the donor; Section 4 shows how monitoring and evaluation evidence becomes management decisions; Sections 5–6 deal with what happens to the results after the funding ends and how the project is formally closed.

## Slide 3
01
SECTION 1
Progress Monitoring: Indicators, Baseline, Targets, Means of Verification and Evidence-Based Management
How does monitoring differ from evaluation?
Which elements accompany every monitoring indicator?
How does monitoring data become a basis for management decisions?
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
03
Notes: Monitoring is a systematic, continuous process of collecting and analysing information on the progress of project implementation. Its aim is to track progress against planned indicators and to identify deviations promptly. Unlike evaluation, it is a cross-cutting process that runs throughout the entire life cycle rather than a separate phase (Lecture 1, Section 3).

## Slide 4
1 · TWO COMPLEMENTARY PROCESSES
Monitoring and Evaluation Compared
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
04
Monitoring
Evaluation
Essence
Systematic, continuous collection and analysis of information on progress
Systematic and objective assessment of the project against evaluation criteria
Continuity
Cross-cutting: throughout the entire life cycle, not a separate phase
Periodic: mid-term, final (end-of-project) and ex-post evaluations
Who carries it out
The project team: the persons responsible under the monitoring plan
Generally independent (external) experts, to ensure objective findings
Focus
Progress against planned indicators; prompt identification of deviations
Relevance, coherence, effectiveness, efficiency, impact, sustainability
Main use
Evidence for ongoing management decisions and for reporting
Adjusting strategy (mid-term); measuring long-term impact and sustainability (ex-post)
Notes: Monitoring is a systematic, continuous process of collecting and analysing information on implementation progress; it tracks progress against planned indicators and promptly identifies deviations, and it runs throughout the whole life cycle. Evaluation is the systematic and objective assessment of the relevance, effectiveness, efficiency, impact and sustainability of a project, generally undertaken with the involvement of independent (external) experts to ensure objectivity. Evaluations take place at defined points: mid-term, final and ex-post. This contrast is the subject of self-check question 1.

## Slide 5
1.1 · SYSTEM OF MONITORING INDICATORS
Anatomy of an Indicator: From Baseline to Target
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
05
Each objectively verifiable indicator in the logframe (for results, the specific objective and the overall objective) is accompanied by:
Baseline
Actual value
Interim target
Final target
Deviation
Project start
Time of measurement
Interim stage
Project end
Baseline
The initial state of the indicator at the start of the project, against which progress is measured.
Target
The planned state of the indicator at the end of the project or at an interim stage.
Actual value
The state of the indicator actually achieved at the time of measurement.
Means of verification
The document or instrument confirming the value: a report, a database or survey results.
Notes: Monitoring relies on objectively verifiable indicators defined in the logical framework (Lecture 2, Section 5) for each level of the intervention logic: results, specific objective and overall objective. Each indicator has a baseline (its initial state at the start of the project, against which progress is measured), a target (the planned state at the end of the project or at an interim stage), an actual value (the state achieved at the time of measurement) and a means of verification (the document or instrument confirming the value: a report, a database or survey results). The gap between the actual value and the target at the time of measurement is the deviation.

## Slide 6
1.2 · MONITORING SYSTEM
The Monitoring Plan: A Worked Example
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
06
For each indicator, the plan defines:
Data-collection methodology
Frequency of measurement
Responsible person
Format for presenting results
ILLUSTRATIVE EXAMPLE · HYPOTHETICAL EDUCATIONAL PROJECT, INTERIM MEASUREMENT
Indicator
Baseline
Target
Value achieved
Deviation
Teachers trained in the updated curriculum
Result · MoV: attendance lists, certificates
0
200
150
−50
Partner schools applying the updated curriculum
Specific objective · MoV: school survey
10%
60%
35%
−25 p.p.
Methodological guides published
Result · MoV: the published guides
0
4
4
0
Illustrative example: all figures are hypothetical. Deviation = value achieved − target at the time of measurement; the bar shows progress from baseline to target.
Notes: The monitoring plan defines, for each indicator, the data-collection methodology, the frequency of measurement, the responsible person and the format for presenting results. Results are typically presented as a table: indicator — baseline — target — value achieved — deviation. The figures on the right are purely illustrative, taken from a hypothetical educational project at an interim measurement point. Ask students what the negative deviations might signal and what further information they would need before deciding on corrective measures.

## Slide 7
1.3 · EVIDENCE-BASED MANAGEMENT
From Paper-Based Monitoring to Evidence-Based Management
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
07
Formal (“paper-based”) monitoring
Information is collected mainly as material for reporting to the donor.
Evidence-based management
Monitoring information is used systematically as a direct basis for management decisions.
MANAGEMENT DECISIONS INFORMED BY MONITORING DATA
Adjusting the work plan
For example, revising the timetable of activities (Section 4).
Reallocating resources
For example, reallocating tasks among team members (Section 4).
Revising strategy
For example, reviewing the implementation strategy after a mid-term evaluation (Section 4).
Notes: Contemporary practice in managing international projects involves a shift from formal, paper-based monitoring towards evidence-based management. Under evidence-based management, information gathered during monitoring is used systematically as a direct basis for management decisions — adjusting the work plan, reallocating resources or revising strategy — rather than merely as material for reporting to the donor. Section 4 returns to how such decisions are prepared at different levels of the consortium.

## Slide 8
02
SECTION 2
Evaluating the Relevance, Effectiveness, Efficiency, Impact and Sustainability of an International Project
What are the six OECD DAC evaluation criteria?
When is a project evaluated, and for what purpose?
How does triangulation make evaluation findings more reliable?
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
08
Notes: Evaluation is the systematic and objective assessment of the relevance, effectiveness, efficiency, impact and sustainability of a project. It is generally undertaken with the involvement of independent (external) experts to ensure the objectivity of the findings. The most widely used methodology is that of the OECD Development Assistance Committee (OECD DAC).

## Slide 9
2.1 · OECD DAC EVALUATION CRITERIA
Six Criteria for Evaluating an International Project
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
09
Relevance
“Is the intervention doing the right things?”
Correspondence of the objectives to beneficiaries' needs, the donor's priorities and global development priorities.
Coherence
Added in 2019
“How well does the intervention fit?”
Compatibility of the project with other interventions in the same sector or country.
Effectiveness
“Is the intervention achieving its objectives?”
The degree to which the project's stated objectives and results have been achieved.
Efficiency
“How well are resources being used?”
The relationship between the resources used and the results obtained.
Impact
“What difference does the intervention make?”
Long-term positive and negative, direct and indirect changes brought about by the project.
Sustainability
“Will the benefits last?”
The likelihood that the project's benefits will continue after the end of donor funding.
Guiding questions: OECD DAC, Evaluation Criteria: Adapted Definitions and Principles for Use, DCD/DAC(2019)58/FINAL, adopted 10 December 2019; the original five criteria were set out in the 1991 DAC Principles for Evaluation of Development Assistance. Definitions: lecture text.
Notes: The OECD DAC criteria form the most widely used evaluation methodology. The definitions on the cards follow the lecture; the guiding questions in quotation marks are those published by the OECD DAC in its 2019 revision, which added coherence to the five criteria first set out in the 1991 DAC Principles for Evaluation of Development Assistance. Relevance echoes the application-assessment criterion (Lecture 3, Section 5); efficiency echoes cost-effectiveness (Lecture 3) and financial efficiency (Lecture 4). Self-check question 2 asks students to apply all six criteria to a hypothetical educational project.

## Slide 10
2.2 · TYPES OF EVALUATION BY TIMING
Mid-Term, Final and Ex-Post Evaluation
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
10
Mid-term evaluation
implementation
after completion
WHEN
Midway through the implementation period
PURPOSE
To adjust the subsequent implementation strategy
Final (end-of-project) evaluation
implementation
after completion
WHEN
Immediately after the project's completion
PURPOSE
To assess the completed project against the evaluation criteria
Ex-post evaluation
implementation
after completion
WHEN
Some time, usually several years, after completion
PURPOSE
To measure actual long-term impact and the sustainability of results
Evaluation is generally undertaken with the involvement of independent (external) experts to ensure the objectivity of the findings.
Notes: A mid-term evaluation is carried out midway through the implementation period with a view to adjusting the subsequent strategy. A final (end-of-project) evaluation is carried out immediately after the project's completion. An ex-post evaluation is carried out some time — usually several years — after completion, in order to measure the project's actual long-term impact and the sustainability of its results. In each case evaluation generally involves independent external experts.

## Slide 11
2.3 · DATA COLLECTION METHODS
Combining Methods: Triangulation of Evaluation Data
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
11
Quantitative methods
Analysis of statistical indicators
Structured surveys
Qualitative methods
In-depth interviews
Focus groups
Case studies
Cross-checked findings
Different data sources
Quantitative
Qualitative
Triangulation: the cross-checking of findings on the basis of different sources and methods of data collection, which enhances the reliability of the evaluation's results.
Notes: Evaluation relies on a combination of quantitative methods (analysis of statistical indicators, structured surveys) and qualitative methods (in-depth interviews, focus groups, case studies). Combining them ensures triangulation: the cross-checking of findings on the basis of different sources and methods of data collection. Triangulation enhances the reliability of the evaluation's results — a finding confirmed by several sources and methods is more credible than one resting on a single source.

## Slide 12
03
SECTION 3
Interim and Final Reporting: Technical, Financial and Analytical Reports
What does each type of report contain, and whom does it serve?
Why must the technical and financial reports be fully consistent?
How does the donor review submitted reports?
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
12
Notes: Reporting translates monitoring data into the accountability documents required by the grant agreement. The lecture distinguishes technical (narrative), financial and analytical reports, and then describes how the donor's project officer reviews them. Timely, high-quality reporting matters because approval of an interim report is generally a condition for the next instalment of funding.

## Slide 13
3.1–3.3 · TYPES OF REPORTS
Three Types of Reports and Their Functions
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
13
Technical (narrative) report
Substantive progress: activities, results against planned indicators, deviations and corrective measures, updated risk register.
MAIN AUDIENCE
The donor's project officer
Financial report
Submitted synchronously with the technical report and fully consistent with it (see Lecture 6, Section 5).
MAIN AUDIENCE
The donor's project officer
Analytical reports
M&E reports and thematic briefs that synthesise monitoring data for management analysis and recommendations.
MAIN AUDIENCE
Consortium management; external stakeholders not party to the grant agreement
Schedule set by the grant agreement: interim reports typically annually or at the end of each stage; the final report within a set period after the project's completion.
Notes: The technical (narrative) report describes substantive progress: activities carried out, results achieved against planned indicators, deviations from the work plan with corrective measures, and the updated status of the risk register (Lecture 7, Section 2). The financial report, discussed in detail in Lecture 6 (Section 5), is submitted synchronously with the technical report and must be fully consistent with it. Analytical reports — monitoring and evaluation reports, thematic analytical briefs — synthesise monitoring data for management analysis and recommendations, and communicate results to stakeholders who are not a party to the grant agreement. Reports follow the schedule set by the grant agreement.

## Slide 14
3.1–3.2 · CONSISTENCY OF REPORTS
Technical and Financial Reports Must Tell the Same Story
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
14
Technical (narrative) report
1
Activities carried out
2
Results achieved against planned indicators
3
Deviations from the work plan and corrective measures taken
4
Updated status of the risk register (Lecture 7)
Financial report
Volume of resources actually used
Submitted synchronously with the technical report
Detailed rules and structure: Lecture 6, Section 5
must correspond
The financial report is submitted synchronously with the technical report and must be fully consistent with it: reported progress must match the resources actually used.
Notes: The technical report sets out what was done and achieved; the financial report, submitted at the same time, shows the resources actually used. The two must be fully consistent: the reported progress of activities must correspond to the volume of resources actually used. The detailed rules for financial reporting were covered in Lecture 6 (Section 5). Self-check question 3 asks why this consistency is critical for approval by the donor.

## Slide 15
3.4 · DONOR REVIEW OF REPORTS
How the Donor Reviews Submitted Reports
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
15
Consortium submits the report
Review by the donor's project officer
Approval of the report
Request for clarification or revision
Order of an on-the-spot check
Interim report: generally a condition for the next instalment
The consortium clarifies or revises the report
Because approval of an interim report generally conditions the next instalment of funding, timely and high-quality reporting is critically important.
Notes: Submitted reports are reviewed by the donor's project officer, who may approve the report, send the consortium a request for clarification or revision (a clarification request), or order an on-the-spot check. Approval of an interim report is generally a condition for the disbursement of the next instalment of funding. This is why timely and high-quality reporting is of critical importance for the consortium's cash flow and for the continuity of activities.

## Slide 16
04
SECTION 4
Preparing Management Decisions Based on the Results of Monitoring and Evaluation
Which decisions are taken at the operational and strategic levels?
When does evidence lead to changes agreed with the donor?
Why must management responses be documented?
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
16
Notes: Data gathered through monitoring and evaluation form the direct basis for management decisions at various levels of the consortium: operational, strategic, and in relations with the donor. This section connects the evidence-based management idea from Section 1 with the change-management procedure (Lecture 5) and risk-response planning (Lecture 7).

## Slide 17
4 · LEVELS OF DECISION-MAKING
From Evidence to Decisions at Three Levels
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
17
Operational level
Project manager, working groups
EVIDENCE
Results of ongoing monitoring
POSSIBLE DECISIONS
Adjust the timetable
Reallocate tasks among team members
Activate risk-response plans (Lecture 7)
Strategic level
Consortium steering committee
EVIDENCE
Findings of a mid-term evaluation
POSSIBLE DECISIONS
Review the implementation strategy
Formally revise the logframe or budget via the change-management procedure (Lecture 5)
Relations with the donor
Formal requests to the donor
EVIDENCE
Evaluation conclusions and recommendations
POSSIBLE DECISIONS
Request an extension of the implementation period
Reallocate the budget between budget lines
In extreme cases: early termination by mutual agreement
Notes: At the operational level, the project manager and working groups use ongoing monitoring results to adjust the timetable, reallocate tasks among team members and activate risk-response plans (Lecture 7, Sections 1–2). At the strategic level, the consortium's steering committee may respond to a mid-term evaluation by reviewing the implementation strategy, including a possible formal revision of the logframe or budget through the change-management procedure (Lecture 5, Section 5). In relations with the donor, evaluation conclusions may ground a formal request to extend the implementation period, to reallocate the budget between budget lines or, in extreme cases, to terminate the project early by mutual agreement.

## Slide 18
4 · ACCOUNTABILITY FOR THE USE OF EVIDENCE
The Monitoring, Evaluation and Decision Loop
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
18
Evidence-based management
Monitoring and evaluation data
Analysis of deviations and findings
Decision at the appropriate level
Documented management response
Adjusted plans, resources or strategy
Management responses must be documented:
Minutes of the steering committee
Responses to evaluators' recommendations
This ensures the consortium's accountability for the use of the evidence obtained.
Notes: The loop summarises evidence-based management: monitoring and evaluation data are analysed, a decision is taken at the appropriate level, the management response is documented, and the adjusted plans are monitored in turn. The lecture stresses that management responses to monitoring and evaluation results must be documented — in the minutes of the steering committee and in responses to evaluators' recommendations. Documentation ensures the consortium's accountability for the use of the evidence obtained. Self-check question 4 asks for an example of a decision a steering committee might take after a mid-term evaluation.

## Slide 19
05
SECTION 5
Sustainability Plan, Impact Pathways, Commercialisation, Scaling Up and Institutionalisation of Results
Along which four dimensions is sustainability elaborated?
How does an impact pathway link outputs to long-term impact?
How do commercialisation, scaling up and institutionalisation differ?
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
19
Notes: Sustainability was discussed conceptually in Lecture 3 (Section 1) and as an application-assessment criterion in Lecture 3 (Section 5). At the project-completion stage it is elaborated in practical terms: four dimensions, an impact pathway, strategies for commercialisation, scaling up and institutionalisation, and a sustainability plan that should be started early in implementation.

## Slide 20
5.1 · SUSTAINABILITY OF PROJECT RESULTS
Four Dimensions of Sustainability
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
20
Sustainable project results
Institutional
Partner organisations can continue using and developing the approaches, structures and competencies developed, by their own means.
Financial
A mechanism funds activities after the grant period: own funds, new grants, commercialisation or public funding.
Political / regulatory
Results are embedded in legal and regulatory instruments or strategic documents at the relevant level.
Social
Target groups remain engaged and the community continues to support the results after the active phase.
Implemented through the sustainability plan: measures, responsible parties and timeframes for each dimension (5.4)
Notes: Institutional sustainability is the capacity of partner organisations to continue using and developing the approaches, structures and competencies developed, by their own means. Financial sustainability requires a mechanism for funding activities after the grant period: the organisation's own funds, new grants, commercialisation or public funding. Political or regulatory sustainability means embedding project results in legal and regulatory instruments or strategic documents at the relevant level. Social sustainability is the continued engagement of target groups and community support after the project's active phase.

## Slide 21
5.2 · IMPACT PATHWAY
The Impact Pathway: From Outputs to Long-Term Impact
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
21
Outputs
immediate results
Outcomes
intermediate consequences
Impact
long-term changes
Illustrative example (hypothetical educational project):
An updated curriculum; 200 teachers trained
Partner schools apply the updated curriculum in regular teaching
Improved learning outcomes for pupils in the region
At the sustainability-planning stage
the pathway elaborates the theory of change (Lecture 2) by answering three questions:
Who?
Who will continue to use and disseminate the results after funding ends
How?
In what manner the results will be used and disseminated
Under what conditions?
Which conditions must hold for this to happen
Notes: The impact pathway is the sequence of steps linking the project's immediate results (outputs) to long-term impact through intermediate consequences (outcomes). It elaborates the project's theory of change (Lecture 2, Section 4) at the sustainability-planning stage by answering three questions: who will continue to use and disseminate the project's results after the end of funding, in what manner, and under what conditions. The example row is illustrative and continues the hypothetical educational project used earlier.

## Slide 22
5.3 · PATHWAYS TO SUSTAINABILITY
Commercialisation, Scaling Up and Institutionalisation
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
22
Commercialisation
Project result
Income
Further development
Converting project results into a source of income capable of sustaining their further development.
APPLIES TO
Projects whose product or technology has potential for market application
Scaling up
Pilot
within the project
Wider reach
larger audience or territory
Expanding the reach or geographical coverage of a successful piloted approach to a larger audience or territory.
TYPICALLY THROUGH
New funding or partnership with other organisations
Institutionalisation
Project results
Permanent structures, procedures, policy
Integrating results into the permanent structures, procedures or policy of partner organisations or public authorities.
WHY THE MOST DURABLE
It does not depend on further project funding
Notes: Commercialisation applies to projects whose product or technology has potential for market application: results are converted into a source of income capable of sustaining their further development. Scaling up expands the reach or geographical coverage of a successful approach piloted within the project to a larger target audience or territory, in particular through new funding or partnership with other organisations. Institutionalisation integrates project results into the permanent structures, procedures or policy of partner organisations or public authorities; it is the most durable form of ensuring sustainability because it does not depend on further project funding. Self-check question 5 asks how institutionalisation differs from scaling up.

## Slide 23
5.4 · SUSTAINABILITY PLAN
Building the Sustainability Plan
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
23
Start early
from the first stages of implementation, not at completion
Sustainability plan developed and implemented
First stages of implementation
Project completion
Dimension | Measures | Responsible | Timeframe
Institutional | Partner universities include the teacher-training module in their regular programmes | Partner vice-rectors for education | By the end of year 2
Financial | Cover running costs from partners' own budgets; prepare a follow-up grant application | Coordinator's grants office | Final six months
Political / regulatory | Submit proposals to embed the module in the relevant professional standard | Steering committee | Year 3
Social | Maintain a network of trained teachers with regular exchange events | Dissemination work-package leader | From year 1 onwards
Illustrative example: a hypothetical plan for an educational project. The structure (measures, responsible parties and timeframes for each dimension) follows the lecture.
Notes: The sustainability plan is the practical instrument for implementing these strategies. It defines specific measures, responsible parties and timeframes for each of the four dimensions of sustainability. In accordance with the requirements of most donors, its development should begin not at the completion stage but considerably earlier, from the first stages of implementation. The entries in the table are purely illustrative and continue the hypothetical educational project.

## Slide 24
06
SECTION 6
Project Closure, Handover of Results, Archiving of Documentation and Lessons Learned
What does formal project closure involve?
What is handed over, to whom, and how is documentation archived?
Why document lessons learned if it is not a formal requirement?
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
24
Notes: Project closure is the final phase of the life cycle (Lecture 1, Section 3). It combines formal steps towards the donor, the handover of results to those who will use them, the archiving of documentation for possible checks and audits, and the documentation of lessons learned for future projects.

## Slide 25
6.1 · FORMAL PROJECT CLOSURE
Four Steps of Formal Project Closure
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
25
Final reports
Prepare and submit the final technical and financial reports (Section 3)
Donor confirmation
Formal confirmation that the obligations of the grant agreement have been fulfilled
Final payment
The final payment or, if non-compliance is identified, a financial correction
Formal dissolution
Dissolution of the project team and the consortium's governing bodies
Closure is the final phase of the project life cycle (Lecture 1). Alongside these formal steps, it includes the handover of results, archiving and lessons learned (next slides).
Notes: Formal closure involves preparing and submitting the final technical and financial reports (Section 3); obtaining formal confirmation from the donor that the obligations of the grant agreement have been fulfilled; making the final payment or, if non-compliance is identified, a financial correction; and formally dissolving the project team and the consortium's governing bodies.

## Slide 26
6.2–6.3 · HANDOVER AND ARCHIVING
Handing Over Results and Archiving Documentation
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
26
HANDOVER
Project consortium
Deliverables
Developed systems
Databases
Equipment
Intellectual property rights
Beneficiaries or institutions responsible for further use
Where necessary: training of the receiving party's staff
ARCHIVING
Technical
Financial
Communication-related
Prompt retrieval
A format that allows documents to be found quickly for a subsequent check or audit by the donor
Retention period
For the period established by the contract, in line with the donor's requirements (Lecture 6)
Notes: Handover is the formal transfer of project deliverables, developed systems, databases, equipment and intellectual property rights to the beneficiaries or institutions that will be responsible for their further use, accompanied where necessary by training of the receiving party's staff. In line with the donor's document-retention requirements (Lecture 6, Section 4), the consortium must systematically archive all project documentation — technical, financial and communication-related — in a format that allows prompt retrieval in the event of a later check or audit, for the period established by the contract.

## Slide 27
6.4 · LESSONS LEARNED
Lessons Learned: Building Institutional Memory
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
27
A structured summary of the project's management experience that answers three questions:
1
What worked well and can be replicated in future initiatives?
2
Which approaches proved ineffective, and why?
3
Which external factors most influenced the course of implementation?
Form: a separate section of the final report or a stand-alone document. Not a formal requirement, but a practical instrument.
From one project to the next
Completed project
experience of management
Documented lessons learned
what to replicate, what to avoid
Institutional memory
of the applicant organisation
Next project initiative
of higher quality
Links the completion of one project to the initiation of the next (project portfolio, Lecture 1)
Notes: Lessons learned are a structured summary of the project's management experience: what worked well and can be replicated, which approaches proved ineffective and why, and which external factors most influenced implementation. They are typically documented as a separate section of the final report or as a stand-alone document. This is not a formal requirement but a practical instrument for building the organisation's institutional memory and improving future project initiatives, linking the completion of one project to the initiation of the next (project portfolio, Lecture 1, Section 2).

## Slide 28
6 · SUMMARY
Project Closure Checklist
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
28
Reporting and payment
Final technical and financial reports submitted
Donor confirmation of fulfilled obligations received
Final payment received or financial correction made
Handover
Deliverables, systems and databases handed over
Equipment and intellectual property rights transferred
Receiving staff trained, where necessary
Archiving
Technical, financial and communication files archived
Format allows prompt retrieval for checks or audits
Retention period set by the contract observed
Learning and dissolution
Lessons learned documented
Project team formally dissolved
Consortium governing bodies formally dissolved
Checklist compiled from Section 6 of the lecture (6.1–6.4).
Notes: The checklist brings together the elements of Section 6: formal closure towards the donor, handover of results, archiving and lessons learned. Suggest that students use it to review the closure of a project they know. Every item corresponds to a requirement or recommendation stated in the lecture.

## Slide 29
SUMMARY
Key Takeaways
Monitoring is continuous and cross-cutting: indicators are tracked against baselines and targets and confirmed by means of verification.
Evidence-based management uses monitoring data as a direct basis for decisions, not merely as material for donor reports.
Evaluation applies the six OECD DAC criteria at mid-term, final and ex-post stages, triangulating quantitative and qualitative data.
Technical and financial reports must be timely and fully consistent; interim approval generally conditions the next instalment.
M&E results lead to documented decisions at the operational, strategic and donor-relations levels.
Sustainability is planned early across four dimensions; closure covers final reports, handover, archiving and lessons learned.
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
29
Notes: Use the six takeaways to recap the lecture and, since this is the final lecture, to connect it to the whole course: the logframe indicators designed in Lecture 2 are monitored here, the reports draw on the financial rules of Lecture 6 and the risk register of Lecture 7, and lessons learned feed the next project cycle.

## Slide 30
SELF-CHECK
Questions for Self-Assessment
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
30
1
What is the fundamental difference between monitoring and evaluation in terms of the continuity of the process and the party responsible for carrying it out?
2
Characterise the six OECD DAC evaluation criteria using the example of a hypothetical educational project.
3
Why is the consistency of the technical and financial reports a critically important condition for their approval by the donor?
4
Give an example of a management decision that a consortium steering committee might take on the basis of the results of a mid-term evaluation.
5
How does the institutionalisation of project results differ from scaling up?
6
What practical function does the documentation of lessons learned perform for the applicant organisation?
Notes: These are the lecture's six self-check questions. Question 2 can be worked in small groups, each group taking two criteria; question 4 can draw on the three levels of decision-making in Section 4.

## Slide 31
SOURCES
Recommended Reading
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
31
OECD/DAC Criteria for Evaluating Development Assistance. Organisation for Economic Co-operation and Development.
Aid Delivery Methods. Volume 1: Project Cycle Management Guidelines. European Commission, EuropeAid Cooperation Office.
A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edition. Project Management Institute, 2021.
Model Grant Agreement (Multi-beneficiary General MGA). European Commission, Funding & Tenders Portal.
Better Evaluation. International Network on Evaluation Methodology and Practice — methodological materials on monitoring and evaluation.

## Slide 32
Thank you for your attention
Questions and discussion
NEXT
Practical Session 8: final presentation of group projects and a short written quiz
LECTURE 8 · INTERNATIONAL PROJECT ACTIVITY
32