## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 1
Theoretical and Methodological Foundations of International Project Management
Essence and typology of international projects, the project life cycle, the project environment and core management methodologies
Content Module 1 · Design and Preparation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
02
01
The essence, features and typology of international projects
02
Project, programme and portfolio: the relationship between the concepts
03
The life cycle of an international project
04
The international project environment: donors, partners, beneficiaries, target groups, stakeholders
05
Project management methodologies: PMBOK, PM², PCM and the Logical Framework Approach
06
Managing under uncertainty, intercultural interaction and limited resources
Notes: The lecture moves from the basic concept of a project to the specific conditions under which international projects are managed. Sections 1–4 build the conceptual vocabulary; Section 5 introduces the methodological toolkit; Section 6 explains why international projects demand particular managerial competencies.

## Slide 3
01
SECTION 1
The Essence, Features and Typology of International Projects
What is a project according to international standards?
What makes a project international?
How can international projects be classified?
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
03

## Slide 4
1.1 · THE CONCEPT OF A PROJECT
What Is a Project? Two Standard Definitions
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
04
PMBOK Guide (PMI)
“A temporary endeavour undertaken to create a unique product, service or result.”
A Guide to the Project Management Body of Knowledge, Project Management Institute
ISO 21500:2021
“A unique set of processes consisting of coordinated and controlled tasks with start and finish dates, undertaken to achieve an objective … including constraints on time, cost and resources.”
Project, programme and portfolio management — Context and concepts
Temporariness
Every project has a clearly defined beginning and end.
Uniqueness
The product, service or result differs in some way from all similar ones.
Notes: PMBOK (PMI): a temporary endeavour undertaken to create a unique product, service or result. ISO 21500:2021 adds the dimension of coordinated and controlled tasks and explicit constraints of time, cost and resources. Emphasise the two core attributes: temporariness (defined start and end) and uniqueness (the result differs from all similar products or services).

## Slide 5
1.1 · THE CONCEPT OF A PROJECT
What Makes a Project International?
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
05
An international project is a project that meets four interrelated criteria:
Multinational actors
Donors, implementers, partners and beneficiaries belong to different national jurisdictions.
External funding
Financed wholly or partly from foreign or supranational sources: EU programmes, IFIs, donor funds, diplomatic missions.
Transnational problem
Addresses problems of a cross-border, regional or global dimension.
Capacity development
Develops the capacity of the recipient country in accordance with the donor's priorities.
Example: an Erasmus+ Capacity Building consortium of Ukrainian and EU universities, funded from the EU budget and aimed at modernising higher education, meets all four criteria.
Notes: An international project is implemented with the participation of actors (donors, implementers, partners, beneficiaries) belonging to different national jurisdictions; it is financed wholly or in part from foreign or supranational sources (EU programmes, international financial institutions, donor funds, diplomatic missions); and it is directed towards problems of a cross-border, regional or global dimension, or towards developing the capacity of the recipient country in line with the donor's priorities.

## Slide 6
1.2 · GENERIC FEATURES
Seven Generic Features of Any Project
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
06
Temporariness
A defined start date and end date.
Uniqueness of result
An unrepeatable combination of objectives, context, team and resources.
Purposefulness
All actions serve a predetermined goal measured by indicators.
Resource constraints
A fixed budget, staffing provision and time frame.
Complexity
Competencies from various fields of knowledge must be combined.
Risk and uncertainty
Factors not fully controllable by the project team.
Phased implementation
Sequential progression through life-cycle stages.
+ 4
specific features are added for international projects (next slide)
Notes: Regardless of sector, any project — including an international one — displays these seven features. Ask students to identify each feature in a project they know. Note that even within a standard donor programme every project is an unrepeatable combination of objectives, context, team and resources.

## Slide 7
1.2 · SPECIFIC FEATURES
What International Projects Add to the Generic Features
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
07
Transnationality
The involvement of actors from different countries.
Donor-orientation
Subordination to the donor's requirements and procedures.
Accountability under international standards
Financial and substantive reporting in accordance with EU or other donor rules.
Intercultural character
Communication and management across different cultural traditions.
7 + 4
seven generic features shared by all projects, plus four features specific to international projects
Together they define the managerial profile of an international project.
Notes: To the seven generic features, international projects add four specific ones: transnationality, donor-orientation, accountability under international standards (financial and substantive reporting under EU or other donor rules), and the intercultural character of communication and management.

## Slide 8
1.3 · TYPOLOGY
Classifying International Projects: Five Criteria
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
08
Criterion | Types of international projects
Source of funding | EU programmes · international financial institutions · development agencies and donor funds · diplomatic missions and embassies · international NGOs
Field of implementation | Economic · educational and scientific · infrastructure · humanitarian · environmental · governance and institutional capacity-building · cross-border cooperation
Scale and territorial coverage | Local · regional · national · cross-border · transnational · global
Nature of the result | Investment (capital) · research · consultancy · technical assistance · capacity-building
Number of participants | Bilateral (two-partner) · multilateral (consortium-based), requiring coordination among partners from different countries
Notes: Classification helps to select the appropriate management tools and to identify the relevant donor rules. A single project can be classified simultaneously under all five criteria — for example, an Erasmus+ Capacity Building project is EU-funded, educational, transnational, capacity-building and consortium-based.

## Slide 9
1.3 · TYPOLOGY BY SOURCE OF FUNDING
Who Funds International Projects?
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
09
EU programmes
Horizon Europe, Erasmus+, Interreg, EU4Business and others
International financial institutions
The World Bank, the EBRD, the EIB
Development agencies and donor funds
USAID, GIZ, SIDA, the European Endowment for Democracy
Diplomatic missions
Embassies' small grants projects
International NGOs
Projects of international non-governmental organisations
Each category of donor has its own priorities, procedures and volumes of funding; they are examined in detail in Lecture 4.
Notes: Each category of funder has its own priorities, procedures and scale of funding. EU programmes (Horizon Europe, Erasmus+, Interreg, EU4Business); IFIs (World Bank, EBRD, EIB); development agencies and donor funds (USAID, GIZ, SIDA, the European Endowment for Democracy); embassies (small grants); and international NGOs. Funding sources are examined in detail in Lecture 4.

## Slide 10
02
SECTION 2
Project, Programme, Portfolio: The Relationship Between the Concepts
Why the distinction matters for tools, decisions and reporting
Coordinated benefits versus strategic alignment
“Doing the work right” versus “doing the right work”
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
10

## Slide 11
2 · LEVELS OF MANAGEMENT
Three Levels of Management in International Project Activity
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
11
Portfolio
Projects and programmes grouped by a single organisational strategy
Programme
Related projects managed jointly for synergistic benefits
Project
A temporary endeavour with a specific, measurable result
Portfolio: “doing the right work”
Strategic selection and prioritisation of initiatives in line with the organisation's mission.
Programme: synergy
Aligning project objectives with strategic priorities; allocating resources; managing inter-project dependencies.
Project: “doing the work right”
Adherence to deadlines, budget and scope.
Notes: A project is a temporary endeavour with a specific, measurable result. A programme is a group of related projects managed in a coordinated way to obtain benefits not available from managing them individually — e.g. Horizon Europe, united by the strategic goal of strengthening Europe's scientific and innovation capacity. A portfolio is a collection of projects, programmes and operational activities managed as a group to achieve organisational strategy; its components need not be functionally related (e.g. a university's portfolio of international projects funded by different donors).

## Slide 12
2 · COMPARISON
Project, Programme and Portfolio Compared
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
12
Dimension | Project | Programme | Portfolio
Essence | Temporary endeavour for a specific, measurable result | Group of related projects and programme activities | Collection of projects, programmes and operations
Link between components | — | Functionally interrelated | Not necessarily interrelated; united by strategy
Management focus | Deadlines, budget, scope | Coordination for a synergistic effect | Strategic selection and prioritisation
Example | A single Erasmus+ project | EU framework programme Horizon Europe | A university's portfolio of international projects
The distinction is methodologically fundamental: it determines the choice of management tools, the level at which decisions are taken, and the reporting system.
Notes: Use the table to test understanding: ask students to place the Horizon Europe framework programme, a single Horizon Europe research project, and a university's full set of international projects into the correct column.

## Slide 13
03
SECTION 3
The Life Cycle of an International Project
Six phases from initiation to closure
Correspondence with Project Cycle Management (PCM)
Why the cycle is iterative rather than linear
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
13

## Slide 14
3 · LIFE CYCLE
Six Phases of the International Project Life Cycle
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
14
Initiation
Context analysis, needs of target groups, project idea, fit with donor priorities
Planning
Objectives, logframe, indicators, budget, timetable, risk plan, application
Implementation
Executing activities, using resources, coordinating partners and the team
Monitoring
Systematic tracking of progress against planned indicators
Evaluation
Relevance, effectiveness, efficiency, impact, sustainability
Closure
Final reports, handover of results, archiving, lessons learned
The model is consistent with Project Cycle Management (PCM), used by the European Commission and most donor organisations.
Notes: The model follows the logic of Project Cycle Management (PCM) used by the European Commission and most donors. Walk through each phase, emphasising the documents produced and the decision taken at the end of each phase.

## Slide 15
3 · LIFE CYCLE IN DETAIL
Phases, PCM Equivalents and Key Outputs
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
15
Phase | PCM equivalent | Key content and outputs
1. Initiation | Identification / Programming | Context analysis; problems and needs of target groups; project idea; preliminary fit with donor priorities; go / no-go decision
2. Planning | Formulation / Design | Objectives and results; logical framework matrix; indicators; budget, timetable and risk plan; funding application
3. Implementation | Implementation | Execution of planned activities; use of resources; coordination of partners; management of the team and document flow
4. Monitoring | Cross-cutting process | Systematic tracking of progress against indicators; up-to-date information for management decisions
5. Evaluation | Mid-term, final, ex-post | Systematic, objective assessment of relevance, effectiveness, efficiency, impact and sustainability
6. Closure | Closure | Final reporting; handover of results to beneficiaries; archiving; consolidation of lessons learned
Notes: Evaluation may be mid-term, final or ex-post. Monitoring is shown as a phase for didactic clarity but is in fact a cross-cutting process throughout implementation.

## Slide 16
3 · ITERATIVE MANAGEMENT
The Life Cycle Is Not Strictly Linear
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
16
Iterative management
Initiation
Planning
Implementation
Monitoring
Evaluation
Closure
Monitoring runs in parallel
It accompanies implementation throughout the project instead of following it.
Evaluation feeds back
Evaluation findings may prompt the revision of plans, budgets and activities.
PCM logic
The iterative cycle is embedded in the PCM approach of the European Commission and most donors.
Notes: Monitoring is carried out in parallel with implementation, and the findings of evaluation may prompt the revision of plans. Management is therefore iterative: information from later phases feeds back into earlier ones. Ask: why is monitoring considered a cross-cutting process rather than a separate stage?

## Slide 17
04
SECTION 4
The International Project Environment
Who shapes, funds, implements and benefits from the project?
Distinguishing beneficiaries, target groups and stakeholders
The foundation for stakeholder analysis (Lecture 2)
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
17

## Slide 18
4 · PROJECT ENVIRONMENT
Mapping the Environment of an International Project
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
18
Wider stakeholders
Target groups · beneficiaries
Donor · associated partners
Consortium
The environment is the totality of actors whose interests and resources influence the project or are affected by it.
1
Consortium: the coordinator and partners who implement the work plan
2
Funding and support: the donor and associated partners
3
Direct effect: target groups and beneficiaries
4
Wider stakeholders: public authorities, academia, media, competing initiatives, the public
Notes: The project environment is the totality of actors whose interests and resources influence the project or are affected by it. The map moves from the consortium at the core (coordinator and partners), through the donor and associated partners, to target groups and beneficiaries, and finally the wider stakeholders: public authorities, the academic community, the media, competing initiatives and the general public.

## Slide 19
4 · KEY ROLES
Donor, Coordinator, Partners and Associated Partners
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
19
Donor (funding body)
Provides financial or other resources; sets funding priorities, procedural requirements and criteria for evaluating applications and reports. E.g. the European Commission, EU executive agencies, donor governments, IFIs, private foundations.
Coordinator (lead applicant)
Leads the consortium, bears the principal contractual responsibility to the donor and coordinates the activities of the partners.
Partners (co-applicants)
Implement the project together with the coordinator; each is responsible for a defined part of the work plan.
Associated partners
Join the project without direct funding from the donor, providing expert, advisory or organisational support.
Notes: The donor sets funding priorities, procedural requirements, and criteria for evaluating applications and reports. The coordinator (lead applicant) bears principal contractual responsibility. Partners (co-applicants) are each responsible for a defined part of the work plan. Associated partners join without direct funding, providing expert, advisory or organisational support.

## Slide 20
4 · A FREQUENT SOURCE OF CONFUSION
Beneficiaries, Target Groups and Stakeholders
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
20
Beneficiaries
Persons, groups or organisations receiving direct benefits from the project
Direct beneficiaries: immediate recipients of services or products
Final beneficiaries: broader groups affected indirectly
Target groups
Specific groups on whom the project has a direct, positive effect at the level of the project purpose
The project interacts with them directly during implementation
Stakeholders
All persons, groups or institutions with an interest in the project, influence on it, or affected by it
Public authorities, academia, media, competing initiatives, the public
Distinguishing these roles is essential for a correct stakeholder analysis (Lecture 2) and for constructing the logical framework matrix.
Notes: Direct beneficiaries are the immediate recipients of the project's services or products; final beneficiaries are broader groups on whom the project has an indirect effect. Target groups are affected directly and positively at the level of the project purpose and interact with the project during implementation. Stakeholders is the broadest category. The distinction is essential for stakeholder analysis and for constructing the logframe.

## Slide 21
05
SECTION 5
Project Management Methodologies: PMBOK, PM², PCM and LFA
Four methodological systems coexist in international practice
The choice depends on the donor, the sector and the project type
The logical framework: a common language between applicant and donor
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
21

## Slide 22
5 · PMBOK (PMI, USA)
PMBOK: Ten Knowledge Areas and Five Process Groups
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
22
TEN KNOWLEDGE AREAS
1
Integration management
2
Scope management
3
Schedule management
4
Cost management
5
Quality management
6
Resource management
7
Communications management
8
Risk management
9
Procurement management
10
Stakeholder management
FIVE PROCESS GROUPS
Initiating
Planning
Executing
Monitoring and controlling
Closing
Notes: PMBOK is a universal, sector-neutral methodology, widely applied in the private sector and increasingly in international technical-assistance projects. The classic structure (as presented in the PMBOK Guide up to the 6th edition, 2017) combines ten knowledge areas with five process groups.

## Slide 23
5 · CURRENT DEVELOPMENTS
The Evolution of the PMBOK Guide
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
23
6TH EDITION
2017
Process-based
10
knowledge areas
5
process groups
49
processes
7TH EDITION
2021
Principle-based
12
principles
8
performance domains
8TH EDITION
2025
Integrated: principles + processes
6
principles
7
performance domains
40
processes
Source: Project Management Institute, A Guide to the Project Management Body of Knowledge, 6th (2017), 7th (2021) and 8th (2025) editions.
Notes: 6th edition (2017): process-based — 10 knowledge areas, 5 process groups, 49 processes. 7th edition (2021): principle-based — 12 principles and 8 performance domains. 8th edition (2025): 6 principles (holistic view; focus on value; quality in processes and deliverables; accountable leadership; sustainability; empowered culture), 7 performance domains (governance, scope, schedule, finance, stakeholders, resources, risk), 40 processes embedded in the domains, and 5 focus areas corresponding to the former process groups. Students should be aware which edition a donor or employer refers to.

## Slide 24
5 · PM² (EUROPEAN COMMISSION)
PM²: The European Commission's Project Management Methodology
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
24
Initiating
Planning
Executing
Closing
STANDARDISED ARTEFACTS
Project charter
Project management plan
Issue and decision log
Designed for public and supranational governance; adapted for grant projects under EU programmes.
PM² combines
PMBOK
+
PRINCE2
Developer: Centre of Excellence in Project Management (CoEPM²), European Commission
Notes: PM² was developed by the European Commission's Centre of Excellence in Project Management (CoEPM²) for projects within EU institutions and subsequently adapted for grant projects under Union programmes. It combines elements of PMBOK and PRINCE2 and offers standardised artefacts and a phase structure adapted to public and supranational governance.

## Slide 25
5 · PROJECT CYCLE MANAGEMENT
PCM: Six Phases of the European Commission's Project Cycle
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
25
Programming
Strategic framework and priorities
Identification
Problems, needs and project ideas
Formulation
Detailed design using the LFA (mandatory)
Implementation
Delivery of activities and results
Monitoring
Tracking progress against indicators
Evaluation
Assessment of results and lessons
The Logical Framework Approach is obligatory at the formulation stage — it links the analysis of problems to a structured, measurable project design.
Notes: PCM was introduced by the European Commission for managing external assistance (development and cooperation) projects. It structures the project across six life-cycle phases and requires the mandatory application of the Logical Framework Approach at the formulation stage (highlighted).

## Slide 26
5 · LOGICAL FRAMEWORK APPROACH
LFA: From Analysis to the Logical Framework Matrix
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
26
1
Stakeholder analysis
2
Problem analysis
3
Objectives analysis
4
Strategy analysis
5
Logframe matrix
Hierarchy of objectives | Indicators | Sources of verification | Assumptions
Overall objective | Impact indicators | Statistics, studies | —
Specific objective(s) | Outcome indicators | Surveys, reports | Conditions for contributing to the overall objective
Results | Output indicators | Project records | Conditions for achieving the specific objective
Activities | Means / resources | Costs / budget | Conditions for delivering results
Notes: The LFA involves the sequential analysis of stakeholders, problems, objectives and strategies, followed by the development of the logframe — a table structuring the hierarchy of objectives with indicators, sources of verification and assumptions. It is mandatory in most EU grant calls and serves as a common language between applicant and donor. The logframe is examined in detail in Lecture 2.

## Slide 27
5 · COMPARATIVE OVERVIEW
Four Methodologies at a Glance
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
27
 | Developer | Core structure | Typical use in international projects
PMBOK | Project Management Institute (USA) | Knowledge areas and process groups (principles and performance domains in recent editions) | Universal, sector-neutral; private sector and technical-assistance projects
PM² | European Commission, CoEPM² | Phases: initiating, planning, executing, closing; standard artefacts | EU institutions; grant projects under EU programmes
PCM | European Commission (external assistance) | Six-phase project cycle from programming to evaluation | Development and cooperation projects of the EU and most donors
LFA | Analytical planning method | Analyses of stakeholders, problems, objectives, strategies; logframe matrix | Mandatory in most EU grant calls; common language with donors
Notes: This overview supports the independent work on Topic 1: a comparative analysis of PMBOK, PM² and PCM in the international project environment. Ask students which methodology best suits (a) a USAID technical-assistance project, (b) an Erasmus+ consortium, (c) a private-sector investment project.

## Slide 28
06
SECTION 6
Managing Under Uncertainty, Intercultural Interaction and Limited Resources
Five factors that distinguish international from national projects
Cultural dimensions in a multinational consortium
The specific context of projects implemented in Ukraine
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
28

## Slide 29
6 · SPECIFIC MANAGERIAL CHALLENGES
Five Factors That Shape International Project Management
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
29
Uncertainty and risk
Political instability, exchange-rate fluctuations, legislative change, logistics; additional security risks for projects in Ukraine.
Intercultural interaction
Different managerial traditions, communication styles, time orientations and levels of power distance.
Resource constraints and rigid donor procedures
Fixed budget, eligibility rules, co-financing, tight reporting deadlines, limited reallocation.
Donor–recipient asymmetry
The donor sets the rules of the game; the applicant must demonstrate conformity with them.
Transparency and accountability
Anti-corruption safeguards; prevention of conflicts of interest and double funding; good governance.
Notes: Uncertainty: political instability, exchange-rate fluctuations, legislative change, logistical constraints and — for projects in Ukraine under current conditions — additional security risks (risk management is covered in Topic 7). Resource constraints: fixed budget, strict eligibility rules, mandatory co-financing, tight reporting deadlines, limited flexibility to reallocate between budget lines without prior consent. Asymmetry: the donor sets the rules; the applicant must demonstrate conformity. Transparency: public funds entail anti-corruption safeguards, prevention of conflicts of interest and double funding, and good governance.

## Slide 30
6 · INTERCULTURAL INTERACTION
Power Distance in a Multinational Consortium
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
30
Chart: Power Distance Index (0–100)
| Ukraine | Poland | France | Italy | USA | Netherlands | Germany | United Kingdom | Sweden | Denmark | Austria
Series | 92 | 68 | 68 | 50 | 40 | 38 | 35 | 35 | 31 | 18 | 11
Power distance (G. Hofstede)
High-PDI cultures expect hierarchy and top-down decisions; low-PDI cultures expect consultation and delegation.
Time orientation (E. Hall)
Monochronic cultures follow linear schedules and strict deadlines; polychronic cultures handle tasks in parallel.
The manager must mediate conflict and build trust in distributed teams.
Source: Hofstede Insights, Country Comparison Tool; G. Hofstede, G. J. Hofstede, M. Minkov, Cultures and Organizations (3rd ed., 2010).
Notes: Power Distance Index (Hofstede): the extent to which less powerful members of organisations accept that power is distributed unequally. Ukraine scores 92, markedly higher than most EU partner countries — implications for decision-making, feedback and delegation within consortia. E. Hall distinguishes monochronic cultures (linear scheduling, strict deadlines) from polychronic ones (parallel tasks, flexible time). Scores: Hofstede Insights country comparison tool; Hofstede, Hofstede & Minkov, Cultures and Organizations (2010).

## Slide 31
SUMMARY
Key Takeaways
A project is a temporary endeavour creating a unique result; an international project adds multinational actors, external funding and a transnational dimension.
Seven generic and four specific features define the managerial profile of an international project.
Project, programme and portfolio differ in management level: doing the work right, creating synergy, doing the right work.
The life cycle runs from initiation to closure; monitoring is cross-cutting and management is iterative.
PMBOK, PM², PCM and the LFA coexist; the choice depends on the donor, the sector and the project type.
Uncertainty, cultural diversity, rigid donor rules, asymmetry and accountability demand specific managerial competencies.
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
31

## Slide 32
SELF-CHECK
Questions for Self-Assessment
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
32
1
How does an international project differ from a national (domestic) project in terms of its actors and sources of funding?
2
Give an example of the relationship between a project, a programme and a portfolio of projects, using an EU programme known to you.
3
Why is monitoring considered a cross-cutting process rather than a separate stage of the project life cycle?
4
What is the difference between a beneficiary and a target group of a project?
5
Compare the methodological emphases of PMBOK and PCM: which is more oriented towards international technical-assistance projects, and why?
6
Which factors of uncertainty are specific to international projects implemented in Ukraine?

## Slide 33
SOURCES
Recommended Reading
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
33
A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edition. Project Management Institute, 2021.
PM² Project Management Methodology Guide. European Commission, Centre of Excellence in Project Management (CoEPM²).
Aid Delivery Methods. Volume 1: Project Cycle Management Guidelines. European Commission, EuropeAid Cooperation Office.
ISO 21500:2021 Project, programme and portfolio management — Context and concepts.
The Standard for Program Management. 5th edition. Project Management Institute, 2024.

## Slide 34
Thank you for your attention
Questions and discussion
NEXT
Lecture 2. Project Design: Conceptualisation, Intervention Logic and Project Justification
LECTURE 1 · INTERNATIONAL PROJECT ACTIVITY
34