## Slide 1
INTERNATIONAL PROJECT ACTIVITY · MASTER'S PROGRAMME
Lecture 5
Planning the Implementation of an International Project and Managing the Project Team
The project management plan, scope and schedule, roles and responsibility, consortium coordination and digital tools
Content Module 2 · Implementation, Administration and Evaluation of International Projects

## Slide 2
OVERVIEW
Lecture Plan
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
02
01
The project management plan: content, structure and functions
02
Managing project scope and boundaries: deliverables and the work breakdown structure
03
Scheduling: the Gantt chart, critical path, milestones, deadlines and control points
04
Resources, roles and responsibility: the RACI matrix, team interaction, leadership
05
Coordinating partners, organising meetings, recording decisions and managing change
06
Digital tools for managing international projects
Notes: Once a project has been approved, the consortium must turn its application into a workable management system. Sections 1–3 deal with the planning documents that govern implementation: the project management plan, the scope and the schedule. Sections 4–6 turn to the people who carry out the work and the mechanisms that coordinate them: roles and leadership, meetings and change control, and digital tools. The lecture builds on the WBS and milestones introduced in Lecture 3.

## Slide 3
01
SECTION 1
The Project Management Plan: Content, Structure and Functions
How does the management plan differ from the project proposal?
Which components make up the project management plan?
What functions does the plan perform in a consortium?
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
03
Notes: The Project Management Plan (PMP) is the foundational document that integrates the outputs of all planning processes and defines how the project will be executed, monitored and closed. This section distinguishes it from the funding application and from the Grant Agreement, and reviews its structure and functions.

## Slide 4
1 · THE PROJECT MANAGEMENT PLAN
Proposal Versus Management Plan: Two Different Documents
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
04
Project proposal (application)
A document addressed to the donor
Intended to persuade the donor of the merits of funding
Submitted before the funding decision
Project approved
Project management plan
An internal operational document of the consortium
Details the approaches to implementing an already approved project
Defines how the project will be executed, monitored and closed
The project management plan is the foundational document: it integrates the outputs of all planning processes into a single plan for implementation.
Notes: Unlike the project proposal (application), which is a document intended to persuade the donor of the merits of funding, the project management plan is an internal operational document of the consortium. It details the approaches to implementing a project that has already been approved. It integrates the outputs of all planning processes and defines how the project will be executed, monitored and closed. This slide answers the first self-check question.

## Slide 5
1.1 · STRUCTURE
Components of the Project Management Plan
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
05
Project Charter
Formally authorises the project's start; defines the project manager and their authority
Scope management plan
Project boundaries, the WBS and scope change-control procedures
This lecture · Section 2
Schedule management plan
The calendar schedule and the methodology for updating deadlines
This lecture · Section 3
Cost management plan
The budget and the methodology for controlling expenditure
Examined in Topic 6
Quality management plan
Quality standards for project outputs
Examined in Topic 7
Resource management plan
Allocation of roles and the responsibility matrix
This lecture · Section 4
Communications management plan
Channels, formats and frequency of reporting
Examined in Topic 7
Risk management plan
The risk register and response strategies
Examined in Topic 7
Procurement management plan
Procedures for engaging contractors
Stakeholder management plan
The strategy for engaging with stakeholders
Notes: A typical plan for managing an international project combines the Project Charter, which formally authorises the start of the project and defines the project manager and their authority, with nine subsidiary plans. Three of them are developed further in this lecture (gold icons): scope, schedule and resources. The cost management plan is examined in Topic 6; the quality, communications and risk management plans in Topic 7.

## Slide 6
1.2 · FUNCTIONS
Three Functions of the Project Management Plan
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
06
Integrative
Brings together all aspects of management in a single, coherent document.
Communicative
A shared reference base for all partners, reducing the risk of divergent understandings of tasks.
Control
The baseline against which actual progress and deviations are measured.
DO NOT CONFUSE
Project management plan
Internal, flexible and subject to updating
≠
Grant Agreement with the donor
Amendments require formal approval: a considerably more rigid procedure
Notes: The plan performs three key functions. It is integrative, bringing together all aspects of management in a single, coherent document; communicative, serving as a shared reference base for all consortium partners and reducing the risk of divergent understandings of tasks; and a control tool, serving as the baseline against which actual progress and deviations are measured. It must be distinguished from the Grant Agreement with the donor: the plan is internal, flexible and subject to updating, whereas amendments to the Grant Agreement require formal approval under a considerably more rigid procedure.

## Slide 7
02
SECTION 2
Managing Project Scope and Boundaries
What is — and is not — included in the project's work?
How does scope creep arise, and how can it be prevented?
Which documents form the scope baseline?
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
07
Notes: Scope management is the process of defining and controlling what is, and is not, included within the project's body of work. The section covers the project scope and the danger of scope creep, the project scope statement, and the work breakdown structure with its dictionary, which together form the scope baseline.

## Slide 8
2.1 · PROJECT SCOPE
Scope Creep: How the Work Grows While Resources Stay Fixed
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
08
At the outset
Agreed scope
First additions
Agreed scope
+ extra activity
Gradual expansion
Agreed scope
+ extra activity
+ extra output
+ extra event
Resources and timelines: no corresponding review
Result: budget overruns and schedule delays — among the most common problems in international projects.
Project scope
The totality of work required to produce project outputs with defined characteristics.
Scope creep
The uncontrolled, gradual expansion of work without a corresponding review of resources and timelines.
Prevention
Define the boundaries clearly at the outset; route material changes through formal change control (Section 5).
Notes: The project scope delineates the totality of work required to produce project outputs with defined characteristics. Scope creep is the uncontrolled, gradual expansion of the content of work without a corresponding review of resources and timelines; it is one of the most common causes of budget overruns and schedule delays in international projects. Clearly defining the boundaries at the outset of implementation is a precondition for preventing it; material changes should then pass through the formal change procedure discussed in Section 5. Ask students for an example from a hypothetical project (self-check question 2).

## Slide 9
2.2 · PROJECT SCOPE STATEMENT
The Scope Statement: Drawing the Project Boundary
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
09
ILLUSTRATIVE EXAMPLE
IN SCOPE
OUT OF SCOPE
Training curriculum
Accepted when approved by all partners
Pilot training courses
Accepted when delivered to the target groups
E-learning platform
Accepted when tested by partner institutions
Purchase of equipment
Translation of textbooks
Additional training cycles
1
Principal project outputs the list of deliverables the project must produce
2
Acceptance criteria the conditions under which each output is accepted
3
Explicit exclusions what the project will not do — to prevent divergent stakeholder expectations
Illustrative example: a hypothetical capacity-building project that develops and pilots a training programme.
Notes: The project scope statement details the project boundaries. It includes a list of the principal project outputs, the criteria for their acceptance, and a list of what is explicitly excluded from the project scope. The explicit exclusions matter because they prevent divergent stakeholder expectations. The example on the left is hypothetical: a capacity-building project that develops and pilots a training programme.

## Slide 10
2.3 · WORK BREAKDOWN STRUCTURE
The WBS at the Implementation Stage
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
10
ILLUSTRATIVE EXAMPLE
Capacity-building project
PROJECT
WP1 Management
WP2 Curriculum
WP3 Pilot training
WP4 Dissemination
WORK PACKAGES
2.1 Needs analysis
2.2 Curriculum design
TASKS
2.2.1 Draft modules
2.2.2 Partner review
2.2.3 Final approval
OPERATIONS
detailed at the implementation stage
WBS DICTIONARY
For each element of the structure:
Description of the work
Acceptance criteria
Resources required
Responsible party
Approved scope statement
WBS
WBS dictionary
+
+
=
Scope baseline the benchmark for controlling changes
Notes: The methodology for constructing the WBS was examined in Lecture 3. At the implementation stage it is elaborated down to the level of the specific operations required to complete each task within a work package. The WBS Dictionary accompanies it and, for each element, defines the description of the work, the acceptance criteria, the resources required and the responsible party. The approved project scope statement, the WBS and the WBS dictionary together form the scope baseline, the benchmark for controlling changes throughout implementation.

## Slide 11
03
SECTION 3
Scheduling: Gantt Chart, Critical Path, Milestones and Control Points
How are the sequence and duration of activities determined?
Why does the critical path set the minimum project duration?
How are milestones and control gates used during implementation?
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
11
Notes: Scheduling turns the WBS into a timetable. The section moves from dependencies and duration estimates to the Gantt chart, the critical path method, and the use of milestones and control gates for monitoring implementation. One hypothetical 12-month project is used throughout the section so that the Gantt chart and the network diagram can be compared.

## Slide 12
3.1 · SEQUENCE AND DURATION
Determining the Sequence and Duration of Activities
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
12
LOGICAL DEPENDENCIES
DURATION ESTIMATING
Finish-to-start (FS)
B can start only after A finishes
A
B
Start-to-start (SS)
B can start only after A starts
A
B
Finish-to-finish (FF)
B can finish only after A finishes
A
B
Expert judgement
Drawing on the experience of specialists
Analogous estimating
Using the durations of similar past activities as a reference
Three-point estimating (PERT)
Combining optimistic, most likely and pessimistic estimates
Work breakdown structure
Logical dependencies
Duration estimates
Project network diagram
Notes: On the basis of the WBS, the logical dependencies between activities are determined: finish-to-start, start-to-start and finish-to-finish. The duration of each activity is then estimated by expert judgement, analogous estimating, or three-point estimating using the PERT method. On this basis the project network diagram is constructed. Finish-to-start is the most intuitive type: the pilot training cannot begin until the curriculum is finished.

## Slide 13
3.2 · THE GANTT CHART
The Gantt Chart: Visualising the Work Plan
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
13
ILLUSTRATIVE EXAMPLE
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
Activity
A Needs analysis
2 months
B Curriculum development
3 months
C E-learning platform set-up
2 months
float
D Pilot training courses
4 months
E Trainer guidebook
2 months
float
F Evaluation and dissemination
3 months
Milestones
MS1
MS2
MS3
MS4
Critical path activity
Non-critical activity
Float (slack)
Milestone
Illustrative example: a hypothetical 12-month capacity-building project; durations in months.
Notes: The Gantt chart is a horizontal bar chart: activities are arranged along the vertical axis, the time scale along the horizontal axis, and the duration of each activity is shown as a bar of corresponding length. It is the most widely used tool for visualising the work plan in project applications and reports, because it is clear to stakeholders without specialised project management training. In this hypothetical example the gold bars form the critical path (A–B–D–F); activities C and E have float. Diamonds mark milestones at the end of months 2, 5, 9 and 12.

## Slide 14
3.3 · THE CRITICAL PATH METHOD
The Critical Path Sets the Minimum Project Duration
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
14
ILLUSTRATIVE EXAMPLE
Start
End
A 2 months
Needs analysis
Float: 0
B 3 months
Curriculum development
Float: 0
C 2 months
E-learning platform
Float: 1 month
D 4 months
Pilot training
Float: 0
E 2 months
Trainer guidebook
Float: 2 months
F 3 months
Evaluation and dissemination
Float: 0
Critical path (zero float)
Non-critical links (activities with float)
PATHS THROUGH THE NETWORK
A → B → D → F
12 months · the critical path
A → C → D → F
11 months · C has 1 month of float
A → B → E → F
10 months · E has 2 months of float
A delay to A, B, D or F delays the whole project; C and E can slip within their float.
Notes: The critical path is the longest sequence of logically linked activities in the project network diagram; it determines the minimum possible duration of the entire project. Activities on the critical path have zero float: any delay directly extends the project completion date. Activities off the critical path have slack that does not affect the final deadline. In this hypothetical example, the path A–B–D–F takes 12 months; a one-month delay to C is absorbed, but a one-month delay to B moves the end date. Identifying the critical path tells the manager where to focus attention (self-check question 3).

## Slide 15
3.4 · MILESTONES AND CONTROL POINTS
Milestones and Control Gates During Implementation
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
15
ILLUSTRATIVE EXAMPLE
Analysis and design
Pilot
Evaluation and dissemination
Month 0
Control gate: proceed to the pilot?
Control gate: proceed to the final phase?
MS1 Needs analysis completed
MS2 Curriculum approved
MS3 Pilot completed
MS4 Final results delivered
Milestones: a signal
Whether a milestone is reached on schedule tells project management and the donor how implementation is progressing.
Control gates: a decision
Planned decision points, such as moving to the next phase, often linked to assessing interim results and adjusting the plan.
Notes: Milestones, examined in Lecture 3, are used during implementation for ongoing progress monitoring: whether a milestone is reached on schedule is a signal to project management and the donor regarding the state of implementation. Control gates are planned decision points, for example a decision on moving to the next phase of the project. They are often linked to the assessment of interim results and, where necessary, to adjustment of the plan. In the hypothetical timeline, the gate at month 5 decides whether the pilot can start on the basis of the approved curriculum.

## Slide 16
04
SECTION 4
Managing Resources, Roles and Responsibility
How does the RACI matrix prevent accountability gaps?
What shapes teamwork in a distributed international consortium?
What kind of leadership does an international project require?
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
16
Notes: This section moves from documents to people. It introduces the responsibility assignment (RACI) matrix, the specific features of team interaction in an international consortium, and the leadership role of the project manager or coordinator.

## Slide 17
4.1 · RESPONSIBILITY ASSIGNMENT MATRIX
RACI: Four Roles for Every Task
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
17
R
Responsible
The party directly responsible for carrying out the task.
Performs the work
A
Accountable
Bears ultimate responsibility for the outcome and approves it.
Exactly one per task
C
Consulted
Consulted before or during the performance of the task.
Two-way communication
I
Informed
Informed of the progress or outcome of the task.
One-way communication
Built at the implementation-planning stage, the RACI matrix prevents duplication of functions and “accountability gaps”: tasks for which no member of the consortium considers themselves responsible.
Notes: The RACI matrix defines, for each task or project output, the role of each team member or consortium partner. R (Responsible) is the party directly responsible for carrying out the task. A (Accountable) bears ultimate responsibility for the outcome and approves it; there must be exactly one A for each task. C (Consulted) involves two-way communication before or during the task; I (Informed) involves one-way communication about progress or outcome. Built at the implementation-planning stage, the matrix prevents duplication of functions and accountability gaps.

## Slide 18
4.1 · RACI IN PRACTICE
A RACI Matrix for an International Consortium
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
18
ILLUSTRATIVE EXAMPLE
Task / output | Project manager | WP leader | Partner teams | Financial officer | Steering Committee
Interim report to the donor | A | R | C | R | I
Training curriculum (WP2 output) | C | A | R | — | I
Partner financial statements | I | — | R | A | —
Budget reallocation request | R | C | C | C | A
Dissemination event | C | A | R | I | I
Read across each row: exactly one A per task, and at least one party responsible for doing the work — no duplication, no accountability gaps.
Notes: This hypothetical matrix shows how RACI roles are distributed across consortium actors. Row 1 answers self-check question 4: the project manager is Accountable for the interim report and approves it, while the WP leaders and the financial officer are Responsible for preparing its sections. Several parties may be Responsible, but each row has exactly one A. Note that the budget reallocation request is approved by the Steering Committee, anticipating the change procedure in Section 5.

## Slide 19
4.2 · TEAM INTERACTION
Team Interaction in a Distributed Consortium
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
19
WHAT SHAPES TEAMWORK
Geographical dispersion
Partners in different countries form a distributed, virtual team.
In-person and remote coordination
Face-to-face and remote forms of coordination have to be combined.
Different organisational cultures
Partner institutions bring their own organisational cultures.
Team charter (ways of working)
Rules of cooperation agreed at the outset of implementation
The working language of communication
Communication channels
The frequency of meetings
The decision-making procedure
Notes: Team interaction in an international project is shaped by the geographical dispersion of partners, which makes the team a distributed or virtual one; by the need to combine in-person and remote coordination; and by differences in the organisational cultures of partner institutions. Effective interaction rests on clearly defined rules of cooperation, a team charter or ways of working, agreed at the outset of implementation. It covers the working language, the communication channels, the frequency of meetings and the decision-making procedure.

## Slide 20
4.3 · LEADERSHIP
The Project Manager: Administrator and Leader
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
20
Administrative management
Planning
Control
Reporting
Leadership
Motivating the team
Managing change
Mediating conflicts (Topic 7)
Project manager
Situational leadership
The ability to adapt one's leadership style to the cultural expectations of partners from different countries: of particular importance in an international context.
External representation
Representing the consortium before the donor and external stakeholders
Notes: The manager of an international project (project manager or coordinator) combines administrative management — planning, control and reporting — with leadership: motivating the team, managing change, mediating conflicts (examined in detail in Topic 7) and representing the consortium before the donor and external stakeholders. In an international context, situational leadership takes on particular importance: the ability to adapt one's leadership style to the cultural expectations of partners from different countries.

## Slide 21
05
SECTION 5
Coordinating Partners, Meetings, Decisions and Change
Which bodies govern an international consortium?
What types of meetings structure implementation?
How are decisions recorded and changes controlled?
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
21
Notes: Coordination turns a group of partner institutions into a functioning consortium. This section covers the typical governance structure, the cycle of consortium meetings, the recording of decisions in minutes, and the formal procedure for managing change.

## Slide 22
5.1 · CONSORTIUM COORDINATION MECHANISMS
Three Tiers of Consortium Governance
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
22
Steering Committee
Representatives of all partners
Project Management Team
Coordination group
Working group
WP1
Working group
WP2
Working group
WP3
Working group
WP4
Strategic level
The highest body for strategic decision-making, with the participation of all partners.
Operational level
The operational body responsible for day-to-day management of the project.
Thematic level
Working groups formed around individual work packages.
Notes: A typical organisational structure for managing an international consortium has three tiers. The Steering Committee is the highest body for strategic decision-making, with representatives from all partners. The coordination group or Project Management Team is the operational body responsible for day-to-day management. Thematic working groups are formed around individual work packages.

## Slide 23
5.2 · ORGANISING CONSORTIUM MEETINGS
The Meeting Cycle of an International Consortium
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
23
Periodic coordination meetings (monthly or quarterly)
Kick-off meeting
Interim meeting
Interim meeting
Final meeting
Kick-off meeting
At the start of implementation: agree working procedures; partners become acquainted.
Coordination meetings
Periodic (monthly or quarterly) meetings for monitoring progress.
Interim and final meetings
Timed to the completion of project phases or reporting periods.
EVERY MEETING
Predetermined agenda
Meeting
Minutes
Notes: The kick-off meeting is held at the start of implementation to agree working procedures and to enable partners to become acquainted with one another (self-check question 5). Periodic coordination meetings, monthly or quarterly, monitor progress. Interim and final meetings are timed to coincide with the completion of project phases or reporting periods. Every meeting requires a predetermined agenda and concludes with minutes.

## Slide 24
5.3 · RECORDING DECISIONS
Minutes of Meeting: An Audit Trail of Decisions
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
24
ILLUSTRATIVE EXAMPLE
MINUTES OF MEETING
Consortium coordination meeting
1
Participants
Representatives of partners P1–P5
2
Matters discussed
Progress of WP2; preparation of the interim report
3
Decisions taken
Pilot training courses start in Month 6
4
Action items
Action | Responsible | Deadline
Circulate the draft curriculum | WP2 leader | Month 5
Submit partner financial statements | All partners | Month 6
WHY SYSTEMATIC MINUTES MATTER
Internal coordination
All partners work from one record of what was decided.
Clear follow-up
Every action item names a responsible party and a deadline.
Donor checks
An audit trail of management decisions for potential checks by the donor.
Notes: The minutes of meeting record the participants, the matters discussed, the decisions taken, and a list of action items, each with a responsible party and a deadline. Systematic minute-taking provides an audit trail of management decisions. This matters both for the internal coordination of the consortium and for potential checks by the donor. The document on the left is a hypothetical example.

## Slide 25
5.4 · CHANGE MANAGEMENT
A Formalised Change Management Procedure
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
25
Trigger: any material change to the project's
Scope
Budget
Timeline
1
Change request
Submission of a formal change request
2
Impact assessment
Assessment of its impact on other elements of the project
3
Approval
By an authorised body of the consortium, typically the Steering Committee
4
Donor agreement
Where necessary: a formal amendment to the Grant Agreement
The consortium may update its internal management plan, but an amendment to the Grant Agreement requires the donor's formal approval under a considerably more rigid procedure.
Notes: Any material change to the scope, budget or timeline of the project must go through a formalised change management procedure. A change request is submitted; its impact on other elements of the project is assessed; it is approved by an authorised body of the consortium, typically the Steering Committee; and, where necessary, it is agreed with the donor by way of a formal amendment to the Grant Agreement. This links back to Section 1: the management plan can be updated internally, but the Grant Agreement cannot.

## Slide 26
06
SECTION 6
Digital Tools for Managing International Projects
Which categories of digital tools support consortium work?
How does a consortium agree on its toolset?
Which data-protection requirements must be taken into account?
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
26
Notes: Contemporary practice in managing international projects involves the widespread use of digital tools. The section groups them by function and then discusses how the consortium selects its toolset, with regard to the donor's requirements on cybersecurity and personal data protection.

## Slide 27
6 · DIGITAL TOOLS
Digital Tools Grouped by Function
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
27
Scheduling and task tracking
Gantt charts, task assignment and monitoring of deadlines.
e.g. Microsoft Project, Smartsheet, Asana, Trello, Monday.com
Communication and video conferencing
Prompt coordination of distributed teams.
e.g. Microsoft Teams, Slack, Zoom, Google Meet
Collaborative document editing
Simultaneous editing of project documentation by partners in different countries.
e.g. Google Workspace, Microsoft SharePoint, OneDrive
Grant management platforms
Donor portals with modules for reporting, document management and contact with the project officer.
e.g. EU Funding & Tenders Portal
Risk and quality management
Electronic risk registers and document version-control systems.
Data visualisation and reporting
Analytical reports based on monitoring indicators (Topic 8).
e.g. Power BI, Google Data Studio / Looker Studio
Notes: Digital tools may be broadly grouped into six categories: scheduling and task tracking; team communication and video conferencing; collaborative document editing; specialised grant management platforms such as donor portals, in particular the EU Funding & Tenders Portal; risk and quality management tools such as electronic risk registers and document version control; and data visualisation and reporting tools for analytical reports based on monitoring indicators (Topic 8). The products named are examples mentioned in the lecture, not recommendations.

## Slide 28
6 · SELECTING THE TOOLSET
Agreeing the Toolset: Security and Data Protection
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
28
1
Agreed at the kick-off meeting: partners choose one common set of tools
2
Enshrined in the communications management plan: the toolset becomes part of the plan
3
Checked against donor requirements: cybersecurity and the protection of personal data
For projects involving partners from the EU, the General Data Protection Regulation (GDPR) applies.
GDPR · REGULATION (EU) 2016/679
Principles for processing personal data (Art. 5)
Lawfulness, fairness and transparency
Purpose limitation
Data minimisation
Accuracy
Storage limitation
Integrity and confidentiality
Accountability
Source: European Commission, “Legal framework of EU data protection” and “Principles of the GDPR”; European Data Protection Board, GDPR Article 5. Applicable since 25 May 2018.
Notes: The choice of digital tools within a consortium is, as a rule, agreed at the kick-off meeting and enshrined in the communications management plan. It must take into account the donor's requirements concerning cybersecurity and the protection of personal data, in particular the General Data Protection Regulation (GDPR) for projects involving partners from the EU. The GDPR is Regulation (EU) 2016/679; it has applied since 25 May 2018, and Article 5 sets out seven principles for processing personal data (sources: European Commission; European Data Protection Board). This supports self-check question 6.

## Slide 29
SUMMARY
Key Takeaways
The project management plan is the consortium's internal operational document; it integrates all subsidiary plans and has integrative, communicative and control functions.
A scope statement with explicit exclusions, the WBS and the WBS dictionary form the scope baseline, the safeguard against scope creep.
The Gantt chart makes the schedule clear to all stakeholders; the critical path, with zero float, sets the minimum project duration.
Milestones signal the state of implementation to management and the donor; control gates are planned decision points.
A RACI matrix with exactly one A per task, a team charter and situational leadership hold a distributed team together.
Governance bodies, minuted meetings, formal change control and an agreed, data-protection-compliant toolset keep the consortium coordinated.
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
29
Notes: Use the takeaways to recap the logic of the lecture: plan, scope and schedule define what will be done and when; roles, leadership and coordination mechanisms define who does it and how decisions are taken.

## Slide 30
SELF-CHECK
Questions for Self-Assessment
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
30
1
How does the project management plan differ from the project proposal submitted to the donor?
2
Give an example of “scope creep” in a hypothetical international project and explain how it can be prevented.
3
Why is identifying the critical path important for the manager of an international project?
4
Explain the distinction between the R and A roles in the RACI matrix, using the example of preparing the consortium's interim report.
5
What function does the consortium's Kick-off Meeting perform?
6
What data-protection requirements should a consortium take into account when selecting digital coordination tools?
Notes: Questions 2 and 4 can be worked on in small groups: one group describes a scope creep scenario and the change procedure that would stop it; another fills in a RACI row for the interim report.

## Slide 31
SOURCES
Recommended Reading
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
31
A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edition. Project Management Institute, 2021.
PM² Project Management Methodology Guide. European Commission, CoEPM².
Practice Standard for Work Breakdown Structures. 3rd edition. Project Management Institute.
Verzuh E. The Fast Forward MBA in Project Management. Wiley.
Model Grant Agreement (Multi-beneficiary General MGA). European Commission, Funding & Tenders Portal.

## Slide 32
Thank you for your attention
Questions and discussion
NEXT
Lecture 6. Financial Management, Budgeting and Administration of International Projects
LECTURE 5 · INTERNATIONAL PROJECT ACTIVITY
32